## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/1205r2
Venue Date: | July 2017
First Author: | Yunsong Yang (Huawei Technologies)
Subject: | Comments from 3rd Recirculation Sponsor Ballot (SB3) on P802.11aq D10.0
Full Date: | 2017-08-16
Author(s): | Name(s) | Yunsong Yang
| Company | Huawei Technologies
Address
Phone:
Fax:
| email: | yangyunsong@huawei.com
Abstract:
This document records the 47 comments (numbered as CIDs 9001 - 9047) received from the 3rd Recirculation Sponsor Ballot (SB3) on P802.11aq D10.0 and any resolutions approved by 802.11 TGaq (CRC). The comments are organized as follows: A tab for all SB3 comments; and
A tab per comment group for SB3 comments:
Tabs named with clause # or techical subject are for coments not ready-for-motion.
Tabs named with a date are for comments that are ready-for-motion or approved.
Mappig of CID numbers of all previous and current WG LBs and SBs are as follows:
Draft 1.0, LB208 (Initial WG Ballot, failed) CIDs 1001 to 1801
Draft 3.0, LB216 (Initial WG Ballot, passed) CIDs 2000 to 2399
Draft 4.0, LB219 (First Recirc) CIDs 3001 to 3071
Draft 5.0, LB221 (Second Recirc) CIDs 4001 to 4065
Draft 6.0, LB222 (Third Recirc) CIDs 5001 to 5043 Draft 7.0, LB1000 (Initial Sponsor Ballot) CIDs 6001 to 6235
Draft 8.0, LB2000 (First Recirc Sponsor Ballot) CIDs 7001 to 7175
Draft 9.0, LB3000 (2nd Recirc Sponsor Ballot) CIDs 8001 to 8075
Draft 10.0, LB4000 (3rd Recirc Sponsor Ballot) CIDs 9001 to 9047

## Revision History
Revision | Date | Description
0 | 2017-07-31 | Initial export from DB with all Type "E" CIDs assigned to the Editor.
1 | 2017-08-11 | Produced after TGaq teleconference on August 11th; created a new Tab "2017-08-11-telco" for 10 CIDs that are marked as ready for motion, in preparation for motion to approve them in a future teleconference.
2 | 2017-08-16 | Updated with the resolutions to 25 editorial comments under the Editor's Ad-hoc (Tab "Editorial"), in preparation for motion to approve them in a future teleconference.

## All SB3 Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
9001 | Montemurro, Michael | 4000 | 10 | 4.5.9.2.5 | 21 | 12 | T | No | 21 | 12 | 4.5.9.2.5 | [5 empty] | The subclause does not really describe what the SIC is The SIC allows applications to exchange pre-association service discovery requests and responses | Replace "The SIC initiates service discovery. Within a STA this exchange includes supporting service discovery requests and responses to and from applications. The SME determines whether to use unsolicited PAD or solicited PAD procedures. The SME also creates the contents of the ANQP requests." with "The SIC initiates service discovery. The SIC exchanges service discovery requests and responses between the SME and applications. The SME determines whether to use unsolicited PAD or solicited PAD procedures. The SME also composes ANQP requests for solicited PAD procedures." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9002 | Montemurro, Michael | 4000 | 10 | 6.3.73.3 | 26 | 15 | T | No | 26 | 15 | 6.3.73.3 | [5 empty] | The confirm needs a GAS Extensions (but not GA Mode) | Add the GAS Extensions parameter to MLME-GAS.confirm. |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9003 | Montemurro, Michael | 4000 | 10 | 6.3.73.2.2 | 25 | 2 | T | No | 25 | 2 | 6.3.73.2.2 | [5 empty] | The description for GAS Extensions is not correct. | At 25.43 and 28.62 change "Specifies the GAS extension for a transmitting STA that supports group address GAS frames." to "Specifies GAS extensions information for GAS frames." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9004 | Montemurro, Michael | 4000 | 10 | 9.4.2.219 | 40 | 12 | T | No | 40 | 12 | 9.4.2.219 | [5 empty] | The field order and naming for the sub-fields do not really make sense. The Group-addressed GAS and Fragment Transmission Flag fields indicate enabled features, while the remainder of the sub-fields indicate the presents of other subfields. | Change "Fragment Retransmission Flag" to "Fragment Retransmission" at 41.1, 58.8, 59.4, and 59.18. Move the "Fragment Retransmission" sub-field from B4 to B1, and shift all other fields to the right 1 bit in Figure 9-589cj. Move the last paragraph on p40 before the paragraph "The Maximum Channel Time ...." on the same page. |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9005 | Montemurro, Michael | 4000 | 10 | 11.25.3.2.4 | 59 | 17 | T | No | 59 | 17 | 11.25.3.2.4 | [5 empty] | The wording of this paragraph could be improved. | Change "If the corresponding GAS Initial Response frame doesn't contain a GAS Extension element or the Fragment Retransmission Flag subfield in the GAS Extension element in the corresponding GAS Initial Response frame is equal to 0, the requesting STA shall not use a GAS Comeback Request frame to request the retransmission of the GAS Query Response fragment." to "If the corresponding GAS Initial Response frame does not contain a GAS Extension element or the value of the Fragment Retransmission Flag subfield in the GAS Extension element is equal to 0, the requesting STA shall not request the retransmission of a GAS Query Response fragment using a GAS Comeback Request frame." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9006 | Lepp, James | 4000 | 10 | 11.25a.4 | 64 | 31 | E | No | 64 | 31 | 11.25a.4 |  | A | Lee Armstrong |  |  | The final sentance in 11.25a.4 ends in a semicolon. | Change semicolon to a period to end the sentance. | ACCEPTED (EDITOR: 2017-08-16 13:28:10Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9007 | Lepp, James | 4000 | 10 | 10.25a.4 | 69 | 31 | E | No | 69 | 31 | 10.25a.4 |  | A | Lee Armstrong |  |  | Final sentence of 10.25a.4 the term "map into" doesn't seem right. | Change to: and the service hash used as input to compute the Bloom Filter Bit Array field is "0xbfd39037d25c" | ACCEPTED (EDITOR: 2017-08-16 13:29:49Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9008 | Thomas, Angela | 4000 | 10 | 12.2.10 |  |  | G | No |  |  | 12.2.10 |  | J |  |  |  | (Comment received from the IEEE-SA RAC) 12.2.10 Requirements for support of MAC privacy enhancements To set a random MAC address, a STA shall assign a random 48-bit value and then shall set the sixth bit of the first octet to one (indicating a locally administered MAC address) and the seventh bit of the first octet to zero (indicating unicast). Using 46 bits of randomness ensures that the probability of random MAC address collision on even the largest networks remains acceptably small. As an aside, this is a different than the 44 bits implicitly allowed to be randomized in P802c. 1. Random MAC address assignment would seem to be out-of-scope for the PAR. The Project Scope reads: "This amendment defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to enable delivery of pre-association Service Discovery information discovery by IEEE 802.11 stations (STAs)." By extension, the ballot group therefore would not include all interested parties -- typically a concern for RevCom. 2. The CSD are not linked on the 802.11 PAR page, and I didn't do a search of mentor for the CSD, but I expect the answer on compatibility with Std 802 was probably generic, and the random assignment quoted above certainly is not compatible with the optional capabilities of Std 802c. |  | REJECTED (GEN: 2017-08-04 17:49:17Z) - No proposed change is required. The following is a response to the comment: The group considers that randomizing the MAC address, as described in clause 12.2.10, is a perfectly reasonable part of the pre-association discovery scope. This avoids revealing privacy compromising information to STAs that are observing the 802.11aq traffic. This is inline with IEEE Std 802c, clause 8.4.1 that states "The locally administered bits of local MAC addresses are arbitrarily assignable under the condition that local MAC addresses are unique within a LAN (which may be a bridged LAN or virtual bridged LAN) unless they are assigned to distinct VLANs in which bridges support Independent VLAN Learning, per Annex F.1.2 ("Duplicate MAC Addresses") of IEEE Std 802.1Q. Any failure of such uniqueness invalidates the fundamental premises of IEEE 802 network operation and may lead to disruption." Furthermore, IEEE Std 802c, clause 8.4.5 also states "In some cases, administrators may wish to assign local MAC addresses in an arbitrary fashion (for example, randomly) and yet maintain compatibility with other assignment protocols operating on the same LAN. For such purposes, a local MAC address may be assigned as an Administratively Assigned Identifier (AAI)." IEEE Std 802c provides compatibility for users of the local address spaces and it enables local administrators who wish to assign addresses arbitrarily and maintains compatibility with other address assignment protocols. IEEE Std 802c, clause 8.4.1, does apply in the IEEE P802.11aq case; whereas clause 8.4.5 does not apply. IEEE Std 802c allows for multiple address assignment protocols to exist in a compatible manner on a single LAN. If there is only one address assignment technique opeating on the LAN, as is the case for IEEE 802.11aq, there is no incompatibility with IEEE Std 802c. A CSD was not created for IEEE P802.11aq, as a CSD was not required at the commencement of the IEEE P802.11aq project. However, at the time a 5 criteria (5C) submission was created and can be found within the document https://mentor.ieee.org/802.11/dcn/12/11-12-1137-06-0pad-draft-5c-proposal.doc. The CSD/5C is a document that is used internally by IEEE 802. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9009 | McCann, Stephen | 4000 | 10 | 2 | 15 | 38 | E | No | 15 | 38 | 2 |  | A | Lee Armstrong |  |  | IETF RFC 6763 is no longer referenced in the document. | Remove the cited line | ACCEPTED (EDITOR: 2017-08-16 13:30:08Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9010 | McCann, Stephen | 4000 | 10 | 3.1 | 15 | 50 | T | No | 15 | 50 | 3.1 | [5 empty] | "the service name" is not defined anywhere | Add the following definition within this clause "Service name: A string of characters describing a service" |  | GEN | Unassigned |  | verify with IEEE dictionary to see if there is already a definition there. |  |  |  | 2017-08-11 20:34 | GEN
9011 | McCann, Stephen | 4000 | 10 | 4.5.9.2.1 | 19 | 53 | E | No | 19 | 53 | 4.5.9.2.1 |  | A | Lee Armstrong |  |  | "non-AP non-PCP STA" is not the convention used in the rest of the document | Change to "non-AP and non-PCP STA". | ACCEPTED (EDITOR: 2017-08-16 13:30:37Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9012 | McCann, Stephen | 4000 | 10 | 9.4.2.217 | 38 | 9 | T | No | 38 | 9 | 9.4.2.217 |  | V |  |  |  | Within Table 9-262z, the first column should be a value and not a range | Change the title of the first column of Table 9-262z to "False Positive Probability value" | REVISED (GEN: 2017-08-11 17:47:20Z). Change the title of the first column of Table 9-262z to "Value". | GEN | 2017-08-11-telco | ready for motion | "Value" means the value contained in the cited subfield. |  |  |  | 2017-08-11 18:06 | GEN
9013 | McCann, Stephen | 4000 | 10 | 9.4.2.219 | 40 | 53 | E | No | 40 | 53 | 9.4.2.219 |  | A | Lee Armstrong |  |  | typo, missing "The" at the start of the sentence | Change the start of the cited sentence to "The Group-addressed GAS..." | ACCEPTED (EDITOR: 2017-08-16 13:30:56Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9014 | McCann, Stephen | 4000 | 10 | 9.4.5.27 | 43 | 1 | E | No | 43 | 1 | 9.4.5.27 |  | A | Lee Armstrong |  |  | typo, missing "the" in the sentence | Change the text in the cited sentence from "The Info ID represents info ID...." to "The Info ID represents the info ID...." | ACCEPTED (EDITOR: 2017-08-16 13:31:55Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9015 | McCann, Stephen | 4000 | 10 | 9.4.5.28 | 43 | 15 | T | No | 43 | 15 | 9.4.5.28 |  | A |  |  |  | There can be multiple service hashes within a Service Information Request ANQP-element | Change the end of the cited sentence from "....with the service hash provided" to "....with the service hash(es) provided". | ACCEPTED (GEN: 2017-08-11 17:49:49Z). | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9016 | McCann, Stephen | 4000 | 10 | 9.4.5.28 | 43 | 55 | E | No | 43 | 55 | 9.4.5.28 |  | A | Lee Armstrong |  |  | typo "lenth" | replace "lenth" with "length" | ACCEPTED (EDITOR: 2017-08-16 13:32:13Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9017 | McCann, Stephen | 4000 | 10 | 9.4.5.28 | 43 | 58 | E | No | 43 | 58 | 9.4.5.28 |  | A | Lee Armstrong |  |  | typo, missing "a" in the sentence | Change the text in the cited sentence from "subfield contains service-specific query" to "subfield contains a service-specific query". | ACCEPTED (EDITOR: 2017-08-16 13:32:28Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9018 | McCann, Stephen | 4000 | 10 | 9.6.8.36 | 47 | 32 | E | No | 47 | 32 | 9.6.8.36 |  | A | Lee Armstrong |  |  | Within Table 9-325a, the entries for order 6 and 7 appear to be in a larger font than the rest of the table. | Change the font size of all fields within Figure 9-325a to be the same size per the IEEE 802.11 editing guidelines. | ACCEPTED (EDITOR: 2017-08-16 13:32:52Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9019 | McCann, Stephen | 4000 | 10 | 9.6.8.37 | 48 | 29 | E | No | 48 | 29 | 9.6.8.37 |  | A | Lee Armstrong |  |  | Within Table 9-325b, the entries for order 5 through 8 appear to be in a larger font than the rest of the table. | Change the font size of all fields within Figure 9-325b to be the same size per the IEEE 802.11 editing guidelines. | ACCEPTED (EDITOR: 2017-08-16 13:33:12Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9020 | McCann, Stephen | 4000 | 10 | 9.6.22.2 | 49 | 27 | E | No | 49 | 27 | 9.6.22.2 |  | A | Lee Armstrong |  |  | typo, extra "5" after the end of the sentence in the right hand cell, in Table 9-416 | Delete the "5" from this table cell | ACCEPTED (EDITOR: 2017-08-16 13:33:33Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9021 | McCann, Stephen | 4000 | 10 | 9.6.22.2 | 49 | 14 | E | No | 49 | 14 | 9.6.22.2 |  | A | Lee Armstrong |  |  | The title of this clause appears to be in a smaller font than similar clauses within the document | Change the size of the clause title to be the same size as the rest of the document, per the IEEE 802.11 editing guidelines. | ACCEPTED (EDITOR: 2017-08-16 13:33:54Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9022 | McCann, Stephen | 4000 | 10 | 11.25.3.3.1 | 61 | 26 | E | No | 61 | 26 | 11.25.3.3.1 |  | J | Lee Armstrong |  |  | Missing articles in the "Symbol Key" at the base of Table 11-15. I appreciate that this is baseline text, but it would be nice to correct it. | Add an "a" to the T line to read "transmitted by a MAC Entity" Add an "a" to the R line to read "received by a MAC Entity" Add an "a" to the -- line to read "transmitted nor received by a MAC Entity" | REJECTED (EDITOR: 2017-08-16 13:41:35Z) Such a change may be acceptable (though not really required) but it should be brought to REVmd, not here. | EDITOR | Editorial | ready for motion |  |  |  |  | 2017-08-16 13:53 | EDITOR
9023 | McCann, Stephen | 4000 | 10 | 11.25a.2 | 63 | 18 | E | No | 63 | 18 | 11.25a.2 |  | A | Lee Armstrong |  |  | The words "of the Service Hint Element" appear to be repeated in this sentence. Earlier cut and paste error? | Change "The values of the bit positions of the Bloom Filter Bit Array field of the Service Hint element of the received Service Hint element, as determined in step 2, are all equal to 1." to "The values of the bit positions of the Bloom Filter Bit Array field of the received Service Hint element, as determined in step 2, are all equal to 1." | ACCEPTED (EDITOR: 2017-08-16 13:42:15Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9024 | McCann, Stephen | 4000 | 10 | A | 67 | 4 | E | No | 67 | 4 | A |  | A | Lee Armstrong |  |  | There are three occurances of "(informative)" in this Annex | Two of the three "(informatives)" can be deleted | ACCEPTED (EDITOR: 2017-08-16 13:43:12Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9025 | McCann, Stephen | 4000 | 10 | B.4.20 | 69 | 8 | E | No | 69 | 8 | B.4.20 |  | A | Lee Armstrong |  |  | typo extra "-" in line | remove the "-" from the left hand cell of the table with the text "-IW2.7" in it. | ACCEPTED (EDITOR: 2017-08-16 13:43:29Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9026 | McCann, Stephen | 4000 | 10 | C.3 | 72 | 59 | E | No | 72 | 59 | C.3 |  | A | Lee Armstrong |  |  | typo "dot11S1GOptionImplemented" should not be underlined in this draft | remove the underline from "dot11S1GOptionImplemented" | ACCEPTED (EDITOR: 2017-08-16 13:43:53Z) | EDITOR | Editorial | ready for motion |  |  | Also fixed other issues with respect to base standards. | 10.1 | 2017-08-16 13:53 | EDITOR
9027 | McCann, Stephen | 4000 | 10 | W.1.2 | 77 | 14 | T | No | 77 | 14 | W.1.2 |  | J |  |  |  | It should be mentioned that sometimes the SIR may have internal security/privacy reasons to not match a particular request from a STA. | Add the following sentence to the end of the paragraph "Optionally the SIR may filter matches based on an internal policy, for example for privacy or security reasons." | REJECTED (GEN: 2017-08-11 17:55:27Z). Internal policy can be a part of the service matching, which is out of scope of this standard. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9028 | McCann, Stephen | 4000 | 10 | W.1.1 | 75 | 47 | E | No | 75 | 47 | W.1.1 |  | A | Lee Armstrong |  |  | typo "theSIC" | change "theSIC" to "the SIC" | ACCEPTED (EDITOR: 2017-08-16 13:44:53Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9029 | McCann, Stephen | 4000 | 10 | W.1.1 | 75 | 49 | E | No | 75 | 49 | W.1.1 |  | A | Lee Armstrong |  |  | typo "subfield.This" | change "subfield.This" to "subfield. This" | ACCEPTED (EDITOR: 2017-08-16 13:45:02Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9030 | Kneckt, Jarkko | 4000 | 10 | 9.4.2.219 | 40 | 21 | T | No | 40 | 21 | 9.4.2.219 | [5 empty] | Currently, the requesting STA may specify the maximum time for the responding STA to respond. This scheme adds complexity to the GAS protocol and creates alternative operating logic to the existing GAS protocol: - The GAS protocol allows the responding STA to provide an initial response in a short time to the requesting STA and set a comeback time when the requesting STA should receive the GAS response. o The GAS protocol is already implemented. The Maximum Channel Time is a new operation proposing very similar operation. o During the comeback time the requesting STA may perform other tasks. When maximum Channel Time is used, the requeting STA needs to receive at the channel for the whole maximum channel time durataion. o STA cannot know the time APs need to prepare the response. It is simplier to have a commong during which the responses will be set to transmission queue. | Delete the Maximum Channel Time field. Use a fixed time interval instead to control when the APs shall transmit their GAS responses. Please modify also the clauses 11.23.3.2.1, 11.25.3.2.2 and 11.25.3.2.3. A submission will be provided to make the necessary changes. |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9031 | Hamilton, Mark | 4000 | 10 | 12.2.10 | 65 | 24 | E | No | 65 | 24 | 12.2.10 |  | A | Lee Armstrong |  |  | Inappropriate use of semi-colon. | Change ";" to "," | ACCEPTED (EDITOR: 2017-08-16 13:45:35Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9032 | Yang, Yunsong | 4000 | 10 | 6.3.118.2.4 | 32 | 49 | T | No | 32 | 49 | 6.3.118.2.4 | [5 empty] | The cited sentence is inaccurate for PCP STA. According to P62L53, a PCP transmits a Service Hint element or Service Hash element, or both, in DMG Beacon, Announce, or Probe Response frames. | Change "that the AP or PCP STA transmits" to "that the AP transmits, or DMG Beacon, Announce, and Probe Response frames that the PCP STA transmits" |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9033 | Yang, Yunsong | 4000 | 10 | 9.4.2.177 | 36 | 46 | T | No | 36 | 46 | 9.4.2.177 | [5 empty] | The format of list of CAG Tuples in Figure 9-589c doesn't comply with REVmd style. | In Figure 9-589c, delete all fields after "CAG Tuple #1" field together with their octet numbers, and change "CAG Tuple #1" to "CAG Tuples" with its octet number changed from "2" to "variable". On P37L1, change "One or more 2-octet CAG Tuple fields are used." to "The CAG Tuples field contains one or more 2-octet CAG Tuple fields." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9034 | Yang, Yunsong | 4000 | 10 | 9.4.5.27 | 42 | 52 | T | No | 42 | 52 | 9.4.5.27 | [5 empty] | The format of list of Info IDs in Figure 9-589cm doesn't comply with REVmd style. | In Figure 9-589cm, delete all fields after "Info ID 1" field together with their octet numbers, and change "Info ID 1" to "Info IDs" with its octet number changed from "2" to "variable". On P43L1, change "The Info ID field represents info ID of an ANQP-element Info ID specified in Table 9-271." to "The Info IDs field contains zero or more Info ID fields. The Info ID field is an unsigned integer of length two octets and contains the info ID of an ANQP-element Info ID specified in Table 9-271." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9035 | Yang, Yunsong | 4000 | 10 | 9.6.22.2 | 49 | 27 | E | No | 49 | 27 | 9.6.22.2 |  | A | Lee Armstrong |  |  | There is an extra "5" at the end of the Notes. | Delete "5" at the end of the Notes. | ACCEPTED (EDITOR: 2017-08-16 13:46:04Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9036 | Yang, Yunsong | 4000 | 10 | 11.25.3.2.1 | 51 | 38 | E | No | 51 | 38 | 11.25.3.2.1 |  | A | Lee Armstrong |  |  | "group addressed GAS subfield" should be "Group-addressed GAS subfield" to be consistent with the name of the subfield in Figure 9-589ck (i.e., B0 in the figure). | Change "group addressed GAS subfield" should be "Group-addressed GAS subfield". | ACCEPTED (EDITOR: 2017-08-16 13:46:25Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9037 | Yang, Yunsong | 4000 | 10 | 11.25a.2 | 62 | 60 | E | No | 62 | 60 | 11.25a.2 |  | A | Lee Armstrong |  |  | One of "its" and "of the Service Hint element" is redundant, as both convey the same meaning. | Change "its" to "the". | ACCEPTED (EDITOR: 2017-08-16 13:46:50Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9038 | Yang, Yunsong | 4000 | 10 | 12.2.10 | 65 | 56 | E | No | 65 | 56 | 12.2.10 |  | A | Lee Armstrong |  |  | An extra "shall" in "a STA shall shall set" | Delete the extra "shall" | ACCEPTED (EDITOR: 2017-08-16 13:47:06Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9039 | Yang, Yunsong | 4000 | 10 | C.3 | 72 | 59 | T | No | 72 | 59 | C.3 |  | V |  |  |  | "dot11S1GOptionImplemented" is a part of the baseline (802.11ah-2016) text and shouldn't be underscored. And do we need all these (2 pages of) entries that are from the baseline document, given the instruction says "insert ..."? | Undo the underscore on "dot11S1GOptionImplemented" or remove all entries in Dot11StationConfigEntry that are from the baseline document. | REVISED (GEN: 2017-08-11 17:39:53Z). Remove the underline from "dot11S1GOptionImplemented". | GEN | 2017-08-11-telco | ready for motion | Same resolution as CID 9026. |  |  |  | 2017-08-11 18:06 | GEN
9040 | Yang, Yunsong | 4000 | 10 | 11.25.3.2.4 | 59 | 1 | T | No | 59 | 1 | 11.25.3.2.4 | [5 empty] | It is not clear whether "If the transmitting and requesting STA support" refers to one STA or two (currently the subject is singular but the verb implies plural. The phrase "the transmitting" provides no clue what STA is being referred to, as the following bullets mentioned both the requesting STA and responding STA. From the two new bullets below, it is sufficient if the condition is only for the requesting STA. | Delete "transmitting and" |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9041 | Yang, Yunsong | 4000 | 10 | 11.25.3.2.4 | 59 | 3 | E | No | 59 | 3 | 11.25.3.2.4 |  | A | Lee Armstrong |  |  | typo in "hte" | Change "hte" to "the". | ACCEPTED (EDITOR: 2017-08-16 13:47:28Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9042 | Yong, Su Khiong | 4000 | 10 |  |  |  | G | No | [8 empty] | current draft does not have deterministic behavior for Solicited PAD to work properly and causes unnecessary power consumption to the STA and latency. | contribution will be submitted |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9043 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 22 | T | Yes | 65 | 22 | 12.2.10 |  | J |  |  |  | It is not obvious that 12.2.10 is within the scope of the project and how it helps to support delivery of pre-association service discovery information to IEEE Std 802.11 stations. | The ballot record should articulate the rationale for concluding that 12.2.10 is within the scope of the project. | REJECTED (GEN: 2017-08-04 17:51:05Z) - No proposed change is required. The following is a response to the comment. Randomizing the MAC address, as described in clause 12.2.10, is a perfectly reasonable part of pre-association discovery scope. This avoids revealing privacy compromising information to STAs that are observing the 802.11aq traffic. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9044 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 25 | T | Yes | 65 | 25 | 12.2.10 |  | V |  |  |  | The draft would arguably make the use of randomized MAC addresses mandatory, because it says "a non-AP STA shall set dot11MACPrivacyActivated to true." I don't believe that is the intention, and I don't think it's a good idea. The full sentence is "To enable MAC privacy enhancements during discovery, BSS transition, and membership in a BSS; a non-AP STA shall set dot11MACPrivacyActivated to true." The introductory clause should be rewritten as a conditional, not an informative, clause; otherwise an alternative conditional should be used. | Change to "If non-AP STA sets dot11MACPrivacyActivated to true, then MAC privacy enhancements relevant to discovery, BSS transition, and membership in a BSS shall be enabled." | REVISED (GEN: 2017-08-11 16:59:49Z). Change the cited sentence to read "A non-AP STA shall set dot11MACPrivacyActivated to true to enable MAC privacy enhancements during discovery, BSS transition, and membership in a BSS." | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9045 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 38 | T | Yes | 65 | 38 | 12.2.10 |  | V |  |  |  | The draft would arguably make the use of randomized MAC addresses mandatory, because it says "A STA that discovers a BSS of interest, wishes to establish a connection,and does not have any transactional state bound to a random MAC address, shall change its MAC address to a random value prior to establishing a connection to the BSS." | Change "A STA" to "A STA with dot11MACPrivacyActivated set to true". | REVISED (GEN: 2017-08-11 16:51:14Z). Change "A STA" on L37, L39, L50, and L53 to "The non-AP STA". And change "a STA" on L56 to "the STA". | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9046 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 56 | T | Yes | 65 | 56 | 12.2.10 |  | J |  |  |  | With the substantial and substantive changes made to 12.2.10 in the prior recirculation, that subclause should be reconsidered, taking into account its consistency with IEEE Std 802, which represents the IEEE 802 Overview and Architecture. IEEE 802 was amended on 15 June 2017 by the approval of IEEE Std 802c, and some of the amemdment content is relevant to 12.2.10. In particular, IEEE 802c details the Structured Local Address Plan (SLAP), which specifies use of local MAC address space. Under the SLAP, the use of local address MAC space is specified differently in four quadrants, distinguished by two bits (the third and fourth least signficant ones). Per 802c, "The locally administered bits of local MAC addresses are arbitrarily assignable under the condition that local MAC addresses are unique within a LAN" and "While a local administrator may assign addresses throughout the local range, the optional Structured Local Address Plan (SLAP) specifies different assignment approaches in four specified regions of local MAC address space." So, observing the SLAP is not mandatory on a network administrator. Nevertheless, difficulties in implemtation of the SLAP will arise if IEEE standards specify that compliant devices must violate it. The current draft does include such a specification: "To construct a random MAC address, a STA shall shall set bit 1 of the first octet to 1 (indicating a locally administered MAC address) and bit 0 of the first octet to 0 (indicating unicast) and shall assign random values to the other 46 bits." | Replace "To construct a random MAC address, a STA shall shall set bit 1 of the first octet to 1 (indicating a locally administered MAC address) and bit 0 of the first octet to 0 (indicating unicast) and shall assign random values to the other 46 bits." with "When constructing a random MAC address, a STA shall <del>shall</del> set bit 1 of the first octet to 1 (indicating a locally administered MAC address) and bit 0 of the first octet to 0 (indicating unicast) <ins>, shall set bits 2 and 3 of the first octet to 0 (indicating the address as an Administratively Assigned Identifier under the Structured Local Address Plan of IEEE Std 802),</ins> and shall assign random values to the other <del>46</del><ins>44</ins> bits. Alternatively, provide another solution to the problem. | REJECTED (GEN: 2017-08-11 17:18:12Z). 802.11aq does not specify a violation of the SLAP. dot11MACPrivacyActivated and 802c are mutually exclusive. If dot11MACPrivacyActivated is set to 1, then 46 bits are randomized. To use the SLAP requires fixing 2 bits following the SLAP rules. To use the SLAP, dot11MACPrivacyActivated shall set to 0. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9047 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 59 | T | Yes | 65 | 59 | 12.2.10 |  | V |  |  |  | The sentence "Using 46 bits of randomness ensures that the probability of random MAC address collision on even the largest networks remains acceptably small." should be deleted because it characteritizes a risk as "acceptably small" even though the actual risks and consequences of failure are determined by deployment scenarios that are outside the scope of the standard. In some cases, fewer bits may suffice. If the consequences are significant enough, then procedures to project againt collision may be warranted. | Delete "Using 46 bits of randomness ensures that the probability of random MAC address collision on even the largest networks remains acceptably small." | REVISED (GEN: 2017-08-11 16:40:47Z). Delete the word "acceptably" from the cited sentence. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN

## 2017-08-11-telco
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
9043 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 22 | T | Yes | 65 | 22 | 12.2.10 |  | J |  |  |  | It is not obvious that 12.2.10 is within the scope of the project and how it helps to support delivery of pre-association service discovery information to IEEE Std 802.11 stations. | The ballot record should articulate the rationale for concluding that 12.2.10 is within the scope of the project. | REJECTED (GEN: 2017-08-04 17:51:05Z) - No proposed change is required. The following is a response to the comment. Randomizing the MAC address, as described in clause 12.2.10, is a perfectly reasonable part of pre-association discovery scope. This avoids revealing privacy compromising information to STAs that are observing the 802.11aq traffic. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9044 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 25 | T | Yes | 65 | 25 | 12.2.10 |  | V |  |  |  | The draft would arguably make the use of randomized MAC addresses mandatory, because it says "a non-AP STA shall set dot11MACPrivacyActivated to true." I don't believe that is the intention, and I don't think it's a good idea. The full sentence is "To enable MAC privacy enhancements during discovery, BSS transition, and membership in a BSS; a non-AP STA shall set dot11MACPrivacyActivated to true." The introductory clause should be rewritten as a conditional, not an informative, clause; otherwise an alternative conditional should be used. | Change to "If non-AP STA sets dot11MACPrivacyActivated to true, then MAC privacy enhancements relevant to discovery, BSS transition, and membership in a BSS shall be enabled." | REVISED (GEN: 2017-08-11 16:59:49Z). Change the cited sentence to read "A non-AP STA shall set dot11MACPrivacyActivated to true to enable MAC privacy enhancements during discovery, BSS transition, and membership in a BSS." | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9045 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 38 | T | Yes | 65 | 38 | 12.2.10 |  | V |  |  |  | The draft would arguably make the use of randomized MAC addresses mandatory, because it says "A STA that discovers a BSS of interest, wishes to establish a connection,and does not have any transactional state bound to a random MAC address, shall change its MAC address to a random value prior to establishing a connection to the BSS." | Change "A STA" to "A STA with dot11MACPrivacyActivated set to true". | REVISED (GEN: 2017-08-11 16:51:14Z). Change "A STA" on L37, L39, L50, and L53 to "The non-AP STA". And change "a STA" on L56 to "the STA". | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9046 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 56 | T | Yes | 65 | 56 | 12.2.10 |  | J |  |  |  | With the substantial and substantive changes made to 12.2.10 in the prior recirculation, that subclause should be reconsidered, taking into account its consistency with IEEE Std 802, which represents the IEEE 802 Overview and Architecture. IEEE 802 was amended on 15 June 2017 by the approval of IEEE Std 802c, and some of the amemdment content is relevant to 12.2.10. In particular, IEEE 802c details the Structured Local Address Plan (SLAP), which specifies use of local MAC address space. Under the SLAP, the use of local address MAC space is specified differently in four quadrants, distinguished by two bits (the third and fourth least signficant ones). Per 802c, "The locally administered bits of local MAC addresses are arbitrarily assignable under the condition that local MAC addresses are unique within a LAN" and "While a local administrator may assign addresses throughout the local range, the optional Structured Local Address Plan (SLAP) specifies different assignment approaches in four specified regions of local MAC address space." So, observing the SLAP is not mandatory on a network administrator. Nevertheless, difficulties in implemtation of the SLAP will arise if IEEE standards specify that compliant devices must violate it. The current draft does include such a specification: "To construct a random MAC address, a STA shall shall set bit 1 of the first octet to 1 (indicating a locally administered MAC address) and bit 0 of the first octet to 0 (indicating unicast) and shall assign random values to the other 46 bits." | Replace "To construct a random MAC address, a STA shall shall set bit 1 of the first octet to 1 (indicating a locally administered MAC address) and bit 0 of the first octet to 0 (indicating unicast) and shall assign random values to the other 46 bits." with "When constructing a random MAC address, a STA shall <del>shall</del> set bit 1 of the first octet to 1 (indicating a locally administered MAC address) and bit 0 of the first octet to 0 (indicating unicast) <ins>, shall set bits 2 and 3 of the first octet to 0 (indicating the address as an Administratively Assigned Identifier under the Structured Local Address Plan of IEEE Std 802),</ins> and shall assign random values to the other <del>46</del><ins>44</ins> bits. Alternatively, provide another solution to the problem. | REJECTED (GEN: 2017-08-11 17:18:12Z). 802.11aq does not specify a violation of the SLAP. dot11MACPrivacyActivated and 802c are mutually exclusive. If dot11MACPrivacyActivated is set to 1, then 46 bits are randomized. To use the SLAP requires fixing 2 bits following the SLAP rules. To use the SLAP, dot11MACPrivacyActivated shall set to 0. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9047 | Marks, Roger | 4000 | 10 | 12.2.10 | 65 | 59 | T | Yes | 65 | 59 | 12.2.10 |  | V |  |  |  | The sentence "Using 46 bits of randomness ensures that the probability of random MAC address collision on even the largest networks remains acceptably small." should be deleted because it characteritizes a risk as "acceptably small" even though the actual risks and consequences of failure are determined by deployment scenarios that are outside the scope of the standard. In some cases, fewer bits may suffice. If the consequences are significant enough, then procedures to project againt collision may be warranted. | Delete "Using 46 bits of randomness ensures that the probability of random MAC address collision on even the largest networks remains acceptably small." | REVISED (GEN: 2017-08-11 16:40:47Z). Delete the word "acceptably" from the cited sentence. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9008 | Thomas, Angela | 4000 | 10 | 12.2.10 |  |  | G | No |  |  | 12.2.10 |  | J |  |  |  | (Comment received from the IEEE-SA RAC) 12.2.10 Requirements for support of MAC privacy enhancements To set a random MAC address, a STA shall assign a random 48-bit value and then shall set the sixth bit of the first octet to one (indicating a locally administered MAC address) and the seventh bit of the first octet to zero (indicating unicast). Using 46 bits of randomness ensures that the probability of random MAC address collision on even the largest networks remains acceptably small. As an aside, this is a different than the 44 bits implicitly allowed to be randomized in P802c. 1. Random MAC address assignment would seem to be out-of-scope for the PAR. The Project Scope reads: "This amendment defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to enable delivery of pre-association Service Discovery information discovery by IEEE 802.11 stations (STAs)." By extension, the ballot group therefore would not include all interested parties -- typically a concern for RevCom. 2. The CSD are not linked on the 802.11 PAR page, and I didn't do a search of mentor for the CSD, but I expect the answer on compatibility with Std 802 was probably generic, and the random assignment quoted above certainly is not compatible with the optional capabilities of Std 802c. |  | REJECTED (GEN: 2017-08-04 17:49:17Z) - No proposed change is required. The following is a response to the comment: The group considers that randomizing the MAC address, as described in clause 12.2.10, is a perfectly reasonable part of the pre-association discovery scope. This avoids revealing privacy compromising information to STAs that are observing the 802.11aq traffic. This is inline with IEEE Std 802c, clause 8.4.1 that states "The locally administered bits of local MAC addresses are arbitrarily assignable under the condition that local MAC addresses are unique within a LAN (which may be a bridged LAN or virtual bridged LAN) unless they are assigned to distinct VLANs in which bridges support Independent VLAN Learning, per Annex F.1.2 ("Duplicate MAC Addresses") of IEEE Std 802.1Q. Any failure of such uniqueness invalidates the fundamental premises of IEEE 802 network operation and may lead to disruption." Furthermore, IEEE Std 802c, clause 8.4.5 also states "In some cases, administrators may wish to assign local MAC addresses in an arbitrary fashion (for example, randomly) and yet maintain compatibility with other assignment protocols operating on the same LAN. For such purposes, a local MAC address may be assigned as an Administratively Assigned Identifier (AAI)." IEEE Std 802c provides compatibility for users of the local address spaces and it enables local administrators who wish to assign addresses arbitrarily and maintains compatibility with other address assignment protocols. IEEE Std 802c, clause 8.4.1, does apply in the IEEE P802.11aq case; whereas clause 8.4.5 does not apply. IEEE Std 802c allows for multiple address assignment protocols to exist in a compatible manner on a single LAN. If there is only one address assignment technique opeating on the LAN, as is the case for IEEE 802.11aq, there is no incompatibility with IEEE Std 802c. A CSD was not created for IEEE P802.11aq, as a CSD was not required at the commencement of the IEEE P802.11aq project. However, at the time a 5 criteria (5C) submission was created and can be found within the document https://mentor.ieee.org/802.11/dcn/12/11-12-1137-06-0pad-draft-5c-proposal.doc. The CSD/5C is a document that is used internally by IEEE 802. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9012 | McCann, Stephen | 4000 | 10 | 9.4.2.217 | 38 | 9 | T | No | 38 | 9 | 9.4.2.217 |  | V |  |  |  | Within Table 9-262z, the first column should be a value and not a range | Change the title of the first column of Table 9-262z to "False Positive Probability value" | REVISED (GEN: 2017-08-11 17:47:20Z). Change the title of the first column of Table 9-262z to "Value". | GEN | 2017-08-11-telco | ready for motion | "Value" means the value contained in the cited subfield. |  |  |  | 2017-08-11 18:06 | GEN
9015 | McCann, Stephen | 4000 | 10 | 9.4.5.28 | 43 | 15 | T | No | 43 | 15 | 9.4.5.28 |  | A |  |  |  | There can be multiple service hashes within a Service Information Request ANQP-element | Change the end of the cited sentence from "....with the service hash provided" to "....with the service hash(es) provided". | ACCEPTED (GEN: 2017-08-11 17:49:49Z). | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9027 | McCann, Stephen | 4000 | 10 | W.1.2 | 77 | 14 | T | No | 77 | 14 | W.1.2 |  | J |  |  |  | It should be mentioned that sometimes the SIR may have internal security/privacy reasons to not match a particular request from a STA. | Add the following sentence to the end of the paragraph "Optionally the SIR may filter matches based on an internal policy, for example for privacy or security reasons." | REJECTED (GEN: 2017-08-11 17:55:27Z). Internal policy can be a part of the service matching, which is out of scope of this standard. | GEN | 2017-08-11-telco | ready for motion |  |  |  |  | 2017-08-11 18:06 | GEN
9039 | Yang, Yunsong | 4000 | 10 | C.3 | 72 | 59 | T | No | 72 | 59 | C.3 |  | V |  |  |  | "dot11S1GOptionImplemented" is a part of the baseline (802.11ah-2016) text and shouldn't be underscored. And do we need all these (2 pages of) entries that are from the baseline document, given the instruction says "insert ..."? | Undo the underscore on "dot11S1GOptionImplemented" or remove all entries in Dot11StationConfigEntry that are from the baseline document. | REVISED (GEN: 2017-08-11 17:39:53Z). Remove the underline from "dot11S1GOptionImplemented". | GEN | 2017-08-11-telco | ready for motion | Same resolution as CID 9026. |  |  |  | 2017-08-11 18:06 | GEN

## Editorial
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
9021 | McCann, Stephen | 4000 | 10 | 9.6.22.2 | 49 | 14 | E | No | 49 | 14 | 9.6.22.2 |  | A | Lee Armstrong |  |  | The title of this clause appears to be in a smaller font than similar clauses within the document | Change the size of the clause title to be the same size as the rest of the document, per the IEEE 802.11 editing guidelines. | ACCEPTED (EDITOR: 2017-08-16 13:33:54Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9038 | Yang, Yunsong | 4000 | 10 | 12.2.10 | 65 | 56 | E | No | 65 | 56 | 12.2.10 |  | A | Lee Armstrong |  |  | An extra "shall" in "a STA shall shall set" | Delete the extra "shall" | ACCEPTED (EDITOR: 2017-08-16 13:47:06Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9037 | Yang, Yunsong | 4000 | 10 | 11.25a.2 | 62 | 60 | E | No | 62 | 60 | 11.25a.2 |  | A | Lee Armstrong |  |  | One of "its" and "of the Service Hint element" is redundant, as both convey the same meaning. | Change "its" to "the". | ACCEPTED (EDITOR: 2017-08-16 13:46:50Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9036 | Yang, Yunsong | 4000 | 10 | 11.25.3.2.1 | 51 | 38 | E | No | 51 | 38 | 11.25.3.2.1 |  | A | Lee Armstrong |  |  | "group addressed GAS subfield" should be "Group-addressed GAS subfield" to be consistent with the name of the subfield in Figure 9-589ck (i.e., B0 in the figure). | Change "group addressed GAS subfield" should be "Group-addressed GAS subfield". | ACCEPTED (EDITOR: 2017-08-16 13:46:25Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9035 | Yang, Yunsong | 4000 | 10 | 9.6.22.2 | 49 | 27 | E | No | 49 | 27 | 9.6.22.2 |  | A | Lee Armstrong |  |  | There is an extra "5" at the end of the Notes. | Delete "5" at the end of the Notes. | ACCEPTED (EDITOR: 2017-08-16 13:46:04Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9031 | Hamilton, Mark | 4000 | 10 | 12.2.10 | 65 | 24 | E | No | 65 | 24 | 12.2.10 |  | A | Lee Armstrong |  |  | Inappropriate use of semi-colon. | Change ";" to "," | ACCEPTED (EDITOR: 2017-08-16 13:45:35Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9029 | McCann, Stephen | 4000 | 10 | W.1.1 | 75 | 49 | E | No | 75 | 49 | W.1.1 |  | A | Lee Armstrong |  |  | typo "subfield.This" | change "subfield.This" to "subfield. This" | ACCEPTED (EDITOR: 2017-08-16 13:45:02Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9028 | McCann, Stephen | 4000 | 10 | W.1.1 | 75 | 47 | E | No | 75 | 47 | W.1.1 |  | A | Lee Armstrong |  |  | typo "theSIC" | change "theSIC" to "the SIC" | ACCEPTED (EDITOR: 2017-08-16 13:44:53Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9026 | McCann, Stephen | 4000 | 10 | C.3 | 72 | 59 | E | No | 72 | 59 | C.3 |  | A | Lee Armstrong |  |  | typo "dot11S1GOptionImplemented" should not be underlined in this draft | remove the underline from "dot11S1GOptionImplemented" | ACCEPTED (EDITOR: 2017-08-16 13:43:53Z) | EDITOR | Editorial | ready for motion |  |  | Also fixed other issues with respect to base standards. | 10.1 | 2017-08-16 13:53 | EDITOR
9025 | McCann, Stephen | 4000 | 10 | B.4.20 | 69 | 8 | E | No | 69 | 8 | B.4.20 |  | A | Lee Armstrong |  |  | typo extra "-" in line | remove the "-" from the left hand cell of the table with the text "-IW2.7" in it. | ACCEPTED (EDITOR: 2017-08-16 13:43:29Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9024 | McCann, Stephen | 4000 | 10 | A | 67 | 4 | E | No | 67 | 4 | A |  | A | Lee Armstrong |  |  | There are three occurances of "(informative)" in this Annex | Two of the three "(informatives)" can be deleted | ACCEPTED (EDITOR: 2017-08-16 13:43:12Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9041 | Yang, Yunsong | 4000 | 10 | 11.25.3.2.4 | 59 | 3 | E | No | 59 | 3 | 11.25.3.2.4 |  | A | Lee Armstrong |  |  | typo in "hte" | Change "hte" to "the". | ACCEPTED (EDITOR: 2017-08-16 13:47:28Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9022 | McCann, Stephen | 4000 | 10 | 11.25.3.3.1 | 61 | 26 | E | No | 61 | 26 | 11.25.3.3.1 |  | J | Lee Armstrong |  |  | Missing articles in the "Symbol Key" at the base of Table 11-15. I appreciate that this is baseline text, but it would be nice to correct it. | Add an "a" to the T line to read "transmitted by a MAC Entity" Add an "a" to the R line to read "received by a MAC Entity" Add an "a" to the -- line to read "transmitted nor received by a MAC Entity" | REJECTED (EDITOR: 2017-08-16 13:41:35Z) Such a change may be acceptable (though not really required) but it should be brought to REVmd, not here. | EDITOR | Editorial | ready for motion |  |  |  |  | 2017-08-16 13:53 | EDITOR
9006 | Lepp, James | 4000 | 10 | 11.25a.4 | 64 | 31 | E | No | 64 | 31 | 11.25a.4 |  | A | Lee Armstrong |  |  | The final sentance in 11.25a.4 ends in a semicolon. | Change semicolon to a period to end the sentance. | ACCEPTED (EDITOR: 2017-08-16 13:28:10Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9020 | McCann, Stephen | 4000 | 10 | 9.6.22.2 | 49 | 27 | E | No | 49 | 27 | 9.6.22.2 |  | A | Lee Armstrong |  |  | typo, extra "5" after the end of the sentence in the right hand cell, in Table 9-416 | Delete the "5" from this table cell | ACCEPTED (EDITOR: 2017-08-16 13:33:33Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9019 | McCann, Stephen | 4000 | 10 | 9.6.8.37 | 48 | 29 | E | No | 48 | 29 | 9.6.8.37 |  | A | Lee Armstrong |  |  | Within Table 9-325b, the entries for order 5 through 8 appear to be in a larger font than the rest of the table. | Change the font size of all fields within Figure 9-325b to be the same size per the IEEE 802.11 editing guidelines. | ACCEPTED (EDITOR: 2017-08-16 13:33:12Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9018 | McCann, Stephen | 4000 | 10 | 9.6.8.36 | 47 | 32 | E | No | 47 | 32 | 9.6.8.36 |  | A | Lee Armstrong |  |  | Within Table 9-325a, the entries for order 6 and 7 appear to be in a larger font than the rest of the table. | Change the font size of all fields within Figure 9-325a to be the same size per the IEEE 802.11 editing guidelines. | ACCEPTED (EDITOR: 2017-08-16 13:32:52Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9017 | McCann, Stephen | 4000 | 10 | 9.4.5.28 | 43 | 58 | E | No | 43 | 58 | 9.4.5.28 |  | A | Lee Armstrong |  |  | typo, missing "a" in the sentence | Change the text in the cited sentence from "subfield contains service-specific query" to "subfield contains a service-specific query". | ACCEPTED (EDITOR: 2017-08-16 13:32:28Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9016 | McCann, Stephen | 4000 | 10 | 9.4.5.28 | 43 | 55 | E | No | 43 | 55 | 9.4.5.28 |  | A | Lee Armstrong |  |  | typo "lenth" | replace "lenth" with "length" | ACCEPTED (EDITOR: 2017-08-16 13:32:13Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9014 | McCann, Stephen | 4000 | 10 | 9.4.5.27 | 43 | 1 | E | No | 43 | 1 | 9.4.5.27 |  | A | Lee Armstrong |  |  | typo, missing "the" in the sentence | Change the text in the cited sentence from "The Info ID represents info ID...." to "The Info ID represents the info ID...." | ACCEPTED (EDITOR: 2017-08-16 13:31:55Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9013 | McCann, Stephen | 4000 | 10 | 9.4.2.219 | 40 | 53 | E | No | 40 | 53 | 9.4.2.219 |  | A | Lee Armstrong |  |  | typo, missing "The" at the start of the sentence | Change the start of the cited sentence to "The Group-addressed GAS..." | ACCEPTED (EDITOR: 2017-08-16 13:30:56Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9011 | McCann, Stephen | 4000 | 10 | 4.5.9.2.1 | 19 | 53 | E | No | 19 | 53 | 4.5.9.2.1 |  | A | Lee Armstrong |  |  | "non-AP non-PCP STA" is not the convention used in the rest of the document | Change to "non-AP and non-PCP STA". | ACCEPTED (EDITOR: 2017-08-16 13:30:37Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9009 | McCann, Stephen | 4000 | 10 | 2 | 15 | 38 | E | No | 15 | 38 | 2 |  | A | Lee Armstrong |  |  | IETF RFC 6763 is no longer referenced in the document. | Remove the cited line | ACCEPTED (EDITOR: 2017-08-16 13:30:08Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9007 | Lepp, James | 4000 | 10 | 10.25a.4 | 69 | 31 | E | No | 69 | 31 | 10.25a.4 |  | A | Lee Armstrong |  |  | Final sentence of 10.25a.4 the term "map into" doesn't seem right. | Change to: and the service hash used as input to compute the Bloom Filter Bit Array field is "0xbfd39037d25c" | ACCEPTED (EDITOR: 2017-08-16 13:29:49Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR
9023 | McCann, Stephen | 4000 | 10 | 11.25a.2 | 63 | 18 | E | No | 63 | 18 | 11.25a.2 |  | A | Lee Armstrong |  |  | The words "of the Service Hint Element" appear to be repeated in this sentence. Earlier cut and paste error? | Change "The values of the bit positions of the Bloom Filter Bit Array field of the Service Hint element of the received Service Hint element, as determined in step 2, are all equal to 1." to "The values of the bit positions of the Bloom Filter Bit Array field of the received Service Hint element, as determined in step 2, are all equal to 1." | ACCEPTED (EDITOR: 2017-08-16 13:42:15Z) | EDITOR | Editorial | ready for motion |  |  |  | 10.1 | 2017-08-16 13:53 | EDITOR

## Unassigned
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
9042 | Yong, Su Khiong | 4000 | 10 |  |  |  | G | No | [8 empty] | current draft does not have deterministic behavior for Solicited PAD to work properly and causes unnecessary power consumption to the STA and latency. | contribution will be submitted |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9001 | Montemurro, Michael | 4000 | 10 | 4.5.9.2.5 | 21 | 12 | T | No | 21 | 12 | 4.5.9.2.5 | [5 empty] | The subclause does not really describe what the SIC is The SIC allows applications to exchange pre-association service discovery requests and responses | Replace "The SIC initiates service discovery. Within a STA this exchange includes supporting service discovery requests and responses to and from applications. The SME determines whether to use unsolicited PAD or solicited PAD procedures. The SME also creates the contents of the ANQP requests." with "The SIC initiates service discovery. The SIC exchanges service discovery requests and responses between the SME and applications. The SME determines whether to use unsolicited PAD or solicited PAD procedures. The SME also composes ANQP requests for solicited PAD procedures." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9002 | Montemurro, Michael | 4000 | 10 | 6.3.73.3 | 26 | 15 | T | No | 26 | 15 | 6.3.73.3 | [5 empty] | The confirm needs a GAS Extensions (but not GA Mode) | Add the GAS Extensions parameter to MLME-GAS.confirm. |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9003 | Montemurro, Michael | 4000 | 10 | 6.3.73.2.2 | 25 | 2 | T | No | 25 | 2 | 6.3.73.2.2 | [5 empty] | The description for GAS Extensions is not correct. | At 25.43 and 28.62 change "Specifies the GAS extension for a transmitting STA that supports group address GAS frames." to "Specifies GAS extensions information for GAS frames." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9004 | Montemurro, Michael | 4000 | 10 | 9.4.2.219 | 40 | 12 | T | No | 40 | 12 | 9.4.2.219 | [5 empty] | The field order and naming for the sub-fields do not really make sense. The Group-addressed GAS and Fragment Transmission Flag fields indicate enabled features, while the remainder of the sub-fields indicate the presents of other subfields. | Change "Fragment Retransmission Flag" to "Fragment Retransmission" at 41.1, 58.8, 59.4, and 59.18. Move the "Fragment Retransmission" sub-field from B4 to B1, and shift all other fields to the right 1 bit in Figure 9-589cj. Move the last paragraph on p40 before the paragraph "The Maximum Channel Time ...." on the same page. |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9005 | Montemurro, Michael | 4000 | 10 | 11.25.3.2.4 | 59 | 17 | T | No | 59 | 17 | 11.25.3.2.4 | [5 empty] | The wording of this paragraph could be improved. | Change "If the corresponding GAS Initial Response frame doesn't contain a GAS Extension element or the Fragment Retransmission Flag subfield in the GAS Extension element in the corresponding GAS Initial Response frame is equal to 0, the requesting STA shall not use a GAS Comeback Request frame to request the retransmission of the GAS Query Response fragment." to "If the corresponding GAS Initial Response frame does not contain a GAS Extension element or the value of the Fragment Retransmission Flag subfield in the GAS Extension element is equal to 0, the requesting STA shall not request the retransmission of a GAS Query Response fragment using a GAS Comeback Request frame." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9010 | McCann, Stephen | 4000 | 10 | 3.1 | 15 | 50 | T | No | 15 | 50 | 3.1 | [5 empty] | "the service name" is not defined anywhere | Add the following definition within this clause "Service name: A string of characters describing a service" |  | GEN | Unassigned |  | verify with IEEE dictionary to see if there is already a definition there. |  |  |  | 2017-08-11 20:34 | GEN
9030 | Kneckt, Jarkko | 4000 | 10 | 9.4.2.219 | 40 | 21 | T | No | 40 | 21 | 9.4.2.219 | [5 empty] | Currently, the requesting STA may specify the maximum time for the responding STA to respond. This scheme adds complexity to the GAS protocol and creates alternative operating logic to the existing GAS protocol: - The GAS protocol allows the responding STA to provide an initial response in a short time to the requesting STA and set a comeback time when the requesting STA should receive the GAS response. o The GAS protocol is already implemented. The Maximum Channel Time is a new operation proposing very similar operation. o During the comeback time the requesting STA may perform other tasks. When maximum Channel Time is used, the requeting STA needs to receive at the channel for the whole maximum channel time durataion. o STA cannot know the time APs need to prepare the response. It is simplier to have a commong during which the responses will be set to transmission queue. | Delete the Maximum Channel Time field. Use a fixed time interval instead to control when the APs shall transmit their GAS responses. Please modify also the clauses 11.23.3.2.1, 11.25.3.2.2 and 11.25.3.2.3. A submission will be provided to make the necessary changes. |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9032 | Yang, Yunsong | 4000 | 10 | 6.3.118.2.4 | 32 | 49 | T | No | 32 | 49 | 6.3.118.2.4 | [5 empty] | The cited sentence is inaccurate for PCP STA. According to P62L53, a PCP transmits a Service Hint element or Service Hash element, or both, in DMG Beacon, Announce, or Probe Response frames. | Change "that the AP or PCP STA transmits" to "that the AP transmits, or DMG Beacon, Announce, and Probe Response frames that the PCP STA transmits" |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9033 | Yang, Yunsong | 4000 | 10 | 9.4.2.177 | 36 | 46 | T | No | 36 | 46 | 9.4.2.177 | [5 empty] | The format of list of CAG Tuples in Figure 9-589c doesn't comply with REVmd style. | In Figure 9-589c, delete all fields after "CAG Tuple #1" field together with their octet numbers, and change "CAG Tuple #1" to "CAG Tuples" with its octet number changed from "2" to "variable". On P37L1, change "One or more 2-octet CAG Tuple fields are used." to "The CAG Tuples field contains one or more 2-octet CAG Tuple fields." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9034 | Yang, Yunsong | 4000 | 10 | 9.4.5.27 | 42 | 52 | T | No | 42 | 52 | 9.4.5.27 | [5 empty] | The format of list of Info IDs in Figure 9-589cm doesn't comply with REVmd style. | In Figure 9-589cm, delete all fields after "Info ID 1" field together with their octet numbers, and change "Info ID 1" to "Info IDs" with its octet number changed from "2" to "variable". On P43L1, change "The Info ID field represents info ID of an ANQP-element Info ID specified in Table 9-271." to "The Info IDs field contains zero or more Info ID fields. The Info ID field is an unsigned integer of length two octets and contains the info ID of an ANQP-element Info ID specified in Table 9-271." |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN
9040 | Yang, Yunsong | 4000 | 10 | 11.25.3.2.4 | 59 | 1 | T | No | 59 | 1 | 11.25.3.2.4 | [5 empty] | It is not clear whether "If the transmitting and requesting STA support" refers to one STA or two (currently the subject is singular but the verb implies plural. The phrase "the transmitting" provides no clue what STA is being referred to, as the following bullets mentioned both the requesting STA and responding STA. From the two new bullets below, it is sufficient if the condition is only for the requesting STA. | Delete "transmitting and" |  | GEN | Unassigned | [5 empty] | 2017-08-11 20:34 | GEN