## Slide 1: TGba Initial Draft (D0.1) Development Process
Date: 2017-10-20
Authors:

## Slide 2: TGba Initial Draft D0.1 Development Process
Review TGba D0.0 (11-17/1585r0))  today
Identify subclauses that have enough details to start writing draft text based on TGba SFD (11-17/575r5) by end of Nov. F2F meeting
Call for volunteers to write draft text for the identified subclauses by end of Nov. F2F meeting
  One primary author working with secondary authors (if there are more than one volunteer)
Upload the prepared draft text to the mentor server for the group to review and make comments before Jan. 2018 F2F meeting
  Commenting through TGba reflector: 7 days review period
Resolve comments on the prepared draft texts before Jan. 2018 F2F meeting
Approve prepared draft texts in Jan. 2018 F2F meeting
TGba editor to implement the draft texts in D0.0 that have been approved by the group and create D0.1
The subclauses that do not have enough details will be added to the next revisions (i.e. D0.2, D0.3, …)