## Slide 1: 802.11 WG Editor’s Meeting (November 2018)
Date: 2018-11-06
Authors:

## Slide 2: Abstract
This document contains agenda/minutes/actions/status as prepared/recorded at the IEEE 802.11 Editors’ Meeting

## Slide 3: Agenda for 2018-11-13 meeting
Roll Call / Contacts / Reflector
Go round table and get brief status report
Draft Numbering
11ax Baseline of REVmd
802.11 Mandatory Draft Review before SB
WG Style Guide for 802.11 09/1034r12
Review WG Style Guide

## Slide 4: Roll Call – 2018-11-13
802.11 Editor’s Present
  P802.11ax Amendment (HEW) – Robert Stacey
  P802.11az Amendment (NGP) – Chao-Chun Wang
  P802.11ba Amendment (WUR) – Po-kai Huang
  P802.11bb Amendment (LC) – Volker Jungnickel
  REVmd – Emily Qi
802.11 Editor’s Not Present
  P802.11ay Amendment (NG60) – Carlos Cordeiro
  P802.11bb Amendment (LC) – Gaurav Patwardhan
  REVmd – Edward Au
Also present:
  Al Petrick Amelia Andersdotter Joseph Levy Mark Hamilton Stephen Palm Yasuhiko Inoue
IEEE Staff present and always welcome!
Note: editors request that an IEEE staff member should be present at least during Plenary meetings

## Slide 5: Volunteer Editor Contacts
  TGax – Robert Stacey – robert.stacey@intel.com
  TGay – Carlos Cordeiro – carlos.cordeiro@intel.com
  TGaz – Chao Chun Wang – chaochun.wang@mediatek.com
  TGba – Po-kai Huang – po-kai.huang@intel.com
  TGbb - Gaurav Patwardhan Gaurav.Patwardhan@hpe.com , Volker Jungnickel volker.jungnickel@hhi.fraunhofer.de
  REVmd – Emily Qi – emily.h.qi@intel.com, Edward Au – edward.ks.au@huawei.com,
  Editors Emeritus:
  TGaa – Alex Ashley – alex.ashley@hotmail.co.uk
  TGac – Robert Stacey – robert.stacey@intel.com
  TGad – Carlos Cordeiro – carlos.cordeiro@intel.com
  TGae – Henry Ptasinski – henry@LOGOUT.COM
  TGaf – Peter Ecclesine – petere@ieee.org
  REVmc – Adrian Stephens – adrian.p.stephens@ieee.org , Edward Au – edward.ks.au@huawei.com, Emily Qi – emily.h.qi@intel.com
  TGah – Yongho Seok yongho.seok@gmail.com, Alfred Asterjadhi – aasterja@qti.qualcomm.com
  TGai - LRA@tiac.net, Ping FANG Ping.FANG@huawei.com
  TGaj – Jiamin CHEN – jiamin.chen@mail01.huawei.com , Shiwen He – shiwenhe@seu.edu.cn
  TGak – Donald Eastlake – d3e3e3@gmail.com
  TGaq – Dan Gal – ddrgal@gmail.com , Lee Armstrong – LRA@tiac.net

## Slide 6: November 13th roundtable status report
11ax – Processing ~500 comments, hope to recirc D4.0 out of Nov meeting and start MDR
11ay – doing comment resolution, plan to recirc D3.0 out of January, then start MDR after comments are received
11az – Published D0.5, in CC, plan to release D0.5.1 after Nov meeting
11ba – D1.0 was in WGLB, doing comment resolution on ~1283 comments, expect to release D1.1 after Nov meeting
11bb – working on SFD (PHY and MAC simulation framework) with a CC of ~100 comments, hope to issue call for proposals out of Nov meeting
REVmd – Processing ~80 comments, plan to recirc D2.0 out of Nov meeting (30 days starting early December)

## Slide 7: Reflector Updates
Each editor is expected to be on the reflector and current.
If you didn’t receive the meeting notice from the reflector, please send email to Robert.Stacey@intel.com
To be updated:

## Slide 8: IEEE Publication Status
Publication of 802.11-2016 December 14, 2016
Publication of 11ai announced December 30, 2016
Second printing of 11ai in April 2017
Publication of 11ah announced May 9, 2017
Publication of 11aj announced April 30, 2018
Publication of 11ak announced June 8, 2018
Publication of 11aq was August 31, 2018

## Slide 9: Update on numbering process
Refer to
https://mentor.ieee.org/802.11/dcn/11/11-11-1149-52-0000-draft-number-alignment-tool.xlsx Dec 2017 was last update
We lost IEEE Diane Lacey’s services, and have to pick up the task.
Updated numbering after 11ax shifted to REVmd baseline, will not update 1149, RIP.

## Slide 10: MDR Status
802.11 Working Group Mandatory Draft Review
  802.11-11/615r6 documents the process. MDR now in the 802.11 Operating Manual 802.11-14/0629r8. The process needs some change so the report is done after the editing is done.
REVmc D3.0 went through MDR process – 802.11-14/781r11 dated Sept 19, 2014
P802.11ah D4.0 went through MDR process – 802.11-15/247r3 dated Mar 12, 2015
P802.11ai D4.0 went through MDR process – 802.11-15/248r4 dated May 14, 2015
P802.11aq D4.0 went through MDR process – 802.11-16/801r0 dated June 22, 2016
P802.11aj D3.0 went through MDR process – 802.11-16/1333r5 dated Dec 9, 2016
  Final changes in D5.0 Feb 17, 2017.
P802.11ak D3.0 went through MDR process – 802.11-17/143r3 dated March 2, 2017
P802.11ax will be started on D4.0 out of November meeting

## Slide 11: 11ax next steps (continued)
MDR review of D4.0 request for several volunteers (two for the style guide, one for MIB following new MIB guidelines), all candidates identified
Changed the 11ax baseline to REVmd
REVmd SB April 2019, probably will have a shorter SB recycle than REVmc did without rolling in any amendments. We expect all to switch baseline to REVmd.

## Slide 12: 802.11 Style Guide
See https://mentor.ieee.org/802.11/dcn/09/11-09-1034-12-0000-802-11-editorial-style-guide.docx
We updated 802.11 WG Style Guide based on 2012 IEEE Standards Style Manual and consistency changes in final publication of the 802.11 standard
Editor’s responsibility includes checking the 2014 IEEE Standards Style Manual when creating or updating drafts. https://development.standards.ieee.org/myproject/Public/mytools/draft/styleman.pdf
Submissions with draft text should conform to both the WG11 Style Guide and IEEE Standards Style Manual
Note that the 802.11 Style Guide evolves with our practice

## Slide 13: 802.11 Editor’s Guide
https://mentor.ieee.org/802.11/dcn/11/11-11-0875-04-0000-editor-s-guide.docx
This document contains material relevant to the job of being an 802.11 editor.
It is recommended that editors read this material before they start, as it may avoid them needlessly re-inventing the wheel. Frame 2017 is used at IEEE-SA.
Creating a Redline, Graphics, Numbering and ANA, Source Control. Subversion server for source control.
Comment Resolution and Publication

## Slide 14: Amendment & other ordering notes
Editors define publication order independent of working group public timelines:
  Since official timeline is volatile and moves around
  Publication order helps provide stability in amendment numbering, figures, clauses and other numbering assignments
  Editors are committed to maintain a rational publication order

## Slide 15: Editor Amendment Ordering
Data as of Nov 2018
See http://grouper.ieee.org/groups/802/11/Reports/802.11_Timelines.htm
In Nov 2017, Editors discussed REVmd schedule and possible completion in 2020. We will revisit the running order in January.
Amendment Number | Task Group | Projected REVCOM Date
REVmd REVmd Amendment 1 | TGax – 697 | May 2020 Dec 2019*
REVmd Amendment 2 | TGay – 679 | Dec 2019*
REVmd Amendment 3 | TGaz – 115 | Mar 2021
REVmd Amendment 4 | TGba – 90 | Sept 2020
 | *REVmd might be March or May, 2020 | 

## Slide 16: Email your draft status updates!
Each editor, please send update for next page via the editor’s reflector no later than Thursday am2 to update table on next page!

## Slide 17: Draft Development Snapshot
TG | Published or Draft Baseline Documents |  |  |  |  |  |  |  |  | Source | MDR | Style Guide | Editor | Snapshot Date
 | Published | aq | md | ax | ay | az | ba | bb |  |  |  |  |  | 
aq | Y | 14.0 |  |  |  |  |  |  |  | Frame 12.0 | Yes | 2012 | Lee Armstrong | 29-Apr
md | Y |  | 1.6 |  |  |  |  |  |  | Frame | No | 2012 | Emily Qi Edward Au | 13-Nov
ax | Y |  | 1.5 | 3.2 |  |  |  |  |  | Framemaker 2017 release | No | 2012 | Robert Stacey | 13-Nov
ay | Y | 14.0 | - | 3.0 | 2.1 |  |  |  |  | Word | No | 2012 | Carlos Cordeiro | 11-Nov
az | Y |  | 1.0 | 3.0 | 2.0 | 0.5 |  |  |  | Word | No | 2012 | Chao Chun Wang | 13-Nov
ba | Y |  | 1.2 | 3.0 | 1.4 | 0.3 | 1.0 |  |  | Framemaker 2017 release | No | 2012 | Po-Kai Wang | 12-Nov
bb |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Most current doc shaded green.
Nov 2018
Changes from last report shown in red.

## Slide 18: Editor Backup Practices
The IEEE Servers provide durable places to retain the 802.11 source files, drawing files, and other components of drafts.
Our best practice is that after a draft is posted in the Member’s Area, a zip file containing all the clean source files, drawing files and other components should be created and sent to the iMeetCentral source code archive for safekeeping.

## Slide 19: IEEEE iMeet central
IEEE-SA iMeet central site
https://imeetcentral.com/
Also used to share emails and large files
Upload zip files to central site

## Slide 20: Publication process
Publication editor creates a marked up PDF with editorial changes highlighted
802.11 technical editor forms a review committee, usual the task group editor and one other person associated with 802.11 editing
Each member of the committee should review each change proposed by the publication editor
Pay particular attention to
  Reconstructed sentences
  Tables with number changes
  ANA assignments
The review process is complete when all publication changes have been reviewed

## Slide 21: MIB Style, Visio and Frame Practices
I’m going to suggest going forward we use a single style with appropriately set tabs, and use leading Tabs to distinguish the syntax and description parts. (Adrian Stephens Feb 9, 2010)
Two ways to format a figure & its caption in frame:
  Insert a table. Insert anchored frame inside table cell to hold graphics. Use table caption as figure caption.
  Insert an anchored frame. Insert caption inside a text frame inside the anchored frame. Insert graphics inside the anchored frame.
Keep embedded figures using visio as long as possible (not in Word)
  Near the end of sponsor ballot, turn these all into .emf (windows meta file) format files (you can do this from visio using “save as”). Keep separate files for the .vsd source and the .emf file that is linked to from frame. There is high likelihood we should use .emf
Frame templates are available

## Slide 22: Two Technical Editors
Peter Ecclesine will run the face to face meetings
Robert Stacey will run the publication process
Robert Stacey is the ANA administrator
All are on the Editor’s email list.

## Slide 23: Build a list of Editor’s meeting discussion topics
YANG models to supplement MIB
Should we have a separate document for YANG models?
Note there is a YANG model from Wi-Fi Alliance publicly available, with ongoing work
https://www.wi-fi.org/file/data-elements-draft-specification-package
MIB normative text that should be in the main body? The default values are used outside the standard
MIB deprecation topic – should be a project, how to proceed?

## Slide 24: Actions
Emily to update 802.11 Style Guide with MIB object deprecation
Robert to find script to renumber Frame drawing file names
Robert – the formal language for frame sequencing (REVmd Annex G) should be addressed
The xxx-STA is implied by being in clause xxx (the 11ax MAC and PHY style)
There should be a submission with the 11ax MAC and PHY style discussion so amendment text
The style guide (and then MDR) should reflect 11ax MAC and PHY style
11az introduced trigger-based sounding, but cannot change other PHY sections (VHT sounding)