## Slide 1: 802.11bd Timeline
Date: 2019-01-10
Authors:

## Slide 2: Overview of Timelines for 802.11ac,11ax and 11p
Stage | Duration |  |  | 
 | 11ac [1] | 11ax [1][2] | 11ba [5] | 11p [3][4]
PAR approval -> Approved Standard | 64 months | 68 months | 46 months | 70 months
PAR approval -> Draft 1.0 | 34 months | 34 months | 22 months | 20 months
PAR approval -> D0.1 | 29 months | 20 months | 14 months | 6 months
D0.1 – Draft 1.0 | 6 months | 12 months | 8 months | 14 months
Draft 1.0 – Draft 2.0 | 8 months | 10 months | 4 months | 8 months
Draft 2.0 - Final | 22 months | 26 months | 20 months | 42 months

## Slide 3: Proposed Timeline for 802.11bd

## Slide 4: Proposed Timeline for 802.11bd
Stage | Duration |  |  |  | 
 | 11ac [1] | 11ax [1][2] | 11ba [5] | 11p [3][4] | Proposed for 11bd
PAR approval -> Approved Standard | 64 months | 68 months | 46 months | 70 months | 48 months (Nov/18 – Mar/24)
PAR approval -> Draft 1.0 | 34 months | 34 months | 22 months | 20 months | 24 months (Nov/18 – Nov/20)
PAR approval -> D0.1 | 29 months | 20 months | 14 months | 6 months (?) | 18 months (Nov/18 –May/20)
D0.1 –> Draft 1.0 | 6 months | 12 months | 8 months | 14 months | 6 months (May/20 – Nov/20)
Draft 1.0 –> Draft 2.0 | 8 months | 10 months | 4 months | 8 months | 6 months (Nov/20 – May/21)
Draft 2.0 -> Final | 22 months | 26 months | 20 months | 42 months | 18 months (May/21 – Nov/22)

## Slide 5: Straw Polls
Do you agree with the timeline presented above as the time estimates for the work in 802.11bd?
Yes:
No:
Abstain:

## Slide 6: References
[1] IEEE802.11-14/0649r1, “802.11ax Timeline Scenarios”
[2] IEEE802.11-18/0968r0, “TGax timeline”
[3] http://www.ieee802.org/11/Reports/802.11_Timelines.htm
[4] IEEE802.11-05/0090r0, “Wave Closing Report”
[5] IEEE802.11-18/2109r1 “January TGba agenda”

## Slide 7: Backup Slides

## Slide 8: 11p timeline
Par approval: 09-2004
[D0.1] Jan 2005 report= A draft amendment was presented and is available on the web site [Commenting started]
WG Letter ballots:
D1.0: 04-2006 (56%)
D2.0: 01-2007 (67%)
D3.0: 09-2007 (74%)
D4.0: 05-2008 (79%)
D5.0: 12-2008 (85%)
D6.0: 03-2009 (89%)
D7.0: 06-2009 (85%)
D8.0: 08-2009 (89%)
D9.0: 10-2009 (93%)
WG Sponsoer ballots
D9.0: 11-2009 (93%)
D10.0: 2-2010 (96%)
D11.0: 4-2010 (99%)
Standard board approval: 7-2010