## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-19/0156r08
Venue Date: | July 2019
First Author: | Michael Montemurro, BlackBerry
Subject: | REVmd Working Group Comments for PHY ad-hoc
Full Date: | 2019-07-04
Author(s): | Name(s) | Michael Montemurro
| Company | BlackBerry
Address
Phone:
Fax:
| email: | mmontemurro@blackberry.com
Abstract:
This document contains comments in the "PHY ad hoc" group, submitted on REVmd WG Ballot LB236 on the published Revmd D2.0.

## Revision History
Revision | Date | Description
0 | 2019-01-15 | Initial revision
1 | 2019-01-17 | Included PHY Motion A tab with comments discussed in Thurs PM1 session
2 | 2019-02-28 | Updated spreadsheet with additional comments on PHY Motion A; assigned comments
3 | 2019-03-12 | Updated spreadsheet with additional comments from GEN, MAC
4 | 2019-03-12 | Updated spreadsheet based on a review of PHY comments during TGmd Tuesday PM1 session
5 | 2019-03-15 | Updated spreadsheet based on a review of PHY comments during TGmd Wednesday PM1 session
6 | 2019-05-13 | Updated spreadsheet based on a review of PHY comments from March to May 11md.
7 | 2019-05-14 | Updated spreadsheet based on a review of PHY comments during May plenary
8 | 2019-07-04 | Update spreadsheet based on a review of PHY comments from May plenary to July 4

## PHY Motion F
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2045 | Assaf Kasher | 236 | 2 | 25.7.2.3 | 3509 | 41 | T | Y | 3509 | 41 | 25.7.2.3 |  | V | Haiming Wang | jaimin-doc |  | "A value of 0├ù0 in the PPDU Type(#1379) field indicates a BRP-RX PPDU" The text here contadicts the text in 25.3.9.1 (CMDG SIG). The value used there is "10" or 0x2 | Change 0x0 to 0x2 or preferably "0b10" | REVISED (PHY: 2019-07-02 18:59:09Z) - Incorporate the changes for CID 2045 and CID 2046 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 18:59:31Z - status set to: Ready for Motion PHY: 2019-04-05 00:17:04Z - status set to: Submission Required |  |  |  | 2019-07-02 19:00 | PHY
2177 | James Lepp | 236 | 2 | 17.2.3.1 | 2893 | 34 | T | N | 2893 | 34 | 17.2.3.1 |  | V | Menzo Wentink |  |  | The RXVECTOR parameter RSSI has an upper limit of "RSSI maximum" but there is no definition of RSSI maximum in the document. There are 7 instances of "RSSI maximum" in the document. | Define RSSI maximum | REVISED (PHY: 2019-05-16 15:15:12Z) - There are multiple places in the draft which uses the value “255” as the maximum RSSI value. Hence, propose to replace “RSSI maximum”, “RSSI max” and “8 bits” with “255”. Instruction to Editor (all PageLine locations are based on D2.2): Change “RSSI Max” to “255” at P495L16. Change “8 bits of RSSI” to “255” at P2887L26. Change “RSSI maximum” to “255” at P2903L35, P2904L32, P2949L60, P2962L56, P3068L12, P3432L48, P3461L18. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-16 15:14:32Z - status set to: Ready for Motion PHY: 2019-04-05 00:09:04Z - status set to: Submission Required |  |  |  | 2019-05-16 15:17 | PHY
2128 | Emily Qi | 236 | 2 | 25.6.8.12 | 3504 | 27 | T | N | 3504 | 27 | 25.6.8.12 |  | A | Haiming Wang | jaimin-doc |  | There are two definitions of TGI: 3504.20 and 3504.27. | Removed the second definition. | ACCEPTED (PHY: 2019-07-02 19:05:17Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:05:20Z - status set to: Ready for Motion PHY: 2019-04-05 00:16:29Z - status set to: Discuss |  |  |  | 2019-07-02 19:06 | PHY
2127 | Emily Qi | 236 | 2 | 25.6.8.11 | 3502 | 57 | T | N | 3502 | 57 | 25.6.8.11 |  | A | Haiming Wang | jaimin-doc |  | There are two definitions of TGI: 3502.50 and 3502.57. | Removed the second definition. | ACCEPTED (PHY: 2019-07-02 19:04:51Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:04:54Z - status set to: Ready for Motion PHY: 2019-04-05 00:16:21Z - status set to: Discuss |  |  |  | 2019-07-02 19:05 | PHY
2126 | Emily Qi | 236 | 2 | 25.3.3 | 3456 | 6 | T | N | 3456 | 6 | 25.3.3 |  | V | Haiming Wang | jaimin-doc |  | How is Table 22-8 related to this parameter? I think it should be Table 21-5 Timing-related constants. | At cited location, change "Table 22-8" to "Table 21-5 Timing-related constants". | REVISED (PHY: 2019-07-02 19:03:18Z) - - Incorporate the changes for CID 2126 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:03:40Z - status set to: Ready for Motion |  |  |  | 2019-07-02 19:04 | PHY
2049 | Assaf Kasher | 236 | 2 | 25.13.1 | 3521 | 6 | T | Y | 3521 | 6 | 25.13.1 |  | V | Haiming Wang | jaimin-doc |  | The receive procedure points to a receive state machine in figure 25-38, however, figure 25-38 is the PHY receive procedure. There is no receive state machine. | Add a receive state macine. | REVISED (PHY: 2019-07-02 19:02:20Z) - - Incorporate the changes for CID 2049 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:02:39Z - status set to: Ready for Motion PHY: 2019-06-10 15:22:58Z - status set to: Insufficient Detail PHY: 2019-04-05 00:17:55Z - status set to: Submission Required |  |  |  | 2019-07-02 19:03 | PHY
2023 | Assaf Kasher | 236 | 2 | 25.2 | 3452 | 50 | T | Y | 3452 | 50 | 25.2 |  | A | Haiming Wang | jaimin-doc |  | "RX_START_OF_FRAME_OFFSET" - using units of 10 nanosecond does make sense when the sampling rate is ~1GHz | replace 10 nanosecond with 100picosecond | ACCEPTED (PHY: 2019-07-02 19:00:46Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:00:51Z - status set to: Ready for Motion PHY: 2019-04-05 00:13:00Z - status set to: Submission Required |  |  |  | 2019-07-02 19:01 | PHY
2046 | Assaf Kasher | 236 | 2 | 25.7.2.3 | 3509 | 43 | T | Y | 3509 | 43 | 25.7.2.3 |  | J | Haiming Wang | jaimin-doc |  | "A value of 0├ù1 in the PPDU Type(#1379) field indicates a BRP-TX PPDU" The text here contradicts the text in 25.9.3.1 (CDMG SIG) The value used there is "11" or 0x3 | Change 0x1 to 0x3 or preferably to "0b11" | REJECTED (PHY: 2019-07-02 19:00:04Z) - - Incorporate the changes for CID 2045 and CID 2046 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:00:20Z - status set to: Ready for Motion PHY: 2019-04-05 00:16:58Z - status set to: Submission Required |  |  |  | 2019-07-02 19:00 | PHY
2312 | Mark RISON | 236 | 2 | 23.3.8.2.1.4 | 3337 | 27 | T | Y | 3337 | 27 | 23.3.8.2.1.4 |  | V | Yujin Noh | 11-19-0261 |  | "Used to indicate that frame is an NDP CMAC frame(#1143). If set to 1," -- not clear what if set to 0 | At the end of the para add "If set to 0, then the SIG format is undefined." | REVISED (PHY: 2019-05-31 18:57:23Z) - Here in this subclause, it is better to focus on the original purpose of S1G SIG field contents of a non NDP CMAC frame. As for an NDP CMAC frame, the corresponding indication is moved to 9.9 (NDP CMAC frames(11ah)) of MAC spec. TGm Editor: make changes according to this document https://mentor.ieee.org/802.11/dcn/19/11-19-0261-07-000m-resolutions-to-s1g-phy.docx | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-31 18:57:40Z - status set to: Ready for Motion PHY: 2019-04-26 14:39:23Z - status set to: Submission Required PHY: 2019-04-26 14:35:39Z - status set to: Ready for Motion PHY: 2019-03-12 16:03:16Z - status set to: Submission Required |  |  |  | 2019-05-31 18:58 | PHY
2044 | Assaf Kasher | 236 | 2 | 25.3.9.1 | 3469 | 17 | T | Y | 3469 | 17 | 25.3.9.1 |  | V | Haiming Wang | jaimin-doc |  | Add a link to the MCS table because it is far away and hard to find | As in comment | REVISED (PHY: 2019-07-02 18:57:56Z) - Incorporate the changes for CID 2044 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:12:55Z - status set to: Ready for Motion PHY: 2019-04-05 00:14:59Z - status set to: Submission Required |  |  |  | 2019-07-02 19:13 | PHY
2037 | Assaf Kasher | 236 | 2 | 25.3.5.3.1 | 3461 | 51 | T | Y | 3461 | 51 | 25.3.5.3.1 |  | V | Haiming Wang | jaimin-doc |  | "duplicate style" - I don't understand what does that mean. | Add a link to 25.3.10 | REVISED (PHY: 2019-07-02 18:57:18Z) Incorporate the changes for CID 2037 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 18:57:30Z - status set to: Ready for Motion PHY: 2019-04-05 00:14:06Z - status set to: Submission Required |  |  |  | 2019-07-02 18:58 | PHY
2036 | Assaf Kasher | 236 | 2 | 25.3.5.3.1 | 3461 | 55 | T | Y | 3461 | 55 | 25.3.5.3.1 |  | V | Haiming Wang | jaimin-doc |  | Figures 25-4, 25-5, and 25-6 show sequences of length 256 used in the preamble while the sequences are actually of length 32 | Fix figures 25-4, 25-5, 25-6 | REVISED (PHY: 2019-07-02 18:56:29Z) Incorporate the changes for CID 2036 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 18:56:43Z - status set to: Ready for Motion PHY: 2019-04-05 00:13:56Z - status set to: Submission Required |  |  |  | 2019-07-02 18:57 | PHY
2032 | Assaf Kasher | 236 | 2 | 25.2.2 | 3450 | 16 | T | Y | 3450 | 16 | 25.2.2 |  | V | Haiming Wang | jaimin-doc |  | "SPREADING_FACTOR" is missing from the TXVECTOR and RXVECTOR | Add a parameter "SPREADING_FACTOR" to the TX/RXVECTOR representing the equivalet CMMG field | REVISED (PHY: 2019-07-02 18:54:32Z) - Incorporate the changes for CID 2032 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 18:54:37Z - status set to: Ready for Motion PHY: 2019-04-05 00:12:44Z - status set to: Submission Required |  |  |  | 2019-07-02 18:55 | PHY
2027 | Assaf Kasher | 236 | 2 | 25.3.6 | 3464 | 12 | T | N | 3464 | 12 | 25.3.6 |  | J | Haiming Wang | jaimin-doc |  | $\sum_{i=N-K}^{N-1}D^i$ - it would be nice to add at the end of the sentence that this is equivalent to setting the shfit register bits to 1. | Add at the end of the sentence ". (This is equivalent to setting the shift register to all ones)." | REJECTED (PHY: 2019-07-02 18:48:41Z) - The description is consistent with the description given in clauses 19.3.9.4.4, 21.3.10.3, and 23.3.8.2.5. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 18:48:45Z - status set to: Ready for Motion |  |  |  | 2019-07-02 18:49 | PHY
2024 | Assaf Kasher | 236 | 2 | 25.3.2.3.6 | 3454 | 51 | T | Y | 3454 | 51 | 25.3.2.3.6 |  | V | Haiming Wang | jaimin-doc |  | Receiver Sensitiviy for MCS 0 is missing from table 25-2 | Add receiver sensitiviy for MCS 0. I believe is should be around -81 and -78 | REVISED (PHY: 2019-07-02 18:47:20Z) - Make the text changes for CID 2024 as documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 18:47:25Z - status set to: Ready for Motion PHY: 2019-04-05 00:13:10Z - status set to: Submission Required |  |  |  | 2019-07-02 18:48 | PHY
2047 | Assaf Kasher | 236 | 2 | 25.7.2.4 | 3510 | 1 | T | Y | 3510 | 1 | 25.7.2.4 |  | A | Haiming Wang | jaimin-doc |  | "Any transmit signal transients that occur due to this TX AWV configuration change" - which TX AWV configuration chagne? None were discussed in this sub clause | Move this sentence afterh the first sentence of the next paragraph | ACCEPTED (PHY: 2019-07-02 19:01:20Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:01:23Z - status set to: Ready for Motion PHY: 2019-04-05 00:17:19Z - status set to: Discuss |  |  |  | 2019-07-02 19:02 | PHY
2375 | Mark RISON | 236 | 2 | 25 |  |  | T | Y |  |  | 25 |  | A | Haiming Wang | jaimin-doc |  | The term "MIMO mode" is used but such a mode is not described | Change "MIMO mode" to "MIMO" throughout | ACCEPTED (PHY: 2019-07-02 19:07:00Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:07:03Z - status set to: Ready for Motion PHY: 2019-06-10 15:16:07Z - status set to: Submission Required |  |  |  | 2019-07-02 19:07 | PHY
2590 | Mark RISON | 236 | 2 | 12.4.3 | 2528 | 1 | G | Y | 2528 | 1 | 12.4.3 |  | J | Dan Harkins | 11-19/387 |  | The Password Identifier element is included in the unprotected authentication frame. It may violate the privacy of users (household). For example, it exposes a group of devices and number of devices that are sharing the same password. Particularly, when these devices belongs to the same household (apartment) in an apartment building, it violates the privacy of users/residents. | Delete the referenced subclause | REJECTED (PHY: 2019-07-03 14:31:57Z) - The feature is useful and not mandatory to use. There are new attacks possible with the use of password identifiers in SAE. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-03 14:32:00Z - status set to: Ready for Motion PHY: 2019-06-10 15:17:10Z - status set to: Insufficient Detail PHY: 2019-04-05 00:05:02Z - status set to: Submission Required |  |  |  | 2019-07-03 14:32 | PHY
2573 | Mark RISON | 236 | 2 |  |  |  | T | Y |  |  |  |  | A | Michael Montemurro |  |  | There are references to a "PMKID field" but no such field exists | Change "PMKID field" to "PMKID List field" throughout | ACCEPTED (PHY: 2019-05-31 19:13:25Z) Note to editor that this is a duplicate of CID 2205 | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-31 19:13:42Z - status set to: Ready for Motion PHY: 2019-04-05 00:02:10Z - status set to: Submission Required |  |  |  | 2019-05-31 19:14 | PHY
2550 | Mark RISON | 236 | 2 | 6.3.19.1.4 | 417 | 35 | T | Y | 417 | 35 | 6.3.19.1.4 |  | A | Michael Montemurro |  |  | "When the Key Type is Group or IGTK, and the key matches the existing GTK or IGTK installed as a result of exiting WNM sleep mode (see 11.2.3.16.1 (WNM sleep mode capability)), if any, or matches the existing GTK or IGTK installed as a result of receipt of EAPOL-Key frames (see 12.7.7.4 (Group key handshake implementation considerations))" -- missing an "if any" for the second case. Also not clear what "existing" means here | Change the cited text at the referenced location to "When the Key Type is Group or IGTK, and the key matches the GTK or IGTK, if any, installed as a result of receipt of EAPOL-Key frames (see 12.7.7.4 (Group key handshake implementation considerations)) or of exiting WNM sleep mode (see 11.2.3.16.1 (WNM sleep mode capability))" | ACCEPTED (PHY: 2019-05-31 19:12:43Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-31 19:12:47Z - status set to: Ready for Motion |  |  |  | 2019-05-31 19:13 | PHY
2546 | Mark RISON | 236 | 2 | 12.4.7.4 | 2538 | 6 | T | Y | 2538 | 6 | 12.4.7.4 |  | J | Dan Harkins |  |  | The approach used does not work, because the Scalar and Anti-Clogging Token fields are not elements, and hence could contain octet sequences that make them look like FFE, Finite Cyclic Group or Vendor Specific elements | Make the Scalar and Anti-Clogging fields self-identifying by making them elements, not fixed fields | REJECTED (PHY: 2019-07-03 14:33:43Z) The approach used is based on the lengths of components and not on their contents on how the contents “Look”. Multiple independent and interoperable implementations using this approach exist. The proposed change would make all existing implementations of SAE be non-compliant. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-03 14:33:54Z - status set to: Ready for Motion PHY: 2019-06-10 15:17:28Z - status set to: Insufficient Detail PHY: 2019-04-05 00:05:37Z - status set to: Submission Required |  |  |  | 2019-07-03 14:34 | PHY
2507 | Mark RISON | 236 | 2 |  |  |  | T | Y |  |  |  |  | V | Michael Montemurro |  |  | "into its IEEE 802.11 MAC" is weird. It looks from other cases that "STA" is intended, i.e. Supplicant/MGTK recipient is considered to be part of the SME | Change "MAC" to "STA" in "into its IEEE 802.11 MAC" in 12.7.7.2 and 14.6.3. After the change in 14.6.3 add a "NOTE---The MGTK recipient is part of the SME." | REVISED (PHY: 2019-05-31 19:15:25Z) - Relative to D2.0: At 2637.31, change “into its IEEE 802.11 MAC” to “into the MAC” At 2764.44, change “into its IEEE 802.11 MAC” to “into the MAC” Relative to D2.2: Change “IEEE 802.11 STA” to “IEEE 802.11 MAC” at 2632.3/6 and 2635.53/56 | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-31 19:15:12Z - status set to: Ready for Motion PHY: 2019-05-31 19:15:07Z - status set to: Discuss |  |  |  | 2019-05-31 19:15 | PHY
2500 | Mark RISON | 236 | 2 | 6.3.94.3.2 | 668 | 33 | T | Y | 668 | 33 | 6.3.94.3.2 |  | V | Michael Montemurro |  |  | "N/A" does not make sense as a valid range for the Key ID | Copy the Valid range cell from the table in 6.3.19.1.2 | REVISED (PHY: 2019-05-31 19:11:23Z) Make the changes shown in https://mentor.ieee.org/802.11/dcn/19/11-19-0322-06-000m-lb236-comment-resolutions-montemurro.docx under Proposed Resolution for CID 2500. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-31 19:12:18Z - status set to: Ready for Motion PHY: 2019-04-05 00:03:55Z - status set to: Submission Required |  |  |  | 2019-05-31 19:12 | PHY
2206 | Jouni Malinen | 236 | 2 | 14.4.10 | 2752 | 26 | T | Y | 2752 | 26 | 14.4.10 |  | V | Kaz Sakoda |  |  | MPM FSM description of the ESTAB state actions in 14.4.10 is not consistent with the MPM finite state machine definition in Table 14-2: description of the OPN_RJCT and CNF_RJCT events is missing. Because of this, the "All other events shall be ignored in this state" requirement would be followed and that would not be consistent with Table 14-2. | On page 2752 line 21, insert two new paragraphs: "When an OPN_RJCT event occurs, the mesh STA shall clear the confirmTimer, perform a sndCLS action using the reason code as specified by the OPN_RJCT event, and set the holdingTimer. The finite state machine shall transition to HOLDING state." and "When a CNF_RJCT event occurs, the mesh STA shall clear the confirmTimer, perform a sndCLS action using the reason code as specified by the CNF_RJCT event, and set the holdingTimer. The finite state machine shall transition to HOLDING state.". | REVISED (PHY: 2019-05-16 16:05:02Z) Insert two paragraphs after the third paragraph of 14.4.10: "When an OPN_RJCT event occurs, the mesh STA shall perform a sndCLS action using the reason code as specified by the OPN_RJCT event, and set the holdingTimer. The finite state machine shall transition to HOLDING state. When a CNF_RJCT event occurs, the mesh STA shall perform a sndCLS action using the reason code as specified by the CNF_RJCT event, and set the holdingTimer. The finite state machine shall transition to HOLDING state." | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-16 16:05:14Z - status set to: Ready for Motion |  |  |  | 2019-05-16 16:05 | PHY
2417 | Mark RISON | 236 | 2 | 9.4.1.49 | 934 | 35 | E | Y | 934 | 35 | 9.4.1.49 |  | V | Mark Rison |  |  | Table 9-78---Subcarriers for which a Compressed Beamforming Feedback Matrix subfield and surrounding should refer to subcarrier indices (not just subcarriers) where it's referring to an index rather than the general concept. Also, "Each SNR value per tone" should refer to "subcarrier" not "tone" (also a few other instances in other Clause 9 subclauses) | In Subclauses 9.4.1.27/28/29/49/50/52/62 change "tone" to "subcarrier" throughout. In Subclauses 9.4.1.26/27/28/29 change "carrier" to "subcarrier" throughout, when not in "subcarrier" | REVISED (PHY: 2019-06-25 19:48:17Z) - Make the changes shown under “Proposed changes” for CID 2417 in https://mentor.ieee.org/802.11/dcn/19/11-19-0856-03-000m-resolutions-for-some-comments-on-11md-d2-0-lb236.docx, which consistently refer to subcarriers as such in the MAC clauses, and consistently identify them using an index. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-06-25 19:48:53Z - status set to: Ready for Motion PHY: 2019-04-05 00:04:38Z - status set to: Submission Required EDITOR: 2019-01-15 02:40:46Z - status set to: Discussion |  |  |  | 2019-06-25 19:49 | PHY
2207 | Jouni Malinen | 236 | 2 | 12.7.10.1 | 2650 | 19 | T | N | 2650 | 19 | 12.7.10.1 |  | A | Michael Montemurro |  |  | Authenticator state machine does not include possibility of getting PMK from SAE. There is only INITPMK and INITPSK states for setting PMK. The SAE case (PMK derived as part of Authentication frame exchange) does not seem to be covered. | Add INITSAE state next to the INITPSK state with "PMK = PMK from SAE" contents and UCT transition to PTKSTART. AUTHENTICATION2 state to INITSAE state transition condition set to "SAE". On page 2653 line 42, replace "INITPMK or INITPSK" with "INITPMK, INITPSK, or INITSAE". On page 2653 line 26, add "INITSAE: This state is entered when SAE authentication is completed successfully." | ACCEPTED (PHY: 2019-05-31 18:58:28Z) Note to editor. The figure changes need to be made to figure 12-50 (relative to D2.0) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-31 19:02:29Z - status set to: Ready for Motion |  |  |  | 2019-05-31 19:03 | PHY
2374 | Mark RISON | 236 | 2 | 25.6.4.2 | 3490 | 16 | T | Y | 3490 | 16 | 25.6.4.2 |  | A | Haiming Wang | jaimin-doc |  | "This is need only for the CMMG OFDM MIMO mode mechanism." is not grammatical, and is not clear either | Change the cited text at the referenced location to "This only applies to the CMMG OFDM mode MIMO mechanism." | ACCEPTED (PHY: 2019-07-02 19:06:31Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:06:34Z - status set to: Ready for Motion PHY: 2019-04-05 00:15:56Z - status set to: Discuss PHY: 2019-04-05 00:15:53Z - status set to: Discussion |  |  |  | 2019-07-02 19:07 | PHY
2373 | Mark RISON | 236 | 2 | 25.5.3.2 | 3478 | 12 | T | Y | 3478 | 12 | 25.5.3.2 |  | A | Haiming Wang | jaimin-doc |  | "This is need only for the CMMG SC mode MIMO mechanism." is not grammatical, and is not clear either | Change the cited text at the referenced location to "This only applies to the CMMG SC mode MIMO mechanism." | ACCEPTED (PHY: 2019-07-02 19:05:54Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:05:52Z - status set to: Ready for Motion |  |  |  | 2019-07-02 19:06 | PHY
2355 | Mark RISON | 236 | 2 | 25.3.3 | 3456 | 6 | T | Y | 3456 | 6 | 25.3.3 |  | A | Haiming Wang | jaimin-doc |  | T_SYML can obviously not be T_SYML or T_SYMS | Change the entry in the Parameter cell to "T_SYM" | ACCEPTED (PHY: 2019-07-02 19:04:22Z) | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:04:26Z - status set to: Ready for Motion PHY: 2019-04-05 00:13:46Z - status set to: Submission Required |  |  |  | 2019-07-02 19:05 | PHY
2333 | Mark RISON | 236 | 2 | 14.9.2 | 2767 | 32 | T | Y | 2767 | 32 | 14.9.2 |  | J | Kaz Sakoda |  |  | It is not clear why the 14.9.2 metric is in units of 0.01 TU but the 14.9.3 metric is in units of 0.01 us | In the referenced subclause change "The airtime link metric shall be encoded as an unsigned integer in units of 0.01 TU." to "The airtime link metric shall be encoded as an unsigned integer in units of 0.01 <micro>s." | REJECTED (PHY: 2019-05-16 16:08:23Z) -. Changing the unit of the airtime link metric is not encouraged, as it should cause backward compatibility issue. Do not apply any changes.The high PHY rate airtime link metric has been added with x1024 finer resolution. [ | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-16 16:10:31Z - status set to: Ready for Motion |  |  |  | 2019-05-16 16:11 | PHY
2313 | Mark RISON | 236 | 2 | 23.3.8.2.1.4 | 3337 | 27 | T | Y | 3337 | 27 | 23.3.8.2.1.4 |  | V | Yujin Noh |  |  | "If set to 1, then the SIG field format is shown in Figure 23-21" -- huh? This makes no sense, since the table this statement is in is all about the SIG field format | Change to "If set to 1, ignore eveything else in this subclause and look at Figure 23-21 instead." | REVISED (PHY: 2019-05-31 14:36:52Z) - Here in this subclause, it is better to focus on the original purpose of S1G SIG field contents of a non NDP CMAC frame. As for an NDP CMAC frame, the corresponding indication is moved to 9.9 (NDP CMAC frames(11ah)) of MAC spec. TGm Editor: make changes according to this document https://mentor.ieee.org/802.11/dcn/19/11-19-0261-07-000m-resolutions-to-s1g-phy.docx. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-31 14:37:00Z - status set to: Ready for Motion PHY: 2019-03-12 16:03:11Z - status set to: Submission Required |  |  |  | 2019-05-31 14:38 | PHY
2602 | Mark RISON | 236 | 2 | 24.4.3.2.1 |  |  | T | Y |  |  | 24.4.3.2.1 |  | V | Jaimin | jaimin-doc |  | Table 24-6 should be aligned with Table 20-11 (DMG v. CDMG) | As it says in the comment | REVISED (PHY: 2019-07-02 19:10:45Z) - Incorporate the changes for CID 2602 documented in https://mentor.ieee.org/802.11/dcn/19/11-19-1034-01-000m-proposed-resolutions-for-11aj-related-comments-in-revmd-lb236.doc. | PHY | PHY Motion F | Ready for Motion | PHY: 2019-07-02 19:10:40Z - status set to: Ready for Motion PHY: 2019-04-05 00:02:45Z - status set to: Submission Required From Jaimin: Proposed resolution: Reject Compared to Table 20-11, two reserved bits in Table 24-6 are used as field “Robust PHY Mode Indication/Reserved bits” to indicate the Robust PHY Mode, which is introduced in 802.11aj to enlarge the data PHY coverage for small antenna array mobile devices. Therefor Table 24-6 cannot be aligned with Table 20-11. More information can be found in the following documents regarding technical proposal of the robust PHY mode and the discussion about backward compatibility issue between DMG and CDMG STAs. https://mentor.ieee.org/802.11/dcn/16/11-16-0456-00-00aj-overview-of-802-11aj-60ghz-and-its-backward-compatibility-features.ppt https://mentor.ieee.org/802.11/dcn/16/11-16-0719-01-00aj-proposed-resolution-to-cid-100-101-102-etc-in-lb217.docx |  |  |  | 2019-07-02 19:11 | PHY
2499 | Mark RISON | 236 | 2 | 6.3.94.2.2 | 667 | 54 | T | Y | 667 | 54 | 6.3.94.2.2 |  | V | Michael Montemurro |  |  | "N/A" does not make sense as a valid range for the Key ID | Copy the Valid range cell from the table in 6.3.19.1.2 | REVISED (PHY: 2019-05-31 19:03:20Z) - At the cited location replace “N/A” with “0-3 shall be used with CCMP and GCMP; 4-5 with BIP for IGTK; 6-7 with BIP for BIGTK; and 8-4095 are reserved” | PHY | PHY Motion F | Ready for Motion | PHY: 2019-05-31 19:03:24Z - status set to: Ready for Motion PHY: 2019-04-05 00:03:49Z - status set to: Submission Required |  |  |  | 2019-05-31 19:04 | PHY

## Motion CCA-ED
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2187 | John Coffey | 236 | 2 | 19.1.1 | 2949 | 14 | T | Y | 2949 | 14 | 19.1.1 |  | V | Sean Coffey |  |  | "... an HT STA shall be capable of transmitting and receiving frames that are compliant with" [11g, 11b]. Does this mean that an HT STA is by definition an ERP or HR/DSSS STA as well? This is not so clear, because the CCA requirements are worded quite differently. It should be made clear. | Add at end of paragraph: "An HT STA that operates in the 5 GHz band shall be an OFDM (Clause 17) STA. An HT STA that operates in the 2.4 GHz band shall be an ERP STA. NOTE--Clauses 15 and 16 define CCA requirements for NonERP DSSS and NonERP HR/DSSS STAs respectively. The CCA requirements for HT STAs defined in this clause supersede those of Clauses 15 and 16." | REVISED (PHY: 2019-05-14 19:25:09Z) - In 19.1.1 (Introduction to the HT PHY), at D2.0 2949.23, add new paragraph "An HT STA that operates in the 5 GHz band shall comply with all normative requirements of Clause 17. An HT STA that operates in the 2.4 GHz band shall comply with all normative requirements of Clause 18.” | PHY | Motion CCA-ED | Ready for Motion | PHY: 2019-05-14 19:25:17Z - status set to: Ready for Motion |  |  |  | 2019-05-14 19:28 | PHY
2182 | John Coffey | 236 | 2 | 18.1.1 | 2936 | 13 | T | Y | 2936 | 13 | 18.1.1 |  | V | Sean Coffey |  |  | (This comment is linked to several others concerning CCA.) Add explanatory note saying that an ERP STA really is a fully compliant DSSS and HR/DSSS STA, even though it does not necessarily follow the exact CCA deifinitions from Clauses 15 and 16. | Add at end of paragraph: "An ERP STA shall be a DSSS STA and an HR/DSSS STA. NOTE--Clauses 15 and 16 define CCA requirements for NonERP DSSS and NonERP HR/DSSS STAs respectively. The CCA requirements for ERP STAs defined in this clause supersede those of Clauses 15 and 16." | REVISED (PHY: 2019-05-14 19:23:30Z) In 18.1.2 (Introduction), at 2936.17-25, add new sentence after first sentence: “An ERP STA shall comply with all normative requirements of Clause 16.” (Same proposed resolution as for CID 2179 above.) | PHY | Motion CCA-ED | Ready for Motion | PHY: 2019-05-14 19:23:41Z - status set to: Ready for Motion |  |  |  | 2019-05-14 19:28 | PHY
2180 | John Coffey | 236 | 2 | 16.3.8.5 | 2888 | 58 | T | Y | 2888 | 58 | 16.3.8.5 |  | V | Sean Coffey |  |  | "dot11HRCCAModeSupported shall indicate the appropriate operation modes. The PHY shall be conifgured through dot11Current CCAMode." What should happen if the device is ERP or HT, and it does not exactly follow these HR/DSSS CCA definitions? | Add at beginning of section "A NonERP HR/DSSS STA shall satisfy all requirements in this section." At line 33, change "The HR/DSSS PHY" to "The STA" (or "The NonERP HR/DSSS STA"). Make similar change at 2858.48 (with "DSSS" instead of "HR/DSSS"). | REVISED (PHY: 2019-05-14 19:22:00Z) - In 15.4.6.5 (CCA), at D2.0 2858.34, add new paragraph before current first paragraph: “Requirements in this subclause are applicable to non-ERP DSSS STAs.”." In 15.4.6.5 (CCA), at D2.0 2858.47, change “The value” to “For a non-ERP DSSS STA, the value“. In 16.3.8.5 (CCA), at D2.0 2888.32, add new paragraph before current first paragraph: “Requirements in this subclause are applicable to non-ERP HR/DSSS STAs.”." In 16.3.8.5 (CCA), at D2.0 2888.58, add at beginning of line “For a non-ERP HR/DSSS STA, “. | PHY | Motion CCA-ED | Ready for Motion | PHY: 2019-05-14 19:22:02Z - status set to: Ready for Motion |  |  |  | 2019-05-14 19:28 | PHY
2179 | John Coffey | 236 | 2 | 16.3.8.5 | 2888 | 33 | T | Y | 2888 | 33 | 16.3.8.5 |  | V | Sean Coffey | 11-19-473r1 |  | Is an ERP STA necessarily a compliant HR/DSSS STA? Is an HT STA at 2.4 GHz necessarily either an HR/DSSS STA or an ERP STA? The answer to these questions is murky given the current draft. The reason is that the definitions of CCA differ in each of the sections. For example, it is not clear whether ERP's definition of CCA (sections 18.3.4 and 18.4.6) supplements or supplants the HR/DSSS definitions (section 16.3.8.5). In some circumstances it might be important to be able to say with confidence whether a STA is compliant or not, so we should fix this. The proposed change takes the "supplant" approach. | Add at beginning of section "A NonERP HR/DSSS STA shall satisfy all requirements in this section." At line 33, change "The HR/DSSS PHY" to "The STA" (or "The NonERP HR/DSSS STA"). Make similar change at 2858.25 (with "DSSS" instead of "HR/DSSS"). | REVISED (PHY: 2019-05-14 19:20:16Z) - In 15.4.6.3 (Receiver maximum input level), at D2.0 2857.58, change “The receiver” to “If the STA is NonERP, the receiver”. In 15.4.6.5 (CCA), at D2.0 2858.25, add new first paragraph “Requirements in this subclause are applicable to non-ERP DSSS STAs.””. (Same place) change “The DSSS PHY” to “The non-ERP DSSS STA”. In 16.3.8.3 (Receiver maximum input level), at D2.0 2888.3, change “The receiver” to “If the STA is non-ERP, the receiver”. In 16.3.8.5 (CCA), at D2.0 2888.33, add new first paragraph “Requirements in this subclause are applicable to non-ERP HR/DSSS STAs.””. (Same place) change “The HR/DSSS PHY” to “The non-ERP HR/DSSS STA”. In 18.1.2 (Introduction), at 2936.17-25, add new sentence after first sentence: “An ERP STA shall comply with all normative requirements of Clause 16.” In 18.3.4 (CCA), at D2.0 2942.12, change “17.3.2 (PPDU format)” to “18.3.2 (PPDU format)”. In 18.4.6 (CCA performance), at D2.0 2943.30, change “valid ERP-DSSS/CCK sync symbols” to “valid DSSS, HR-DSSS, ERP-DSSS or ERP-CCK sync symbols”. | PHY | Motion CCA-ED | Ready for Motion | PHY: 2019-05-14 19:19:54Z - status set to: Ready for Motion |  |  |  | 2019-05-14 19:28 | PHY

## Insufficient Details
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2689 | Thomas Derham | 236 | 2 | 4.10.7 | 294 | 57 | T | N | 294 | 57 | 4.10.7 |  |  | Thomas Derham |  |  | In PMKSA caching, STA sends one or more PMKIDs in the clear in (Re)Assoc Request frame (or Auth frame in FILS case). In cases where PMK lifetime and caching period are long, the same PMKID might be sent each time a STA connects to the same AP/network, and this could be used by bad actors to track a user's location with privacy implications. | Provide means by which, e.g. during each auth/assoc procedure, the AP can securely provision STA with a randomly-generated pseudonym for the PMKID which the STA uses on the next auth/assoc with that AP |  | PHY | Insufficient Details | Submission Required | PHY: 2019-03-13 22:16:23Z - status set to: Submission Required |  |  |  | 2019-07-04 14:11 | PHY
2050 | Assaf Kasher | 236 | 2 |  | 3520 |  | T | Y | 3520 |  |  |  |  | Assaf Kasher |  |  | In the receive procedure there is no reference as to what does the receiver do with a bad CRC in the decoding of each LDPC word. If the procedure does not specify behavior, or which primitive is used to transfer this to the MAC those bits are wasted. | Maybe sending a primitive of bad/OK CRC in between PHY_DATA can be usefull. It can help if there is a receive state machine that tells what to do in this case |  | PHY | Insufficient Details | Submission Required | GEN: 2019-03-11 21:55:38Z - Discussed comment and possible need for information in the PHY, it can pass to MAC, but no PHY state machine to use it. This should be sent to the Tgaj group. GEN: 2019-01-25 22:47:05Z - status set to: Submission Required |  |  |  | 2019-07-03 13:33 | PHY
2051 | Assaf Kasher | 236 | 2 | 17.3.5.5 | 2906 | 60 | T | Y | 2906 | 60 | 17.3.5.5 |  |  | Assaf Kasher | 2165-11-18 |  | "If dot11MACPrivacyActivated is true, the initial state of the scrambler shall be reset when the STA's MAC address is changed." - There are a few problems here: 1) How does the PHY know that the MAC address have chagned. 2) If it is supposed to be pseudo-random, what does resetting it mean? 3) sometimes the scrambler initialization conveys information - how does that reconcile with resetting? | See submission 11-18-2165 |  | PHY | Insufficient Details | Submission Required | PHY: 2019-03-11 21:59:56Z - status set to: Submission Required |  |  |  | 2019-07-04 14:24 | PHY
2052 | Assaf Kasher | 236 | 2 | 3.2 | 176 | 43 | T | Y | 176 | 43 | 3.2 |  |  | Jaimin |  |  | "China directional multi-gigabit (CDMG): Pertaining to operation in DMG and where the channel is contained within the Chinese 60 GHz frequency band" - it seems that Chinese 60GHz band is contained with other reglulatory domain bands: US or Europe for example. Can CDMG BSS operate in Europe or the US | Clarify |  | PHY | Insufficient Details | Submission Required | GEN: 2019-01-25 22:46:47Z - status set to: Submission Required |  |  |  | 2019-07-03 13:28 | PHY
2067 | Assaf Kasher | 236 | 2 | 24.9.2.2.2 | 3444 | 7 | T | Y | 3444 | 7 | 24.9.2.2.2 |  |  | Jaimin Chen |  |  | "The STF and the CE field at the end of BRP PPDU" - what structure does these fields have? I can guess they have the same structure as the STF and CE at the beginning of the PPDU, but its only a guess | Specify that these fields have the same structure as the STF and CE at the beginning of the PPDU |  | PHY | Insufficient Details | Submission Required | PHY: 2019-04-05 00:11:49Z - status set to: Submission Required |  |  |  | 2019-07-03 13:29 | PHY
2068 | Assaf Kasher | 236 | 2 | 24.9.2.2.2 | 3444 | 8 | T | Y | 3444 | 8 | 24.9.2.2.2 |  |  | Jaimin Chen |  |  | "are used for measuring and training the alternative link of CDMG STAs during enhanced beam tracking" - what antenna setting (AWV) is used to transmit and receive these fields. | Specify what AWV/Sector is used for transmission and what for reception and how does the initiator and responder know this. |  | PHY | Insufficient Details | Submission Required | PHY: 2019-04-05 00:11:56Z - status set to: Submission Required |  |  |  | 2019-07-03 14:58 | PHY
2021 | Assaf Kasher | 236 | 2 | 24.6 | 3439 | 57 | T | N | 3439 | 57 | 24.6 |  |  | Jaimin Chen |  |  | CDMG low-power SC mode is equivalent to the DMG LP SC PHY that has been made obsolete. It should also be made obsolete | Declare CDMG LP SC mode obsolete |  | PHY | Insufficient Details | Submission Required | PHY: 2019-04-05 00:11:39Z - status set to: Submission Required |  |  |  | 2019-07-03 13:28 | PHY
2712 | yujin noh | 236 | 2 | 19.3.9.3.3 | 2977 | 42 | T | N | 2977 | 42 | 19.3.9.3.3 |  |  | Menzo Wentink |  |  | Looking at P2977L42, it says that the L-STF is identical to the Clause 17 (Orthogonal frequency division multiplexing (OFDM) PHY specification) short training symbol. The non-HT short training OFDM symbol in the 20 MHz channel width is shown in Equation (19-8). However, there seems to be inconsistency between 11a STF sequence related Equations (17-6), (17-7) and L-STF sequence related Equations (19-8), (19-10). It presents different power scaling factors on two different clauses. Clause 19 (and later clauses) absorbs the part of scaling factor in the Equation (19-8) and also adds per antenna CSD. | Option 1) At P2977L42, corresponding description deleted such as "The L-STF in the 20 MHz channel width is shown in Equation (19-8). However if we want to point out that there is no L-STF change between clause 17 and clause 19 (excluding CSD and scaling factors), Option 2) might be desirable. Option 2) change Equation (17-6) to use the scaling factor of sqrt (1/2) and update Equation (17-7) to include another factor of N_L_STF to be consistent with later clauses. |  | PHY | Insufficient Details | Insufficient Detail | PHY: 2019-06-10 15:18:29Z - status set to: Insufficient Detail |  |  |  | 2019-07-04 14:25 | PHY
2291 | Mark Hamilton | 236 | 2 | 20.9.2.2 | 3096 | 50 | T | Y | 3096 | 50 | 20.9.2.2 |  |  | Mark Hamilton |  |  | BRP packet structure has some problems in details. The bullet list items in 20.9.2.2.1 both say, "BRP-[TR]X PPDUs are packets that have TRN training subfields appended to them." First, this isn't necessarily true, as the BRP PPDU could be a request for training TRNs, and not carry any itself. Also, these two sentences look like the define/describe BRP PPDUs, but they define the RX and TX variants identically, which isn't useful. The following sentences are the useful part. The definition of "training field(s)" is not clear, so the meaning of "Traning Length" in Table 20-11 (etc) is not clear. In fact, this field is not a length at all, but a number _N_ that can be used to derive the number (and therefore length of) the AGC and TRN subfields. Also, the AGC/TRN subfields are sometimes called "training fields" and sometimes "a training field". Since both of these fields actually have internal structure (they are not just a list of AGC sequences, nor TRN subfields, it is probably best to call these a distinguishable and singular name. Why does subclause 20.9.2.2.2 start with (or detail at all) the rules about setting [TR]XVECTOR parameters? 20.4.2 and 20.5.2 claim to be definitions of the PPDU formats, but there is no (obvious) definition of the AGC and TRN subfields in those clauses. A reference would be helpful. "A value of N in the Training Length field indicates 4├ùN AGC subfields" - does this mean the AGC (sub)field(s) has that many "AGC fields" (each of which is 4N repetitions of the Golay sequence), or there are just a total of 4N repetitions of the Golay sequence? "and that the TRN-R/T field has N TRN-Units" - There is no TRN-R/T field. | A submission will be provided. |  | PHY | Insufficient Details | Submission Required | PHY: 2019-02-28 20:48:38Z - status set to: Submission Required |  |  |  | 2019-07-04 14:26 | PHY
2690 | Thomas Derham | 236 | 2 | 12.4.7.4 | 2537 | 56 | T | N | 2537 | 56 | 12.4.7.4 |  |  | Thomas Derham |  |  | In SAE when Password Identifier is used, STA sends Password Identifier in the clear in Auth frame. Since the Password Identifier is typically the identifier of a long-term password, the same Password Identifier would be sent each time a STA performs SAE authentication with a given network, and this could be used by bad actors to track a user's location with privacy implications. | Provide means by which, e.g. during each SAE auth/assoc procedure, the AP can securely provision STA with a randomly-generated pseudonym for the SAE Password Identifier which the STA uses on the next SAE auth/assoc with that AP |  | PHY | Insufficient Details | Submission Required | PHY: 2019-03-13 21:14:47Z - status set to: Submission Required |  |  |  | 2019-07-04 14:13 | PHY
2685 | Stephen McCann | 236 | 2 | 12.2.10 | 2518 | 24 | T | N | 2518 | 24 | 12.2.10 |  |  | Roger Marks | 11-19/286 |  | Regarding MAC address privacy, a simple scheme to advertise the capability of a local administered LAN was discussed in 802.11 ARC (November 2018, see https://mentor.ieee.org/802.11/dcn/18/11-18-2022-00-0arc-local-administrator-advertisements.ppt). It was suggested to create a submission to add such functionality to Draft P802.11REVmd_D2.0.pdf. | Commenter will provide a submission. |  | PHY | Insufficient Details | Submission Required | PHY: 2019-01-15 14:40:11Z - status set to: Submission Required https://mentor.ieee.org/802.11/dcn/19/11-19-0134-01-000m-mac-address-policy-anqp-element.docx |  |  |  | 2019-07-04 14:13 | PHY
2670 | Michael Montemurro | 236 | 2 | 12.2.10 | 2518 | 45 | T | N | 2518 | 45 | 12.2.10 |  |  | Assaf Kasher | 2165-11-18 |  | The reference to changing scrambler settings is PHY dependent. The text needs to be update to indicate so. | Commenter will provide a submission to update the cited text. |  | PHY | Insufficient Details | Submission Required | PHY: 2019-01-15 14:40:28Z - status set to: Submission Required Related to CID 2051 - the contribution will address this comment as well. |  |  |  | 2019-07-04 14:12 | PHY
2387 | Mark RISON | 236 | 2 | 25.3.9.1 | 3467 | 41 | T | Y | 3467 | 41 | 25.3.9.1 |  |  | Assaf Kasher |  |  | Table 25-7---Fields in the CMMG SIG field needs the same changes as made under CID 1351. However Assaf reports that it "requires (a lot of) more work because the scrambling is not mentioned in the encoding process." | Ask Assaf to kindly to the more work |  | PHY | Insufficient Details | Submission Required | PHY: 2019-04-05 00:14:25Z - status set to: Submission Required |  |  |  | 2019-07-04 15:09 | PHY
2244 | Mark Hamilton | 236 | 2 | 15.2.2.3 | 2836 | 56 | T | Y | 2836 | 56 | 15.2.2.3 |  |  | Menzo Wentink |  |  | Obsolete (legacy) "Antenna ID", TX_ANTENNA, RX_ANTENNA, dot11CurrentRXAntenna, dot11CurrentTXAntenna, ANT_STATE, and the Antenna element. The linkage between the signaled antenna and the actually used antenna is never stated, so this is not useful/usable. | Using the usual language, mark as obsolete: - TX_ANTENNA at P2836.56, P2837.20, P2877.24. - RX_ANTENNA at P2837.50, P2838.37, P2877.22, P2893.59. - dot11CurrentRXAntenna at P2849.25, P2874.40, P2933.36, P2945.48, P3040.22, P4155.57. - dot11CurrentTXAntenna at P2849.21, P2874.37, P2933.33, P2945.45, P3040.19, P4155.22. - Antenna element at P1136.28. - dot11RMAntennaInformationActivated at P3797.4. |  | PHY | Insufficient Details | Submission Required | PHY: 2019-04-05 00:08:10Z - status set to: Submission Required |  |  |  | 2019-07-04 14:24 | PHY
2284 | Mark Hamilton | 236 | 2 | 8.3.5.6.2 | 761 | 30 | T | Y | 761 | 30 | 8.3.5.6.2 |  |  | Menzo Wentink |  |  | 8.3.5.6.2 says "The required PHY parameters are listed in 8.3.4.3 (PHY SAP service primitives parameters)." But, 8.3.4.3 just says "A set of parameters" for PHY-TXSTART.confirm (and .request).q | Change reference to somewhere that describes these "PHY parameters". |  | PHY | Insufficient Details | Submission Required | PHY: 2019-04-05 00:04:13Z - status set to: Submission Required |  |  |  | 2019-07-04 14:12 | PHY
2069 | Assaf Kasher | 236 | 2 | 20.9.2.2.5 | 3099 | 43 | T | Y | 3099 | 43 | 20.9.2.2.5 |  |  | Assaf Kasher |  |  | "Any transmit signal transients that occur due to this TX AWV configuration change" - which TX AWV configuration chagne? None were discussed in this paragraph | Move this as the third sentence in the next paragraph |  | PHY | Insufficient Details | Insufficient Detail | PHY: 2019-06-10 15:19:12Z - status set to: Insufficient Detail PHY: 2019-04-05 00:10:15Z - status set to: Submission Required |  |  |  | 2019-07-04 14:26 | PHY

## Pending-additional-feedback
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2295 | Mark Hamilton | 236 | 2 | C.3 | 3778 | 50 | T | Y | 3778 | 50 | C.3 |  |  | Mark Hamilton and Mark Rison |  |  | dot11AuthenticationResponseTimeout is deprecated, but it doesn't say why (by convention, it should). There is no obvious reason why this is deprecated. | Change "Deprecated" to "current" |  | PHY | Pending-additional-feedback | Submission Required | PHY: 2019-04-03 23:33:45Z - status set to: Submission Required PHY: 2019-02-28 21:03:37Z - status set to: Discussion PHY: 2019-02-28 21:03:30Z - status set to: Discuss |  |  |  | 2019-07-04 15:40 | PHY
2601 | Mark RISON | 236 | 2 | 19 |  |  | T | Y |  |  | 19 |  |  | Mark Rison |  |  | Re CID 1468: need to be clearer that the ED thresholds are based on declaring busy *if* a PPDU of a given type with energy above a certain threshold is present, not based on detecting a PPDU of a given type and *then* checking the energy is above the corresponding threshold | As it says in the comment | In the table in 6.5.4.3 When generated (in the aCCATime row), in 17.3.10.6 CCA requirements, in 18.4.6 CCA performance, in 19.3.19.5.4 CCA sensitivity in 20 MHz, in 19.3.19.5.5 CCA sensitivity in 40 MHz (2x), in 20.4.4.2.2 CCA, in 20.5.4.2.2 CCA, in 24.4.4.2.2 CCA, in 24.5.4.2.2 CCA, 25.4.6.2.2 CCA, 25.5.7.2.2 CCA, 25.6.9.3.2 CCA: change “a valid” to “a” or “an”, as appropriate for the starting sound of the following word. | PHY | Pending-additional-feedback | Review | PHY: 2019-07-02 20:18:22Z - status set to: Review PHY: 2019-05-24 17:26:23Z - status set to: Submission Required PHY: 2019-05-15 19:24:04Z - status set to: Discuss PHY: 2019-04-12 15:06:44Z - status set to: Ready for Motion PHY: 2019-02-15 21:35:56Z - status set to: Submission Required |  |  |  | 2019-07-04 15:40 | PHY
2029 | Assaf Kasher | 236 | 2 | 25.3.13 | 3472 | 59 | T | Y | 3472 | 59 | 25.3.13 |  | J | Haiming Wang | jaimin-doc |  | This text follows the RCPI clause as it was in the original 11ad standard. Over time the text in 20.3.10 changed. I prefer that the text in 20.3.10 alligns with the text here, the group may decide otherwise | allign the text in 25.3.13 with other RCPI subclauses | REJECTED (PHY: 2019-07-02 18:52:03Z) - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | PHY | Pending-additional-feedback | Ready for Motion | PHY: 2019-07-02 18:52:09Z - status set to: Ready for Motion PHY: 2019-06-10 15:20:46Z - status set to: Insufficient Detail PHY: 2019-04-05 00:15:07Z - status set to: Submission Required |  |  |  | 2019-07-02 18:53 | PHY

## Review Required
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2357 | Mark RISON | 236 | 2 |  |  |  | T | Y | [5 empty] | Haiming Wang | 11-19/1034r2 |  | Do not introduce a separate CMMG Control. Do like everything else and have a CMMG-variant HT Control | Revert the changes to Figure 9-2. In 9.2.4.1.10 change the last bullet to "It is set to 1 in a QoS Data or Management frame transmitted by a CMMG STA to indicate that the frame contains an CMMG variant HT Control field.". In 9.2.4.6.4 and Table 9-314 and 10.32 and 10.33.4 and 10.35.5 change "CMMG Control field" and "CMMG control field" to "CMMG variant HT Control field" throughout. Delete Subclause 10.9. In 10.35.5 delete "The procedures in this subclause apply to CMMG PPDUs for which the CMMG Control field, if present, is the CMMG Control field." (gibberish) |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:00:06Z - status set to: Submission Required |  |  |  | 2019-07-04 15:17 | PHY
2041 | Assaf Kasher | 236 | 2 | 25.5.7.2.2 | 3448 | 31 | E | Y | 3448 | 31 | 25.5.7.2.2 |  |  | Assaf Kasher | 11-19/1034 |  | CCA is based on senstivity of MCS0, which is not defined in the standard. The quoted numbers fir the sensitiviy for SC MCS1. | change MCS0 to MCS1 |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:12:21Z - status set to: Submission Required PHY: 2019-02-28 21:05:36Z - status set to: Discussion EDITOR2: 2019-02-22 16:31:44Z - status set to: Discuss - Per the discussion on the February 22nd call, this CID is transferred to PHY. |  |  |  | 2019-07-04 14:28 | PHY
2042 | Assaf Kasher | 236 | 2 | 25.6.9.3.2 | 3508 | 51 | E | Y | 3508 | 51 | 25.6.9.3.2 |  |  | Assaf Kasher | 11-19/1034 |  | CCA is based on senstivity of MCS0, which is not defined in the standard. The quoted numbers fir the sensitiviy for SC MCS1. | change MCS0 to MCS1 |  | PHY | Review Required | Review | PHY: 2019-07-04 14:28:29Z - status set to: Review PHY: 2019-06-10 15:21:59Z - status set to: Discuss PHY: 2019-06-10 15:21:44Z - status set to: Insufficient Detail PHY: 2019-04-05 00:16:42Z - status set to: Discuss PHY: 2019-02-28 21:05:44Z - status set to: Discussion EDITOR2: 2019-02-22 16:32:11Z - status set to: Discuss - Per the discussion on the February 22nd call, this CID is transferred to PHY. |  |  |  | 2019-07-04 14:29 | PHY
2048 | Assaf Kasher | 236 | 2 | 25.12.1 | 3517 | 53 | T | Y | 3517 | 53 | 25.12.1 |  |  | Haiming Wang | 11-19/1034 |  | The transmit procedure ignore (Mandatory) AGC and TRN fields | Indicate that the transmission does not end at the last bit of the PSDU if AGC and TRN are appended |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:17:33Z - status set to: Submission Required |  |  |  | 2019-07-04 14:30 | PHY
2129 | Emily Qi | 236 | 2 | E.1 | 4343 | 30 | T | N | 4343 | 30 | E.1 |  |  | Peter Ecclesine | 11-19/796 |  | In Table E-6, there are empty cells for the column "Global operating class" for operating classes 11, 12, 13, 14, and 15. | Discuss and accept proposed changes for Table E-4 and Table E-6 in doc18/1431r1. |  | PHY | Review Required | Discuss | PHY: 2019-04-05 00:21:58Z - status set to: Discuss PHY: 2019-04-05 00:21:38Z - status set to: Submission Required |  |  |  | 2019-07-04 15:39 | PHY
2700 | Tomoko Adachi | 236 | 2 | E.1 | 4333 |  | T | Y | 4333 |  | E.1 |  |  | Peter Ecclesine | 11-19/796 |  | The bandwidth between 5,030 and 5,091 MHz is no longer allowed in Japan. The use ended in Nov. 30th, 2017. | Delete those operating classes where the channels are between 5,030 and 5,091 MHz from Table E-3. |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:21:09Z - status set to: Submission Required |  |  |  | 2019-07-04 15:14 | PHY
2701 | Tomoko Adachi | 236 | 2 | E.1 | 4333 |  | T | Y | 4333 |  | E.1 |  |  | Peter Ecclesine | 11-19/796 |  | In Table E-3, there are some same sets with different operating class numbers, such as 8 and 11, 17 and 20, 25 and 26. Originally, they were seperated because each of them had a different behavior limit set. But such information is gone. | Bring back the information on behavior limit set. |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:20:43Z - status set to: Submission Required |  |  |  | 2019-07-04 15:14 | PHY
2186 | John Coffey | 236 | 2 | 19.1.1 | 2949 | 10 | T | Y | 2949 | 10 | 19.1.1 |  |  | Menzo Wentink |  |  | It would be useful for several purposes to add an extra reduced-capability PHY, permitting implementers to choose a subset of PHY modes from the HR/DSSS, ERP, and HT PHYs. For some applications that have stringent constraints on complexity, such as many IoT applications, it might be useful to be able to implement a device that supports only the 1 and 2 Mbps HR/DSSS modes and the 6 Mbps ERP mode, for example (perhaps transmitting at 1 and 2 Mbps most of the time, but able to process 6 Mbps preambles). Or it might be useful to implement a device that implemented only the HR/DSSS rates, but also supported short slot time. At present, such devices would not be IEEE 802.11 compliant. An easy change to the specification would suffice to permit these variations. Interoperability should not be a problem since even a full HT device operating at long range might not be able to process PPDUs sent at any but the lowest rates, and this possibility has existed since the beginning. | Add at end of first paragraph (or as separate paragraph after the first) "In addition, a reduced capability PHY based on the HT PHY ("RC-HT") is defined in this clause." At the end of the section (line 41), add new paragraph: "The additional RC-HT PHY is defined as follows: (1) Each HT, ERP, Clause 17 OFDM, HR/DSSS and DSSS data rate and preamble type is optional for the RC-HT PHY; (2) If transmission or reception of any HR/DSSS data rate is supported by the RC-HT PHY, then transmission and reception of 1 Mb/s and 2 Mb/s shall be supported; (3) if transmission or reception of any ERP-OFDM data rate, or HT mode at 2.4 GHz, is supported by the RC-HT PHY, then transmission and reception of the ERP-OFDM 6 Mb/s mode shall be supported; (4) if transmission or reception of any Clause 17 OFDM data rate, or HT data rate at 5 GHz, is supported by the RC-HT PHY, then transmission and reception of the Clause 17 6 Mb/s mode shall be supported; (5) if 1, 2, or 6 Mb/s data rate is supported, the corresponding preamble type shall be supported; (6) preamble detect CCA shall only be required for supported preambles; (7) the minimum receiver sensitivity requirements of Clauses 15, 16, 17, 18, and 19 shall not apply; (8) the RC-HT PHY shall support transmission and reception of at least one HR/DSSS, ERP-OFDM or Clause 17 OFDM rate; (9) in all other respects the RC-HT PHY shall follow the requirements of the HT PHY. NOTE--In particular, an RC-HT STA shall signal HT capabilities during association and reassociation, and in beacons, probe requests, and probe responses." |  | PHY | Review Required | [5 empty] | 2019-07-04 14:24 | PHY
2331 | Mark RISON | 236 | 2 | 14.9.2 | 2767 | 32 | T | Y | 2767 | 32 | 14.9.2 |  |  | Kaz Sakoda | 11-19/429 |  | There is too much in common between 14.9.2 Airtime link metric and 14.9.3 High PHY rate airtime link metric | Replace everything from the second para of the referenced subclause to the end of it with "This metric is the same as the high PHY rate airtime link metric (see 14.9.3) with <italic>n</italic> set to 1." |  | PHY | Review Required | Review | PHY: 2019-07-04 14:21:59Z - status set to: Review |  |  |  | 2019-07-04 14:22 | PHY
2035 | Assaf Kasher | 236 | 2 | 25.5.6.4 | 3480 | 53 | T | Y | 3480 | 53 | 25.5.6.4 |  |  | Haiming Wang | 11-19/1034 |  | $N_{TXT}$ is not previously defined (appears first in table 25-12) | Define it! |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:15:27Z - status set to: Submission Required |  |  |  | 2019-07-04 15:10 | PHY
2335 | Mark RISON | 236 | 2 | 14.9.3 | 2768 | 45 | T | Y | 2768 | 45 | 14.9.3 |  |  | Kaz Sakoda | 11-19/429 |  | The definition of O, "Channel access overhead, which includes frame headers, training sequences, access protocol frames, etc." is too vague | Change the cited text to "Channel access overhead, which is the time from the start of the first PPDU in the TXOP to the end of the PHY header of the first PPDU in the TXOP that carries includes a QoS Data frame." |  | PHY | Review Required | Review | PHY: 2019-07-04 14:22:53Z - status set to: Review |  |  |  | 2019-07-04 14:23 | PHY
2298 | Mark Hamilton | 236 | 2 | 8.3.5.12.4 | 769 | 19 | T | Y | 769 | 19 | 8.3.5.12.4 |  |  | Menzo Wentink |  |  | PHY-CCA.indication's "Effect of receipt" says, "The effect of receipt of this primitive by the MAC is unspecified." This is of course not true, there are lots of specifications in the Standard for behavior when this indication occurs. There are more of these in the PHY SAP clause. | Replace the cited sentence with, "The MAC is notified of the change in channel state." At P760.3, replace the sentence with, "The receipt of this primitive by the MAC entity cause the MAC receive state machine to accept an octet of data." At P769.64, replace the sentence with, "The reciept of this primitive by the MAC entity causes the MAC to start the recieve state machine." |  | PHY | Review Required | [5 empty] | 2019-07-04 14:12 | PHY
2436 | Mark RISON | 236 | 2 |  |  |  | T | Y | [5 empty] | Michael Montemurro | 11-19/1136 |  | It is not clear whether Robustness of Management frames is a capability (MMPDU *can* be protected if PMF was negotiated) or a stated (PMF was negotiated and MMPDU is protected). E.g. the definition "A Management frame that is eligible for protection." suggests the former, while 4.3.8's "Enhanced cryptographic encapsulation mechanisms for robust Management frames" suggests the latter. Some places use expressions like "protected robust Management frame", which both suggests the former and provides a way to distinguish the capability ("robust") from the actuality ("protected robust") | Add "protected" before "robust Management" throughout where not already present |  | PHY | Review Required | Submission Required | PHY: 2019-07-03 14:51:40Z - status set to: Submission Required PHY: 2019-07-03 14:51:32Z - status set to: Discuss PHY: 2019-06-10 14:14:28Z - status set to: Insufficient Detail PHY: 2019-04-05 00:00:44Z - status set to: Submission Required |  |  |  | 2019-07-05 16:07 | PHY
2440 | Mark RISON | 236 | 2 | 12.7 |  |  | T | Y |  |  | 12.7 |  |  | Michael Montemurro | 11-19/1136 |  | Key Data Length can't be 0 if there is something in the Key Data field. And if you list the contents it should cover all the possible contents | Delete "Key Data Length = length of Key Data field in octets" in 12.7.6.2/3/5, "Key Data Length = length of Key Data field in octets of included RSNEs and GTK" in 12.7.6.4, "Key Data Length = Cipher-suite dependent(#1408); see Table 12-5 (Cipher suite key lengths)" in 12.7.7.2, "Key Data Length = 0" in 12.7.7.3 |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:01:23Z - status set to: Submission Required |  |  |  | 2019-07-05 16:08 | PHY
2441 | Mark RISON | 236 | 2 | E.1 | 4336 | 12 | T | Y | 4336 | 12 | E.1 |  |  | Peter Ecclesine | 11-19/796 |  | It's not clear what "E-4a->9" and similar means | Delete the rows for Operating class = 61 to 76 inclusive |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:21:22Z - status set to: Submission Required |  |  |  | 2019-07-04 15:14 | PHY
2442 | Mark RISON | 236 | 2 | E.1 |  |  | T | Y |  |  | E.1 |  |  | Peter Ecclesine | 11-19-796r1 |  | Behavior limits set should only be "Reserved" for reserved operating classes | Change "Reserved" in the Behavious limits set cell to an em dash in all the table rows in the tables in E.1 where the Channel starting frequency cell is not "Reserved" |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:01:43Z - status set to: Submission Required |  |  |  | 2019-07-03 14:57 | PHY
2498 | Mark RISON | 236 | 2 | 20.4.3.3.4 | 3072 | 54 | T | Y | 3072 | 54 | 20.4.3.3.4 |  |  | Assaf Kasher |  |  | Re CID 1024: if the coding process *does* affect the DEI field, then how is d(0) recovered from c(0)? | Change the NOTE to "NOTE---The scrambling and coding process that transforms the DMG control mode header into the bit stream c(k) does not affect the Differential Encoder Initialization field of the DMG control mode header(#1024)." |  | PHY | Review Required | Review | PHY: 2019-07-04 14:25:10Z - status set to: Review |  |  |  | 2019-07-04 14:25 | PHY
2505 | Mark RISON | 236 | 2 | 12 |  |  | T | Y |  |  | 12 |  |  | Michael Montemurro | 11-19/1136 |  | "IPN integer value" -- it can hardly be a real complex value | Delete "integer" in "integer value" throughout Clause 12 |  | PHY | Review Required | Insufficient Detail | PHY: 2019-06-10 14:15:05Z - status set to: Insufficient Detail PHY: 2019-04-05 00:02:30Z - status set to: Submission Required |  |  |  | 2019-07-05 16:09 | PHY
2509 | Mark RISON | 236 | 2 | 12 |  |  | T | Y |  |  | 12 |  |  | Michael Montemurro | 11-19/1136 |  | There are occasional references to "wrapped" keys, but it's not clear how these keys differ from keys elsewhere | In 9.4.2.47 change "wrapped IGTK" to "encrypted IGTK" and "AES-Key-wrapped IGTK" to "IGTK". In 12.6.1.1.10 change "wrapped MGTK" to "MGTK". In 9.4.2.47 change "Key Length field is" to "The Key Length field is" and "RSC field contains" to "The RSC field contains" |  | PHY | Review Required | Submission Required | PHY: 2019-06-10 15:15:28Z - status set to: Submission Required |  |  |  | 2019-07-05 16:09 | PHY
2630 | Mark RISON | 236 | 2 | E.1 | 4328 | 32 | G | Y | 4328 | 32 | E.1 |  |  | Peter Ecclesine | 11-19/796 |  | CID 1446 clarifies that an operating class defines four things. However, this is not compatible with the resolution of some previous comments related to operating classes | Review previous comments on operating classes and address those whose resolution is not compatible with the definition in E.1 |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:20:18Z - status set to: Submission Required |  |  |  | 2019-07-04 15:13 | PHY
2290 | Mark Hamilton | 236 | 2 | E.1 | 4329 | 49 | T | Y | 4329 | 49 | E.1 |  |  | Peter Ecclesine | 11-19/796 |  | In the Tables in E.1, for Operating classes in 2.4 GHz (such as 12 or 81), the fourth column is really channel width, not channel spacing. Where does it say that the 2.4 GHz channels are spaced 5 GHz apart? | Change the column heading to "Channel width". Add a column for "Channel spacing" (or "offset" or something similar), or a reference to where this information is available. |  | PHY | Review Required | Submission Required | PHY: 2019-04-05 00:20:31Z - status set to: Submission Required |  |  |  | 2019-07-04 15:13 | PHY
2334 | Mark RISON | 236 | 2 | 14.9.2 | 2767 | 32 | T | Y | 2767 | 32 | 14.9.2 |  |  | Kaz Sakoda | 11-19/429 |  | The definition of O, "Channel access overhead, which includes frame headers, training sequences, access protocol frames, etc." is too vague | Change the cited text to "Channel access overhead, which is the time from the start of the first PPDU in the TXOP to the end of the PHY header of the first PPDU in the TXOP that carries includes a QoS Data frame." |  | PHY | Review Required | Review | PHY: 2019-07-04 14:22:36Z - status set to: Review |  |  |  | 2019-07-04 14:23 | PHY