## Slide 1: TGmd Closing Report September 2019
Date: 2019-09-19
Authors:

## Slide 2: Abstract
This presentation contains the IEEE 802.11 TGmd closing report for the September 2019 session.

## Slide 3: Work Completed this week
Completed comment resolution of 723 comments received in LB236
Approved motion for Working Group Letter Ballot on P802.11REVmd D3.0 Recirculation ballot on P802.11REVmd expected to open October 14th
Plan to request EC approval for SB in November 2019
Planned teleconference: 2019-11-01 10am Eastern, 2 hours
Agenda: https://mentor.ieee.org/802.11/dcn/19/11-19-1374-08-000m-2019-september-tgmd-agenda.pptx

## Slide 4: TGmd Schedule
January 2018 – Initial WGLB
November 2018 –D2.0 WGLB Recirculation LB
May 2019 – MEC/MDR done
September 2019 – D3.0 WGLB Recirculation LB
September 2019 – Form SB Pool - Pool formation is open, closes 2019-10-11
November 2019 – D3.0 Recirculation (unchanged)
December 2019 – Initial SB D3.0
March 2020– Recirculation SB D4.0
July 2020 – WG/EC approval
Sept 2020 – RevCom/SASB approval

## Slide 5: References
PAR: https://mentor.ieee.org/802.11/dcn/17/11-17-0004-03-0000-revision-par-proposal-tgmd.doc
Approved PARs: https://standards.ieee.org/about/sba/index.html
Comment spreadsheet: https://mentor.ieee.org/802.11/dcn/18/11-18-0611-21-000m-revmd-wg-ballot-comments.xls