## Slide 1: P802.11ba Report to EC on Unconditional Approval to go to SA Ballot
Date: 2020-1-14
Authors:

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for unconditional approval to send IEEE P802.11ba D6.0 to SA Ballot.
This document was approved during the interim session of the 802.11 working group on 17 January 2020.
  Passed in the Working Group 109 yes, 0 no , 2 abstain

## Slide 3: Status Summary
The TGba Draft went through six WG Letter Ballots. Draft 2.0 was the first to achieve > 75% needed for an approved draft
The TG has resolved over 2600 comments received on drafts 1.0 to 6.0.

## Slide 4: 802.11 WG Letter Ballot Results – P802.11ba
Ballot ID | Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
237 | 03 March 2019 | Technical Letter Ballot for TGba Draft 2.0 | Technical | 329 | 282 | 86 | 26 | 7.9 | 202 | 43 | 82
241 | 18 June 2019 | First Recirculation Ballot for TGba draft 3.0 | Recirculation | 329 | 292 | 89 | 27 | 8.2 | 216 | 40 | 84
241.1 |  | LB 241 Post-Ballot vote change |  | 329 | 292 | 89 | 27 | 8.2 | 221 | 35 | 86
243 | 15 Oct. 2019 | Second Recirculation Ballot for TGba draft 4.0 | Recirculation | 329 | 297 | 90 | 24 | 7.3 | 238 | 27 | 90
243.1 |  | LB 243 Post-Ballot vote change |  | 329 | 297 | 90 | 24 | 7.3 | 239 | 26 | 90
248 | 17 Dec. 2019 | Third Recirculation Ballot for TGba draft 5.0 | Recirculation | 329 | 299 | 91 | 22 | 6.7 | 258 | 12 | 96
248.1 |  | LB 248 Post-Ballot vote change |  | 329 | 299 | 91 | 22 | 6.7 | 263 | 7 | 97
250 | 1 Feb. 2020 | Fourth Recirculation ballot for TGba draft 6.0 | Recirculation | 329 | 299 | 91 | 23 | 7 | 266 | 4 | 99

## Slide 5: 802.11 WG Letter Ballot Comments – P802.11ba
Ballot ID | Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
237 | 03 March 2019 | Technical Letter Ballot for TGba Draft 2.0 | 827 (581 T, 227 E, 19 G)
241 | 18 June 2019 | First Recirculation Ballot for TGba draft 3.0 | 418 (265 T, 144 E, 9 G)
243 | 15 Oct. 2019 | Second Recirculation Ballot for TGba draft 4.0 | 146 (100 T, 43 E, 3 G)
248 | 17 Dec. 2019 | Third Recirculation Ballot for TGba draft 5.0 | 22 (19 T, 1 E, 2 G)
250 | 1 Feb. 2020 | Third Recirculation Ballot for TGba draft 6.0 | 3 (2 T, 1 E, 0 G)
Total |  |  | 1416 (967 T, 416 E, 33 E)

## Slide 6: IEEE-SA Mandatory Editorial Coordination
Mandatory Draft Review (MDR) and Mandatory Editorial Coordination (MEC) completed in the final report doc.: IEEE 802.11-19/1765r6:
https://mentor.ieee.org/802.11/dcn/19/11-19-1765-06-0000-tgba-mdr-report.docx

## Slide 7: Unsatisfied Technical comments by commenter (No must-be-satisfied comments received in LB250)
Voter | 237 | 241 | 243 | 248 | 250 | Total
Joseph Levy (InterDigital) – Not Responded | 39 | 15 | 19 | 9 | 0 | 82
Marc Emmelmann (Koden-TI / Fraunhofer FOKUS) | 0 | 5 | 0 | 0 | 0 | 5
Mark Rison (Samsung Cambridge Solution Centre) | 0 | 0 | 1 | 0 | 0 | 1
Osama Aboulmagd (Huawei) | 3 | 0 | 2 | 0 | 0 | 5
Total | 42 | 20 | 22 | 15 | 0 | 99

## Slide 8: Unsatisfied Technical Comments in Categories (No must-be-satisfied comments received in LB250)
D2.0 (LB237)
D3.0 (LB241)
D4.0 (LB243)
D5.0 (LB248)
Row Labels | Count of Comment Group
Misc | 3
MLME | 1
Wake up operation | 6
WUR Frame Format and Processing | 1
WUR PHY FDMA and padding | 2
WUR Power Management and negotiation | 7
Grand Total | 20
Row Labels | Count of Comment Group
MAC Introduction | 1
Wake up operation | 6
WUR Frame Format and Processing | 1
WUR Power Management | 7
Grand Total | 15
Row Labels | Count of Comment Group
Annex G | 1
Architecture and Interface | 4
Channel Access | 1
Editorial | 1
Group ID | 1
M/O and feature description | 6
MAC Introduction | 1
Wake up operation | 2
WUR Beacon and synchronization | 5
WUR Capabilities element | 1
WUR Duty Cycle | 2
WUR Frame Format and Processing | 6
WUR Power Management and negotiation | 11
Grand Total | 42
Row Labels | Count of Comment Group
Channel Access | 1
Definition | 1
Misc | 1
Protected WUR Frame | 6
Reference Matlab Model | 1
Wake up operation | 2
WUR Beacon and synchronization | 1
WUR Discovery | 1
WUR Duty Cycle | 2
WUR Frame Format and Processing | 1
WUR Power Management and negotiation | 5
WUR XXX channel | 1
Grand Total | 23

## Slide 9: Unsatisfied comments (No must-be-satisfied comments received in LB250)
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during working group ballot may be found in the embedded document on the right:
  Double click on the icon to the right to open this.
Unsatisfied comments on D2.0
Unsatisfied comments on D3.0
Unsatisfied comments on D4.0
Unsatisfied comments on D5.0

## Slide 10: TGba Timeline
 | Open | Close
First SA Ballot | Feb. 8, 2020 | March 8, 2020
Second SA Ballot | April 8, 2020 | April 22, 2020
Third SA Ballot | May 15, 2020 | May 30 2020
EC to Revcom | July 2020 | 
Revcom to SB | September 2020 |