## Summary Stats
CID RESOLUTION STATUS 2020-10-07
Comment Type | Ballot Total | JAN | MAY | JUN | JUL | AUG | SEP | TOTAL Motioned | Remaining to Motion | Done - but not motioned | TODO Detail
Technical | 460 | 70 | 85 | 45 | 3 | 1 | 92 | 296 | 164 | 58 | 21 of which are not assigned
Editorial | 546 | 0 | 434 | 2 | 0 | 0 | 0 | 436 | 110 | 80 | 80 (RW - Ready) + 18-2 (reassigned Tech) + 14 (not assigned)
General | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16 of which are not assigned
TOTAL | 1022
PLAN for D3.0 | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
Proposed number of Tech CIDs | 1022 SEP: 46.8571; 1022 OCT: 93.7143; 1022 NOV: 23.4286
D3.0 R. Ballot 11/20
SUMMAY | NOT ASSIGNED | ASSIGNED | DONE | STRAWPOLLED ONLY | TODO | TODO - Strawpolls | TOTAL
Technical CIDS | 12 | 448 | 296 | 58 | 164 | 106 | 460
Editorial CIDs | 1 | 545 | 436 | 80 | 110 | 30 | 546
General CIDs | 7 | 9 | 4 | 0 | 12 | 12 | 16
Note on C15: Microsoft Office User: 18 of these are really technical and have been assigned to others.
Note on E15: Microsoft Office User: In draft and due to be strawpolled soon (straightforward editiorial - and reversible if necessary)

## CID Leaderboard
TECH CID Resolver | JAN | MAY | JUN | JUL | AUG | SEP | TOTAL Motions | Total Assigned | Total Outstanding | 17v7 outstanding | RECENT CORRECTIONS (8/25)
Christian Berger | JAN: 14; MAY: 32; SEP: 15 | 61 | 63 | 2 | 17 | CID 3011 (motioned) now correctly assigned to Christian
Ganesh Venkatesan | JAN: 36; JUL: 2 | 38 | 44 | 6 | 6 | CID 3565 (motioned) now correctly assigned to Ganesh
Assaf Kasher | 19 | 15 |  | 1 |  | 2 | 37 | 76 | 39 | 41
Dibakar Das | JAN: 0; JUN: 27; SEP: 8 | 35 | 63 | 28 | 36
Erik Lindskog | JAN: 0; SEP: 34 | 34 | 44 | 10 | 42 | 2 completed by editor which were really editorial
Nehru Bhandaru | 0 |  | 17 |  | 1 | 15 | 33 | 31 | -2 | 14 | CID 3357, 3523 were motioned but are Editorial, and not listed here.
Jonathan Segev | JAN: 0; MAY: 15; SEP: 18 | 33 | 39 | 6 | 24 | CID 3892 is now correctly assigned to JS (is motioned) NOT Qinghua
Niranjan Grandhe | JAN: 0; MAY: 23 | 23 | 24 | 1 | 1
Feng Jiang | JAN: 0; JUN: 1 | 1 | 1 | 0 | 0 | CID 3130 motioned by Ali Raissinia, CID 3271 reassigned to dibakar, CID3269 to Qinghua
Ali Rasissini | [6 empty] | 1 | 1 | 0 | 0 | bar: JAN
ChaoChun | JAN: 0 | 0 | 0 | 0 | 0
Roy Want | JAN: 0 | 0 | 0 | 0 | 0
Jerome Henry | JAN: 0 | 0 | 1 | 1 | 1
Qi Wang | JAN: 0 | 0 | 2 | 2 | 2
Yongho Seok | JAN: 0 | 0 | 14 | 14 | 14
Qinghua Li | JAN: 0 | 0 | 16 | 16 | 16
Girish Madpuwar | JAN: 0 | 0 | 20 | 20 | 20
TOTAL TECH CIDS | 70 | 85 | 45 | 3 | 1 | 92 | 296 | 439 | 143 | 234

## Motions
Action | MOTION | Ed | DOC # | AUTHORS | NOTES | #Ed CIDs | #Tech CIDs | #STRAW | CIDs
JAN
N/A | 202001-01 |  | 1898r0 |  | November Ad Hoc Minutes | 0 | 0
N/A | 202001-02 |  | 2005r0 |  | November Minutes | 0 | 0
DONE | 202001-03 |  | 121r0 | Ali Raissinia |  | 0 | 1 |  | 3130
DONE | 202001-04 |  | 118r1 | Assaf Kasher |  | 0 | 11 |  | 3079, 3080, 3208, 3081, 3210, 3082, 3089, 3090, 3091, 3092 and 3093
DONE | 202001-05 |  | 137r3 | Assaf Kasher |  | 0 | 5 |  | 3067, 3068, 3181, 3186 and 3938
DONE | 202001-06 |  | 126r2 | Ganesh Venkatesan |  | 0 | 13 |  | 3163, 3164, 3561, 3563, 3564, 3165, 3166, 3167, 3565, 3572, 3577, 3583 and 3439
DONE | 202001-07 |  | 167r1 | Assaf Kasher |  | 0 | 3 |  | 3823, 3832, 3936
DONE | 202001-08 |  | 183r1 | Ganesh Venkatesan |  | 0 | 16 |  | 3580, 3581, 3585, 3169, 3586, 3314, 3483, 3915, 3984, 3425, 3853, 3032, 3033, 3436, 3437 and 3438
N/A | 202001-09 |  |  |  | Ad hoc scheduling | 0 | 0
DONE | 202001-10 |  | 198r2 | Ganesh Venkatesan |  | 0 | 7 |  | 3440, 3441, 3490, 3034, 3035, 3231 and 3840
DONE | 202001-11 |  | 154r2 | Christian Berger |  | 0 | 14 |  | 3664, 3985, 3669, 3672, 3675, 3688, 3689, 3692, 3693, 3695, 3697, 3698, 3699 and 3470
MAY
N/A | 202005-01 |  | 140r0 | Assaf Kasher | Interim Meeting MInutes 13-17th Jan (Irvine) | 0 | 0 |  | N/A
N/A | 202005-02 |  | 249r0 | Assaf Kasher | Telecon MInutes 8th Jan | 0 | 0 |  | N/A
N/A | 202005-03 |  | 251r0 | Assaf Kasher | Telecon MInutes Jan-Feb | 0 | 0 |  | N/A
N/A | 202005-04 |  | 419r1 | Roy Want | Ad Hoc Meeting Minutes March | 0 | 0 |  | N/A
N/A | 202005-05 |  | 592r0 | Assaf Kasher | Telecon MInutes April | 0 | 0 |  | N/A
DONE | 202005-06 |  | 159r1 | Jonathan Segev |  | 0 | 9 |  | 3862, 3878, 3892, 3854, 3489, (3511), 3533, 3535, 3566 and 3592 | DBv7 assign 3892 from Qinghua to Jonathan Segev ( motioned)
DONE | 202005-07 |  | 256r1 | Jonathan Segev | Use 3511 (2nd occurrence), from this motion, as final. | 0 | 6 |  | 3829, 3511, 3630, 3708, 3709 and 3716
DONE | 202005-08 |  | 388r2 | Assaf Kasher |  | 0 | 15 |  | 3648, 3026, 3027, 3262, 3573, 3574, 3575, 3028, 3029, 3638, 3916, 3918, 4002, 3042 and 4003
DONE | 202005-09 |  | 379r1 | Niranjan Grandhe |  | 0 | 23 |  | 3722, 3727, 3728, 3730, 3731, 3732, 3733, 3735, 3738, 3739, 3908, 3255, 3256, 3257, 3258, 3742, 3743, 3745, 3746, 3467, 3259, 3747 and 3260
DONE | 202005-10 |  | 366r2 | Christian Berger |  | 0 | 13 |  | 3503, 3504, 3193, 3009, 3101, 3192, 3848, 3894, 3010, 3011, 3222, 3431 and 3710, | DBv7 assign 3011 to Christian Berger (motioned)
DONE | 202005-11 |  | 368r2 | Christian Berger | Removed 3242 as no resolution in 368r2 | 0 | 19 |  | 3115, (3242), 3719, 3701, 3702, 3906, 3703, 3705, 3706, 3707, 3711, 3712, 3685, 3686, 3713, 3657, 3714, 3715, 3247 and 3907
JUNE
DONE | 202006-01 |  | 255r1 | Nehru Bhandaru |  | 0 | 14 |  | 3517, 3514, 3515, 3522, 3406, 3519, 3407, 3408, 3536, 3409, 3414, 3833, 3448 and 3521
DONE | 202006-02 |  | 530r0 | Nehru Bhandaru |  | 0 | 3 |  | 3524, 3525 and 3526
DONE | 202006-03 |  | 607r1 | Dibakar Das |  | 0 | 6 |  | 3676, 3677, 3678, 3680, 3811 and 3126
DONE | 202006-04 | CCW | 642r0 | ChaoChun / Roy Want | Editorials x 434 | 434 | 0 |  | <CCW 434 CID Editorial Batch from January>
DONE | 202006-05 |  | 641r0 | Dibakar Das |  | 0 | 1 |  | 3679
DONE | 202006-06 |  | 707r3 | Christian Berger | New Tech Contribution | 0 | 0 |  | TECH
DONE | 202006-07 |  | 759r1 | Feng Jiang |  | 0 | 1 |  | 3129
DONE | 202006-08 |  | 759r3 | Dibakar Das |  | 0 | 2 |  | 3629 and 3271
DONE | 202006-09 |  | 788r2 | Dibakar Das |  | 0 | 18 |  | 3013, 3014, 3015, 3102, 3283, 3355, 3389, 3016, 3017, 3827, 3888, 3324, 3434, 3962, 3287, 3435, 4004 and 4005
DONE | 202006-10 |  | 806r1 | Nehru Bhandaru | Editorials -> Tech CIDS | 2 | 0 |  | 3357 and 3523 | CID 3357, 3523 are Editorial
JULY
N/A | 202007-01 |  | 1043r0 | Assaf Kasher / Roy Want | Telecon Minutes May-July | 0 | 0 |  | N/A
DONE | 202007-02 |  | 800r1 | Ganesh Vankatesan |  | 0 | 2 |  | 3232 and 3440
DONE | 202007-03 |  | 889r3 | Nehru Bhandaru | New Tech Contribution: Note r4 exists | 0 | 0 |  | TECH
DONE | 202007-04 |  | 698r2 | Assaf Kasher |  | 0 | 1 |  | 3940
AUG
N/A | 202008-01 |  | 847r0 | Assaf Kasher | Minutes Plenary Meetings May - July | 0 | 0 |  | N/A
N/A | 202008-02 |  | 1195r0 | Roy Want | Minutes Telecon July 15th | 0 | 0 |  | N/A
DONE | 202008-03 |  | 963r2 | Nehru Bhandaru |  | 0 | 1 |  | 3880
DONE | 202008-04 |  | 1106r0 | Nehru Bhandaru | New Technical Contribution | 0 | 0 |  | TECH
SEPT
DONE | 202009-01 |  | 1186r0 | Nehru Bhandaru | New Technical Contribution | 0 | 0 |  | TECH
DONE | 202009-02 |  | 1189r3 | Jonathan Segev |  | 0 | 8 |  | 3094,3095, 3212, 3941, 3618, 3762, 3764, and 3825
DONE | 202009-03 |  | 1257r1 | Jonathan Segev |  | 0 | 8 |  | 3758, 3844, 3854, 3855, 3860, 3862, 3863, and 3867
DONE | 202009-04 |  | 1143r1 | Assaf Kasher |  | 0 | 2 |  | 3510 and 3361
DONE | 202009-05 |  | 1196r2 | Jonathan Segev |  | 0 | 2 |  | 3281 and 3387
DONE | 202009-06 |  | 1208r1 | Christian Berger | New Technical Contribution | 0 | 0 |  | TECH
| 202009-07 |  | 1219r3 | Christian Berger |  | 0 | 13 |  | 3008, 3884, 3011, 3019, 3105, 3242, 3671, 3119, 4019, 3267, 3268, 3986 and 3987
| 202009-08 |  | 1225r4 | Nehru Bhandaru |  | 0 | 15 |  | 3132, 3304, 3319, 3388, 3399, 3404, 3453, 3460, 3461, 3520, 3650, 3839, 3974, 3975 and 3988
N/A | 202009-09 |  |  |  | Vice Chair affirmation |  |  |  | N/A
| 202009-10 |  | 1020r8 | Erik Lindskog |  | 0 | 8 |  | 3103, 3020, 3830, 3336, 3045, 3143, 3857 and 3337
N/A | 202009-11 |  |  |  | Timeline commit | 0 | 0 |  | N/A
| 202009-12 |  | 1487r4 | Erik Lindskog |  | 0 | 26 |  | 3858, 3307, 3052, 3053, 3874, 3558, 3554, 3555, 3556, 3655, 3654, 3659, 3800, 3801, 3808, 3165, 3166, 3890, 3891, 3308, 3309, 3547, 3548, 3789, 3790 and 3791
new | 202009-13 |  | 1308r0 | Nehru Bhandaru | New Technical Contribution | 0 | 0 |  | TECH
| 202009-14 |  | 1209r3 | Christian Berger |  | 1 | 1 |  | 3266(Ed) and 3895
| 202009-15 |  | 1394r1 | Dibakar Das |  | 0 | 8 |  | 3127, 3299, 3814, 3816, 3116, 3543, 3544, and 3537
| STRAWPOLL |  | 1392r2 | Dibakar Das |  | 0 | 0 | 16 | 3594, 3599, 3600, 3904, 3601, 3603, 3605, 3608, 3621, 3622, 3624, 3628, 3683, 3813, 3815, and 3861
| STRAWPOLL |  | 1393r1 | Dibakar Das |  | 0 | 0 | 2 | 3896, and 3999
| STRAWPOLL |  | 1410r0 | Roy Want | Editorial CIDs x 80 | 80 | 0 |  | <80 Editorials - see doc>
| STRAWPOLL |  | 1245r3 | Christian Berger |  | 0 | 0 | 1 | 3883
| STRAWPOLL |  | 1502r3 | Erik Lindskog |  | 0 | 0 | 10 | 3052, 3053, 3874, 3557, 3656, 3804, 3301, 3152, 3841, and 3310
| STRAWPOLL |  | 340r8 | Girish Madpuwar |  | 0 | 0 | 16 | 3066, 3760, 3842, 3843, 3912, 3913, 3914, 3771, 3777, 3778, 3779, 3780, 3782, 3783, 3625, and 3768
| STRAWPOLL |  | 1553r1 | Assaf Kasher |  | 0 | 0 | 13 | 3000, 3018, 3054, 3055, 3056, 3057, 3058, 3059, 3060, 3061, 3153, 3154, and 3175
| TOTAL |  |  |  |  | 517 | 295 | 58

## New + changed CID Requests
NEW | 2020-08-11 | 2020-08-13 | 2020-08-19 | 2020-08-19 | 2020-08-25 | 2020-08-26
Count | Christian Berger | Nehru Bhandaru | Jonathan Segev | Yongho Seok | Yongho Seok | Assaf Kasher
1 | 3011 | 3132 | 3106 | 3317 | 3321 | 3643
2 | 3019 | 3304 | 3108 | 3320 | 3322 | 3457
3 | 3020 | 3319 | 3214 |  | 3455
4 | 3105 | 3388 | 3276 |  | 3456
5 | 3267 | 3399 | 3282 |  | 3457
6 | 3268 | 3404 | 3411 |  | 3458
7 | 3986 | 3453 | 3412 |  | 3507
8 | 3987 | 3460 | 3424 |  | 3614
9 | 4019 | 3461 |  |  | 3615
10 |  | 3520
11 |  | 3650
12 |  | 3839
13 |  | 3974
14 |  | 3975
15 |  | 3988
CORRECT OR REASSIGN
CID | FROM | TO | STATUS
3011 | n/a | Christian Berger | Motioned
3892 | Qinghua Li | Jonathan Segev | Motioned
3271 | Feng Jiang | Dibakar Das | Motioned
3130 | Feng Jiang | Ali Raissina | Motioned
3269 | Feng Jiang | Qinghua Li | Not Motioned
3889 | Erik Lindskog | n/a | Not Motioned
3328 | Erik Lindskog | n/a | Not Motioned
3565 | N/A | Ganesh Venkatesan | Motioned 202001-06
3310, 3311 | Dibajar Das | Erik Lindskog | Not Motioned
3568, 3658 | Editor | Erik Lindskog | Not Motioned | (From prior 434 batch)