## Slide 1: TGbe (Extremely High Throughput)
TGbe had scheduled 4 conf. calls during the electronic interim
  Two Joint calls, one parallel MAC/PHY, and one MAC
  Continued presentation of PDTs and of technical submissions
    Worked towards the creation of TGbe D0.1
    Plan is to have TGbe D0.1 ready by September 30, 2020
  Confirmed TGbe officers (Vice-Chairs and Secretary)
Agenda is available in 11-20/1269r8
  Teleconference Plan is provided in the next slide
Motions List is available in 11-20/841r22

## Slide 2: Teleconference Plan
Sep 21 (Monday) – MAC/PHY 10:00-13:00 ET
Sep 23 (Wednesday) – MAC 10:00-13:00 ET
Sep 24 (Thursday) – MAC/PHY 19:00-22:00 ET
Sep 28 (Monday) – MAC/PHY 19:00-22:00 ET
Sep 30 (Wednesday) – Joint(Motions) 10:00-13:00 ET
Oct 01 (Thursday) – No Conf Call Golden Week
Oct 05 (Monday) – No Conf Call Golden Week
Oct 08 (Thursday) – MAC/PHY 19:00-22:00 ET
Oct 12 (Monday) – MAC/PHY 19:00-22:00 ET
Oct 15 (Thursday) – Joint (Motions) 10:00-13:00 ET
Oct 19 (Monday) – MAC/PHY 10:00-13:00 ET
Oct 22 (Thursday) – MAC/PHY 19:00-22:00 ET
Oct 26 (Monday) – MAC/PHY 19:00-22:00 ET
Oct 29 (Thursday) – Joint(Motions) 10:00-13:00 ET
Nov 02 (Monday) – MAC/PHY 10:00-13:00 ET
Nov 05 (Thursday) – MAC/PHY 19:00-22:00 ET

## Slide 3: Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 Letter Ballot May 2021
D2.0 LB recirculation Mar 2022
D3.0 LB recirculation Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024