## Slide 1
Date: 2020-11-12
Author:
P802.11ay Report to EC on Conditional Approval to forward draft to RevCom

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send the P802.11ay draft to RevCom.
This document (Revision 3) was approved by the 802.11 working group on 2020-11-10.
  Passed in the Working Group: 103 yes, 0 no, 11 abstain
Revision 4 adds the WG motion results and updated the status of the ballot results

## Slide 3: Standards Association (SA) Ballot Results – P802.11ay
Ballot Close Date | Title | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
Jan 9, 2020 | Initial SA ballot for P802.11ay Draft 5.0 | 137 | 113 | 82 | 2 | 1 | 99 | 12 | 89
Sept 29, 2020 | First Recirculation SA Ballot for P802.11ay Draft 6.0 | 137 | 114 | 83 | 3 | 2 | 101 | 9 | 91
Nov 2, 2020 | Post ballot vote changes to Approve* | 137 | 114 |  |  |  | 104 | 6# | 94
TBD | Second Recirculation SA Ballot for P802.11ay Draft 7.0 | 137 |  |  |  |  |  |  | 
* Yang, Sakoda, Yee
# 6 voters with valid DISAPPROVE comments; 1 voter who casted DISAPPROVE without any MBS comment – have been contacting this voter for a few comments but the voter is non-responsive

## Slide 4: SA Ballot Comments – P802.11ay
Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
Jan 9, 2020 | Initial SA ballot for P802.11ay Draft 5.0 | 135 (64 technical, 69 editorial, 2 general)
Sept 29, 2020 | First Recirculation SA Ballot for P802.11ay Draft 6.0 | 90 (52 technical, 36 editorial, 2 general)

## Slide 5: Unsatisfied comments by commenters
Voter | Initial | 1st Re | 2nd Re | Comment topic | Total
Joseph Levy (No response from the commenter) | 7 | 0 |  | Spatial multiplexing power save; ATIM frame usage for power management of non-AP STAs; definitions of DMG A-PPDU and EDMG A-PPDU; radar implementation | 7
Payam Torab | 0 | 2 |  | TDD beamforming; TDD channel access. | 2
Alecsander Eitan | 0 | 2 |  | Definition and PICS of directional transmit activity report | 2
TOTAL | 7 | 4 |  |  | 11

## Slide 6: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during the SA ballots are in the embedded document on the right:
  Double click on the icon to open the file

## Slide 7: Mandatory Coordination
Coordination Entity | Draft | Date | Status
IEEE-SA Editorial (MEC) | D3.1 | July 2019 | “Meets all editorial requirements.”
Quantities, Units and Letter Symbols (SCC14) |  |  | Not required
Terms and Definitions (SCC10) |  |  | Not required
Registration Authority Committee (RAC) |  |  | Not required

## Slide 8: P802.11ay Timeline
Milestone | Date
Report to EC for conditional approval to proceed to RevCom | November 13, 2020 or December 1, 2020
2nd Recirculation SA ballot on D7.0 | November 30, 2020
Comment response notification | December 16, 2020
Post to RevCom by | February 12, 2021