## Summary Stats
CID RESOLUTION STATUS 2021-06-029: Based on LB253 Database Snapshot 11-21/286r6
Comment Type | Ballot Total | MAR | APR | MAY | JUN | JUL | AUG | OCT | NOV | JAN | TOTAL Motioned
Technical | 256 | MAR: 63; APR: 40; MAY: 32; JUN: 3 | 138
General | 2 | [9 empty] | 0
Editorial | 218 | MAR: 10; APR: 4; MAY: 13; JUN: 9 | 36
TOTAL | 476 | MAR: 73; APR: 44; MAY: 45; JUN: 12 | 174
PLAN for D4.0 | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Goal | JUL: D4.0: Ballot by end Aug
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | MOTION DUPs | STRAW ONLY | STRAW DUPs | TODO
Technical CIDS | 33 | 223 | 138 | 118 | 0 | 42 | 1 | 77
General CIDs | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2
Editorial CIDs | 208 | 10 | 36 | 182 | 0 | 11 | 0 | 171
Includes Withdrawn CIDs as Rejects

## CID Leaderboard
TECH CID Resolver | MAR | APR | MAY | JUN | JUL | AUG | SEP | TOTAL Motions | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Nehru Bhandaru | MAR: 33; MAY: 4 | 37 | 43 | 6 | 0 | 0 | 0 | 6
Ali Rasissini | APR: 27; MAY: 3 | 30 | 31 | 1 | 0 | 0 | 0 | 1
Assaf Kasher | MAR: 15; APR: 8 | 23 | 25 | 2 | 0 | 0 | 0 | 2
Christian Berger | MAR: 15; APR: 1; MAY: 2 | 18 | 22 | 4 | 0 | 1 | 0 | 3
Youhan Kim | MAY: 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0
Dibakar Das | MAY: 9 | 9 | 34 | 25 | 0 | 17 | 0 | 8
Steve Shellhammer | MAY: 5; JUN: 1 | 6 | 6 | 0 | 0 | 0 | 0 | 0
Jonathan Segev | APR: 3 | 3 | 5 | 2 | 0 | 0 | 0 | 2
Tianyu Wu | JUN: 2 | 2 | 10 | 8 | 0 | 0 | 0 | 8
Qi Wang | [7 empty] | 0 | 7 | 7 | 0 | 0 | 0 | 7
Erik Lindskog | [7 empty] | 0 | 31 | 31 | 0 | 24 | 0 | 7
Ganesh Venkatesan | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Girish Madpuwar | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Yongho Seok | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Feng Jiang | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Qinghua Li | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Jerome Henry | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 63 | 39 | 32 | 3 | 0 | 0 | 0 | 137 | 223 | 86 | 0 | 42 | 0 | 44
[8 empty] | UNASSIGNED | 33 |  |  |  | NET TODO= | 77
[11 empty] | June & July |  | PER MTH (1) | 77

## Motions
DB Action | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | #STR Ed | #STR Gen | #STR Tech | CIDs
MAR | [14 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
N/A | 202101-01 | 2021-03-09 | 72r0 | Assaf Kasher | November Ad Hoc Minutes |  |  |  | 0 | 0 | 0 |  |  |  | TGaz January 2021 interim minutes
N/A | 202001-02 | 2021-03-09 | 1986r1 | Assaf Kasher | November Minutes |  |  |  | 0 | 0 | 0 |  |  |  | TGaz Nov 2020 - Jan 2021 minutes
| 202101-03 | 2021-03-09 | 291r4 | Nehru Bhandaru |  |  |  |  | 33 | 0 | 10 |  |  |  | 5018, 5019, 5030, 5031, 5085, 5086, 5144E, 5263, 5268, 5276, 5292E, 5299, 5300, 5301, 5302, 5303, 5304, 5305E, 5306, 5307, 5308, 5337E, 5338E, 5339E, 5340E, 5357E, 5358, 5359, 5360, 5362, 5363, 5370, 5371E, 5372E, 5374, 5394, 5398, 5401, 5403, 5445, 5453, 5455, and 5456 (43 CIDs total)
| 202001-04 | 2021-03-09 | 346r2 | Assaf Kasher |  |  |  |  | 15 | 0 | 0 |  |  |  | 5109, 5111, 5440, 5441, 5442, 5443, 5114, 5115, 5395, 5281, 5286, 5397, 5402, 5136, 5149 (15 CIDs total)
| 202101-05 | 2021-03-10 | 307r3 | Christian Berger |  |  |  |  | 4 | 0 | 0 |  |  |  | 5088, 5454, 5193, and 5175 (4 CIDs total)
| 202001-06 | 2021-03-10 | 318r2 | Christian Berger |  |  |  |  | 11 | 0 | 0 |  |  |  | 5204, 5072, 5205, 5207, 5404, 5405, 5214, 5215, 5216, 5217 and 5151 (11 CIDs total)
APR
| 202104-01 | 2021-04-29 | 478r2 | Ali Raissinia |  |  |  |  | 21 | [5 empty] | 5045, 5046, 5047, 5049, 5050, 5051, 5052, 5053, 5056, 5057, 5058, 5059, 5060, 5062, 5063, 5064, 5067, 5068, 5069, 5070,and 5071 (21 CIDs total)
| 202104-02 | 2021-04-29 | 505r1 | Ali Raissinia |  |  |  |  | 6 | [5 empty] | 5061, 5066, 5198, 5222, 5224, 5230 (6 CIDs total)
N/A | 202104-03 | 2021-04-29 | 532r0 | Dibarkar Das |  |  |  |  | 0 | [5 empty] | Technical Contribution TC532r0
| 202104-04 | 2021-04-29 | 533r2 | Johnathan Segev |  |  |  |  | 3 |  | 4 |  |  |  | 5000, 5003E, 5004E, 5005, 5006E, 5009, 5237E (7 CIDs total),
| 202104-05 | 2021-04-29 | 564r2 | Assaf Kasher |  |  |  |  | 8 | [5 empty] | 5219, 5029, 5400, 5139, 5152, 5097, 5098, 5429, 5260 (9 CIDs total)
| 202104-06 | 2021-04-29 | 519r3 | Christian Berger |  |  |  |  | 1 | [5 empty] | 5014 (1 CIDs total)
MAY
| 202105-01 | 2021-05-10 | 422r0 | Assaf Kasher | [10 empty] | TGaz meeting minutes Feb-Apr 2021
| 202105-02 | 2021-05-10 | 777r0 | Assaf Kasher | [10 empty] | TGaz Telecon meinutes Feb-Apr 2021
| 202105-03 | 2021-05-10 | 708r0 | Nehru Bhandaru |  |  |  |  | 4 | [5 empty] | 5260, 5351, 5364, 5385 (4 CIDs total)
| 202105-04 | 2021-05-10 | 536r1 | Steve Shellhammer |  |  |  |  | 5 | [5 empty] | 5413, 5414, 5415, 5416 and 5417 (5 CIDs total)
| 202105-05 | 2021-05-12 | 761r3 | Christian Berger |  |  |  |  | 2 | [5 empty] | 5190 and 5191 (2 CIDs total)
| 202105-06 | 2021-05-12 | 811r1 | Youhan Kim |  |  |  |  | 9 | [5 empty] | 5473, 5460, 5461, 5463, 5467, 5468, 5474, 5469, 5471 (9 CIDs total)
N/A | 202105-07 | 2021-05-17 | 750r2 | Jon Rosdahl | [10 empty] | PAR Extension
| 202105-08 | 2021-05-17 | 810r2 | Ali Raissinia |  |  |  |  | 3 | [5 empty] | 5016, 5027 and 5036 (3 CIDs total)
| 202105-09 | 2021-05-17 | 815r1 | Dibarkar Das |  |  |  |  | 9 |  | 4 |  |  |  | 5007, 5008, 5010E, 5037, 5041, 5048E, 5132, 5141E, 5162E, 5164, 5165, 5167, 5168 (13 CIDs total)
JUNE
| SP | 2021-06-21 | 928r1 | Erik Lindskog |  | 11 |  | 6 | [6 empty] | 5235E, 5252E, 5253E, 5020, 5021, 5026, 5032, 5033E, 5367E, 5391, 5034, 5035, 5043, 5073, 5074, 5076, 5242E (17 CIDs)
| SP | 2021-06-16 | 978r1 | Erik Lindskog |  | 9 |  | 5 | [6 empty] | 5077, 5243E, 5078, 5246E, 5075, 5244E, 5245E, 5079, 5080, 5083, 5084, 5082, 5081 and 5143E (14 CIDs)
| SP | 2021-06-23 | 967r2 | Dibarkar Das |  | 17 | [8 empty] | 5451, 5450, 5449, 5428, 5427, 5396, 5393, 5234, 5218, 5194, 5180, 5172, 5171, 5170, 5169, 5135 and 5042 (17 CIDs).
| 202106-01 | 2021-06-24 | 835r2 | Jonathan Segev | [6 empty] | 9 |  |  |  | 5203E, 5254E, 5261E, 5294E, 5348E, 5353E, 5378E, 5381E, 5444E (9 CIDs total)
N/A | 202106-02 | 2021-06-24 | 864r1 | Steve Shellhammer |  |  |  |  | 1 | [5 empty] | 5090 (1 CIDs total)
| 202106-03 | 2021-06-24 | 901r0 | Christian Berger | [10 empty] | Technical Contribution
| 202106-04 | 2021-06-24 | 917r0 | Tianyu Wu |  |  |  |  | 2 | [5 empty] | 5189, 5192 (2 CIDs)
| SP | 2021-06-24 | 911r2 | Christian Berger |  | 1 | [8 empty] | 5377 (1 CID)
| SP | 2021-06-24 | 929r2 | Erik Lindskog |  | 4 | [8 empty] | 5220, 5221, 5223, and 5028 (4 CIDs)
N/A | SP | 2021-06-24 | 968r0 | Youhan Kim | [10 empty] | Technical Contribution
JULY
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
| TOTAL |  |  |  |  | 42 | 0 | 11 | 137 | 0 | 27 | 0 | 0 | 0
20
14

## ToDo Per Member
TODO
TECH CIDs | Nehru Bandharu | Ali Raissinia | Youham Kim | Assaf Kasher | Christian Berger | Jonathan Segev | Steve Shellhammer | Qi Wang | Tianyu Wu | Erik Lindskog | Dibakar Das | UNASSIGNED
Complete | 37/43 | 30/31 | 9/9 | 24/25 | 19/20 | 3/5 | 6/6 | 0/7 | 2/12 | 24/32 | 26/34 | 0/33
ToDo #1 | 5093 | 5044 |  | 5138 | 5213 | 5206 |  | 5424 | 5001 | 5055 | 5011
ToDo #2 | 5095 |  |  |  |  | 5208 |  | 5425 | 5002 | 5232 | 5039
ToDo #3 | 5181 | [6 empty] | 5435 | 5103 | 5233 | 5040
ToDo #4 | 5187 | [6 empty] | 5437 | 5106 | 5235 | 5174
ToDo #5 | 5228 | [6 empty] | 5447 | 5160 | 5255 | 5195
ToDo #6 | 5439 | [6 empty] | 5452 | 5423 | 5256 | 5196
ToDo #7 | [7 empty] | 5457 | 5432 | 5257 | 5229
ToDo #8 | [8 empty] | 5433 | 5258 | 5271
ToDo #9 | [8 empty] | 5434
ToDo #10 | [8 empty] | 5436
ToDo #11
ToDo #12
ToDo #13
ToDo #14
ToDo #15
ToDo #16
ToDo #17
ToDo #18
ToDo #19
ToDo #20
ToDo #21
ToDo #22
ToDo #23
ToDo #24
ToDo #25
ToDo #26
ToDo #27
ToDo #28
ToDo #29
ToDo #30
ToDo #31
ToDo #32
ToDo #33
ToDo #34
ToDo #35