## Slide 1: TGbh Closing Report
Date: 2021-05-16
Authors:

## Slide 2: Abstract
This document is the closing report for TGbh
“Randomized and Changing MAC addresses” (RCM)
May 2021 Interim Session (virtual)

## Slide 3: Work Completed
Agenda is here: 11-21/0610r5
Noted press release/blog for TGbh and TGbi: 11-21/0760r1
Noted liaison from WBA (planned response in July)
Reviewed contributions:
  Parental controls use case: 11-21/0804r2
  Agreed to include use case in the tracking document, even if we agree to make/propose no text changes to 802.11 for the use case, for the sake of tracking our work.
Continued working through other items in tracking document: 11-21/0332r7

## Slide 4: Timeline
  PAR approved Feb 2021
  First TG meeting Mar 2021
  D0.1 Nov 2021
  Initial Letter Ballot (D1.0) Mar 2022
  Recirculation LB (D2.0) Jul 2022
  Initial SA Ballot (D3.0) Nov 2022
  Final 802.11 WG approval Mar 2023
  802 EC approval May 2023
  RevCom and SASB approval May 2023

## Slide 5: Teleconference(s)
Monday June 14, 13:00 ET, 2 hours
Monday June 28, 13:00 ET, 2 hours

## Slide 6: July 2021 Plans
Three meeting slots planned
Review/respond to WBA liaison
Continue gathering/reviewing Use Cases and Impacts of RCM
Consider “solutions” to use cases that are in 802.11 scope to resolve