## Summary Stats
CID RESOLUTION STATUS 2021-03-02: Based on SA1 Database Snapshot 11-22/84r2
Comment Type | Ballot Total | NOV | DEC | JAN | FEB | MAR | APR | TOTAL Motioned | PERCENTAGE
Technical | 166 | 13 | 0 | 55 | 27 | 2 |  | 97 | 58.4337
General | 6 | JAN: 3; FEB: 0 | 3 | 50
Editorial | 192 | FEB: 0; MAR: 100 | 100 | 52.0833
TOTAL | 364 | 13 | 0 | 58 | 27 |  |  | 200
PLAN for D4.0 | JUL | AUG | SEP | OCT | NOV | DEC | JAN
Goal | JUL: D5.0: Ballot out of May 2022 meeting
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | TODO
Technical CIDS | 105 | 61 | 97 | 69 | 69
General CIDs | 0 | 6 | 3 | 3 | 3
Editorial CIDs | 0 | 192 | 100 | 92 | 92
Includes Withdrawn CIDs as Rejects

## CID Leaderboard
TECH or GEB CID Resolver | NOV | DEC | JAN | FEB | MAR | APR | MAY | TOTAL Motions | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Christian Berger | NOV: 13; JAN: 16; FEB: 6; MAR: 2 | 37 | 38 | 1 | 0 | 0 | 0 | 1
Assaf Kasher | JAN: 14; FEB: 10 | 24 | 24 | 0 | 0 | 0 | 0 | 0
Jonathan Segev | JAN: 13; FEB: 10 | 23 | 23 | 0 | 0 | 0 | 0 | 0
Nehru Bhandaru | JAN: 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Ali Rasissini | JAN: 7; FEB: 1 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Qi Wang | [7 empty] | 0 | 2 | 2 | 0 | 0 | 0 | 2
Tianyu Wu | [7 empty] | 0 | 6 | 6 | 0 | 0 | 0 | 6
Erik Lindskog | [7 empty] | 0 | 7 | 7 | 0 | 0 | 0 | 7
Dibakar Das | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Youhan Kim | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Steve Shellhammer | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Ganesh Venkatesan | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Girish Madpuwar | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Yongho Seok | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Feng Jiang | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Qinghua Li | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Jerome Henry | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 13 | 0 | 58 | 27 | 2 | 0 | 0 | 100 | 116 | 16 | 0 | 0 | 0 | 16
[8 empty] | UNASSIGNED | 56 |  |  |  | NET TODO= | 72
Negative likely indicates a duplicate resolution

## Motions
DB Action | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | CIDs/Text
NOV | [11 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
NA | 202101-01/03 | 2021-11-09 |  | Assaf Kasher | November Ad Hoc Minutes |  |  |  | 0 | 0 | 0 | Minutes
| 202111-04 | 2022-11-11 | 1842r1 | Christian Berger |  |  |  |  | 6 | 0 | 0 | 7291, 7292, 7328, 7329, 7331, 7357 [6 CIDs]
| 202111-05 | 2022-11-11 | 1843r1 | Christian Berger |  |  |  |  | 4 | 0 | 0 | 7025, 7318, 7355, 7356 [4 CIDs]
TC | 202111-06 | 2022-11-15 | 1580r5 | Nehru Bhandaru | [7 empty] | Technical Contribution (TC)
| 202111-07 | 2022-11-15 | 1837r1 | Jonathan Segev | [7 empty] | WFA RE Text
| 202111-08 | 2022-11-15 | 1875r1 | Christian Berger |  |  |  |  | 3 | 0 | 0 | 7338, 7337, 7339 [3 CIDs]
DEC/JAN
| 202201-01 | 2022-01-05 | 1944r2 | Ali Raissinia |  |  |  |  | 7 | 0 | 0 | 7152, 7153, 7156, 7157, 7158, 7160, 7161 [7 CIDs]
| 202201-02 | 2022-01-06 | 1979r2 | Nehru Bhandaru |  |  |  |  | 8 | 0 | 0 | 7316, 7290, 7240, 7239, 7159, 7149, 7039, 7018 [8 CIDs]
| 202201-03 | 2022-01-06 | 1841r5 | Christian Berger |  |  |  |  | 16 | 0 | 0 | 7049, 7026, 7032, 7033, 7048, 7050, 7053, 7282, 7283, 7344, 7345, 7346, 7347, 7348, 7349, 7352
NA | 202201-04 | 2022-01-17 | 1833r0 | Assaf Kasher | [7 empty] | Minutes
NA | 202201-05 | 2022-01-17 | 1834r0 | Assaf Kasher | [7 empty] | Minutes
NA | 202201-06 | 2022-01-18 | 87r1 | Assaf Kasher | [7 empty] | Minutes
| 202201-07 | 2022-01-20 | 128r1 | Jonathan Segev |  |  |  |  | 6 | 2 | 0 | 7005G, 7016G, 7017, 7019, 7020, 7034, 7040, 7043 ( 8 CIDs total)
| 202201-08 | 2022-01-24 | 168r1 | Jonathan Segev |  |  |  |  | 5 | 0 | 0 | 7047, 7056, 7065, 7072, 7076 (5 CIDs total)
| 202201-09 | 2022-01-24 | 131r2 | Shulinh Feng (Julia) | [7 empty] | Technical Contribution/Clarification
| 202201-10 | 2022-01-24 | 156r1 | Assaf Kasher |  |  |  |  | 13 | 1 | 0 | 7367, 7368, 7369, 7370, 7371, 7372, 7373, 7251, 7301G, 7105, 7078, 7080, 7094, 7095 (14 CIDs total)
FEB | 202202-01 | 2022-02-03 | 149r1 | Christian Berger |  |  |  |  | 3 | 0 | 0 | 7052, 7279 and 7281 (total of 3)
| 202202-02 | 2022-02-09 | 259r1 | Assaf Kasher |  |  |  |  | 10 | 0 | 0 | 7097, 7101 ,7102, 7107, 7108, 7109, 7112, 7119, 7120 and 7121 (total of 10)
| 202202-03 | 2022-02-09 | 148r2 | Christian Berger |  |  |  |  | 2 | 0 | 0 | 7075 and 7087 (total of 2)
| 202202-04 | 2022-02-09 | 265r1 | Christian Berger |  |  |  |  | 1 | 0 | 0 | 7077 (total of 1)
| 202202-05 | 2022-02-09 | 297r0 | Ali Raissinia |  |  |  |  | 1 | 0 | 0 | 7036 (total of 1)
| 202202-06 | 2022-02-23 | 366r1 | Jonathan Segev |  |  |  |  | 10 | 0 | 0 | 7079, 7081, 7084, 7085, 7088, 7089, 7090, 7091, 7092, 7093 (total of 10)
MAR | 202203-01 | 2022-03-02 | 368r0 | Roy Want |  |  |  |  | 0 | 0 | 100 | <see 368r0>
| 202203-02 | 2022-03-02 | 357r0 | Christian Berger |  |  |  |  | 2 | 0 | 0 | 7082, 7083 (total of 2)
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
| TOTAL |  |  |  |  | 0 | 0 | 0 | 97 | 3 | 100
20
14

## ToDo Per Member
TODO
NAME | TOTAL | TECH CIDS
GRAND TOTAL
NOTE: This tab will be filled out closer to the end when we are counting down to re-enter SA recirculation ballot