## Summary Stats
CID RESOLUTION STATUS 2021-04-19: Based on SA1 Database Snapshot 11-22/84r4
Comment Type | Ballot Total | NOV | DEC | JAN | FEB | MAR | APR | TOTAL Motioned | PERCENTAGE
Technical | 166 | 13 | 0 | 53 | 27 | 46 | 9 | 148 | 89.1566
General | 6 | JAN: 3; FEB: 0; MAR: 1 | 4 | 66.6667
Editorial | 192 | FEB: 0; MAR: 101 | 101 | 52.6042
TOTAL | 364 | 13 | 0 | 56 | 27 | 148 |  | 253
PLAN for D4.0 | JUL | AUG | SEP | OCT | NOV | DEC | JAN
Goal | JUL: D5.0: Ballot out of May 2022 meeting
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | TODO
Technical CIDS | 2 | 164 | 148 | 18 | 18
General CIDs | 1 | 5 | 4 | 2 | 2
Editorial CIDs | 0 | 192 | 101 | 91 | 91
Includes Withdrawn CIDs as Rejects

## CID Leaderboard
TECH CID Resolver | NOV | DEC | JAN | FEB | MAR | APR | MAY | TOTAL Motions | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Assaf Kasher | JAN: 11; FEB: 10; MAR: 20; APR: 5 | 46 | 47 | 1 | 0 | 0 | 0 | 1
Christian Berger | 13 |  | 16 | 6 | 3 | 1 |  | 39 | 40 | 1 | 0 | 0 | 0 | 1
Jonathan Segev | JAN: 11; FEB: 10; MAR: 15 | 36 | 38 | 2 | 0 | 0 | 0 | 2
Ali Raissinia | JAN: 7; FEB: 1; MAR: 1; APR: 3 | 12 | 12 | 0 | 0 | 0 | 0 | 0
Nehru Bhandaru | JAN: 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Erik Lindskog | MAR: 5 | 5 | 6 | 1 | 0 | 0 | 0 | 1
Qi Wang | MAR: 2 | 2 | 9 | 7 | 0 | 0 | 0 | 7
Tianyu Wu | [7 empty] | 0 | 4 | 4 | 0 | 0 | 0 | 4
Dibakar Das | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Youhan Kim | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Steve Shellhammer | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Ganesh Venkatesan | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Girish Madpuwar | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Yongho Seok | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Feng Jiang | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Qinghua Li | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Jerome Henry | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 13 | 0 | 53 | 27 | 46 | 9 | 0 | 148 | 164 | 16 | 0 | 0 | 0 | 16
[8 empty] | UNASSIGNED | 2 |  |  |  | NET TODO= | 18
Negative likely indicates a duplicate resolution

## Motions
DB Action | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | CIDs/Text
NOV | [11 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
NA | 202101-01/03 | 2021-11-09 |  | Assaf Kasher | November Ad Hoc Minutes |  |  |  | 0 | 0 | 0 | Minutes
| 202111-04 | 2022-11-11 | 1842r1 | Christian Berger |  |  |  |  | 6 | 0 | 0 | 7291, 7292, 7328, 7329, 7331, 7357 [6 CIDs]
| 202111-05 | 2022-11-11 | 1843r1 | Christian Berger |  |  |  |  | 4 | 0 | 0 | 7025, 7318, 7355, 7356 [4 CIDs]
TC | 202111-06 | 2022-11-15 | 1580r5 | Nehru Bhandaru | [7 empty] | Technical Contribution (TC)
| 202111-07 | 2022-11-15 | 1837r1 | Jonathan Segev | [7 empty] | WFA RE Text
| 202111-08 | 2022-11-15 | 1875r1 | Christian Berger |  |  |  |  | 3 | 0 | 0 | 7338, 7337, 7339 [3 CIDs]
DEC/JAN
| 202201-01 | 2022-01-05 | 1944r2 | Ali Raissinia |  |  |  |  | 7 | 0 | 0 | 7152, 7153, 7156, 7157, 7158, 7160, 7161 [7 CIDs]
| 202201-02 | 2022-01-06 | 1979r2 | Nehru Bhandaru |  |  |  |  | 8 | 0 | 0 | 7316, 7290, 7240, 7239, 7159, 7149, 7039, 7018 [8 CIDs]
| 202201-03 | 2022-01-06 | 1841r5 | Christian Berger |  |  |  |  | 16 | 0 | 0 | 7049, 7026, 7032, 7033, 7048, 7050, 7053, 7282, 7283, 7344, 7345, 7346, 7347, 7348, 7349, 7352 (16 CIDS)
NA | 202201-04 | 2022-01-17 | 1833r0 | Assaf Kasher | [7 empty] | Minutes
NA | 202201-05 | 2022-01-17 | 1834r0 | Assaf Kasher | [7 empty] | Minutes
NA | 202201-06 | 2022-01-18 | 87r1 | Assaf Kasher | [7 empty] | Minutes
| 202201-07 | 2022-01-20 | 128r1 | Jonathan Segev |  |  |  |  | 6 | 2 | 0 | 7005G, 7016G, 7017, 7019, 7020, 7034, 7040, 7043 ( 8 CIDs total)
| 202201-08 | 2022-01-24 | 168r1 | Jonathan Segev |  |  |  |  | 5 | 0 | 0 | 7047, 7056, 7065, 7072, 7076 (5 CIDs total)
| 202201-09 | 2022-01-24 | 131r2 | Shulinh Feng (Julia) | [7 empty] | Technical Contribution/Clarification
| 202201-10 | 2022-01-24 | 156r1 | Assaf Kasher |  |  |  |  | 11 | 1 | 0 | 7367, 7368, 7369, 7370, 7371, 7372, 7373, 7251, 7301G, 7105, 7078, 7080, 7094, 7095 (14 CIDs total)
FEB | 202202-01 | 2022-02-03 | 149r1 | Christian Berger |  |  |  |  | 3 | 0 | 0 | 7052, 7279 and 7281 (total of 3)
| 202202-02 | 2022-02-09 | 259r1 | Assaf Kasher |  |  |  |  | 10 | 0 | 0 | 7097, 7101 ,7102, 7107, 7108, 7109, 7112, 7119, 7120 and 7121 (Total of 10)
| 202202-03 | 2022-02-09 | 148r2 | Christian Berger |  |  |  |  | 2 | 0 | 0 | 7075 and 7087 (Total of 2)
| 202202-04 | 2022-02-09 | 265r1 | Christian Berger |  |  |  |  | 1 | 0 | 0 | 7077 (Total of 1)
| 202202-05 | 2022-02-09 | 297r0 | Ali Raissinia |  |  |  |  | 1 | 0 | 0 | 7036 (Total of 1)
| 202202-06 | 2022-02-23 | 366r1 | Jonathan Segev |  |  |  |  | 10 | 0 | 0 | 7079, 7081, 7084, 7085, 7088, 7089, 7090, 7091, 7092, 7093 (total of 10)
MAR | 202203-01 | 2022-03-02 | 368r0 | Roy Want |  |  |  |  | 0 | 0 | 99 | <see 368r0> includes 7098E also resolved later
| 202203-02 | 2022-03-02 | 357r0 | Christian Berger |  |  |  |  | 2 | 0 | 0 | 7082, 7083 (Total of 2)
NA | 202203-03 | 2022-03-07 | 103r2 | Assaf Kasher | [7 empty] | Minutes
NA | 202203-04 | 2022-03-07 | 403r0 | Assaf Kasher | [7 empty] | Minutes
NA | 202203-05 | 2022-03-07 | 224r0 | Peter Yee | [7 empty] | Tgaz NGP ISO/IEC JTC1/SC6
| 202203-06 | 2022-03-07 | 402r3 | Assaf Kasher |  |  |  |  | 7 | 0 | 0 | 7114, 7213, 7214, 7130, 7162, 7170, 7177 (Total of 7)
| 202203-07 | 2022-03-08 | 400r2 | Assaf Kasher |  |  |  |  | 3 | 0 | 1 | 7094, 7096, 7098E, 7099 (Total of 4)
| 202203-08 | 2022-03-09 | 437r2 | Erik Lindskog |  |  |  |  | 5 | 0 | 1 | 7031, 7035, 7042E, 7257, 7261, and 7262 (Total of 6)
| 202203-09 | 2022-03-10 | 451r3 | Christian Berger |  |  |  |  | 1 | 0 | 0 | 7095 (Total of 1)
| 202203-10 | 2022-03-10 | 471r2 | Jonathan Segev |  |  |  |  | 15 | 0 | 0 | 7123, 7131, 7134, 7138, 7139, 7172, 7181, 7182, 7185, 7186, 7187, 7195, 7196, 7191, 7219, 7223 (Total of 16)
| 202203-11 | 2022-03-17 | 471r3 | Assaf Kasher |  |  |  |  | 1 | 0 | 0 | 7222 (replaces resolution for 7223)
| 202203-12 | 2022-03-17 | 503r1 | Assaf Kasher |  |  |  |  | 9 | 1 | 0 | 7003G, 7062, 7224, 7225, 7226, 7302, 7229, 7243, 7258 and 7275 (10 CIDs total)
| 202203-13 | 2022-03-23 | 505r0 | Ali Raissinia |  |  |  |  | 1 | 0 | 0 | 7146 (1 CID)
| 202203-14 | 2022-03-30 | 489r3 | Qi Wang |  |  |  |  | 2 | 0 | 0 | 7122, 7126 (2 CIDs)
| 202204-01 | 2022-04-06 | 598r1 | Assaf Kasher |  |  |  |  | 5 | 0 | 0 | 7223, 7314, 7363, 7364, 7351 (5 CIDs)
| 202204-02 | 2022-04-13 | 572r1 | Christian Berger |  |  |  |  | 1 | 0 | 0 | 7264 (1 CID)
| 202204-03 | 2022-04-13 | 624r1 | Ali Raissinia |  |  |  |  | 3 | 0 | 0 | 7310, 7317 and 7322 (3 CIDs total)
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
| TOTAL |  |  |  |  | 0 | 0 | 0 | 148 | 4 | 101
20
14

## ToDo Itemized
TECH/GENERAL CIDS TODO
| UNASSIGNED TECH | Ali Raissinia | Qi Wang | Tianyu Wu | Erik Lindskog | Assaf Kasher | Christian Berger | Jonatha Segev |  | GENERAL
| 7300 |  | 7204 | 7209 | 7254 | 7343 | 7336 | 7227 |  | 7294G (Assigned JS)
| 7353 |  | 7205 | 7211 |  |  | 7296 | 7293 |  | 7295G (Unassigned)
|  |  | 7284 | 7212
|  |  | 7285 | 7217
7286
7288
TOTAL | 2 | 0 | 6 | 4 | 1 | 1 | 2 | 2 | TOTAL | 2
TODO | [8 empty] | TODO
GRAND TOTAL | [8 empty] | GRAND TOTAL
TECH CIDS | 18 | [7 empty] | GENERAL CIDS | 2