## Slide 1: TGbe May 2022 Closing Report
Date: 2022-05-04
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 7 conf. calls during the May electronic interim
  Four Joint calls, and three parallel MAC/PHY calls
    Covered comment resolution documents and some proposed draft texts (PDTs)
      All WG CC36 comments are now resolved
  Instructed the editor to generate IEEE802.11 TGbe D2.0
    TGbe D2.0 is expected to be available by end of May’22
  Approved a 35-day WG LB on IEEE 802.11be D2.0
  Amended the TGbe timeline and re-affirmed TGbe vice chairs and secretary
  Approved a TGbe ad-hoc meeting for Sept 07-09’22
Agenda is available in 11-22/595r16, with queues available in 11-22/428r30
  Future Teleconference Plan is provided in the next slide
Motions List is available in 1982r78
Goals for July:
  Complete comment assignments for WG LB comments and resolve comments
Distribution of ~4350 CIDs
9%
67%
24%
Resolution Status

## Slide 3: Teleconference Plan
June 16 Thursday – MAC 10:00-12:00 ET
June 20 Monday – MAC/PHY 19:00-21:00 ET
June 22 Wednesday – Joint ** 10:00-12:00 ET
June 23 Thursday – MAC 10:00-12:00 ET
June 27 Monday – MAC/PHY 19:00-21:00 ET
June 29 Wednesday – Joint (Motions) 10:00-12:00 ET
June 30 Thursday – MAC 10:00-12:00 ET
July 04 Monday – No Conf Call Holiday
July 06 Wednesday – Joint ** 10:00-12:00 ET
July 07 Thursday – MAC 10:00-12:00 ET
** Can be modified to MAC/PHY on the fly with pre-announcement.
May 18 Wednesday – No Conf Call Holiday
May 19 Thursday – No Conf Call Holiday
May 23 Monday – MAC/PHY 19:00-21:00 ET
May 25 Wednesday – Joint** 10:00-12:00 ET
May 26 Thursday – MAC 10:00-12:00 ET
May 30 Monday – No Conf Call Holiday
June 01 Wednesday – Joint ** 10:00-12:00 ET
June 02 Thursday – MAC 10:00-12:00 ET
June 06 Monday – MAC/PHY 19:00-21:00 ET
June 08 Wednesday – Joint (Motions) 10:00-12:00 ET
June 09 Thursday – MAC 10:00-12:00 ET
June 13 Monday – MAC/PHY 19:00-21:00 ET
June 15 Wednesday – Joint ** 10:00-12:00 ET

## Slide 4: Amended TGbe Timeline And Status
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Letter Ballot Mar May 2022
D3.0 Letter Ballot Nov 2022
Initial SA Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024