## Slide 1: TGbe July 2022 Closing Report
Date: 2022-07-14
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 10 sessions during the July plenary
  Five Joint calls, and five parallel MAC/PHY calls
    Discussed comment resolution documents and a couple of technical submissions
      Around 510 comments from LB266 were resolved (~12% of total, see figure for more details)
  Instructed the editor to generate IEEE802.11 TGbe D2.1
    TGbe D2.1 is expected to be available by end of July’22
  Appointed TGbe secretary
Agenda is available in 11-22/862r12
  Future Teleconference Plan is provided in the next slide
Motions List is available in 1038r4
Goals for September:
  Hold a MAC ad-hoc meeting in San Diego, CA (7-9 September)
  Continue comment resolutions for LB266 and TGbe CA document
CID Distribution (~4120)
16%
73%
11%
PHY
MAC
JOINT

## Slide 3: Teleconference Plan
July 18-22 (Mon-Fri) - No Conf Calls Holiday
July 27 (Wednesday) – Joint 10:00-12:00 ET
July 28 (Thursday) – MAC 10:00-12:00 ET
Aug 01 (Monday) – MAC/PHY 19:00-21:00 ET
Aug 03 (Wednesday) – MAC 10:00-12:00 ET
Aug 10 (Wednesday) – Joint (Motions) 10:00-12:00 ET
Aug 11 (Thursday) – MAC 10:00-12:00 ET
Aug 15 (Monday) – MAC/PHY 19:00-21:00 ET
Aug 17 (Wednesday) – MAC 10:00-12:00 ET
Aug 24 (Wednesday) – Joint (Motions) 10:00-12:00 ET
Aug 25 (Thursday) – MAC 10:00-12:00 ET
Aug 29 (Monday) – MAC/PHY 19:00-21:00 ET
Aug 31 (Wednesday) – MAC 10:00-12:00 ET

## Slide 4: TGbe Timeline And Status
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Letter Ballot May 2022
D3.0 Letter Ballot Nov 2022
Initial SA Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024