## Slide 1: TGbc Closing Report
Date: 2022-07-13
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for July 2022.

## Slide 3: Meeting Goals & Accomplishments of the week
Goal for the week:
Resolve all remaining comments
Approve MDR report
Approve creation of D4.0 and to for WG Recirculation ballot
Accomplishments
Group met 2 times this week
Resolved all
Reviewed MDR and approved resulting changes to the TGbc draft
Interaction with voters having a “standing no-vote” to identify unsatisfied comment resolutions and to identify potential further changes to the draft to satisfy the commenter wrt. to all of the submitted comments
Motion to request WG to start Recirculation Ballot on D4.0
Timeline approved

## Slide 4: TGbc schedule (revised)
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
September 2021 D2.0 WG Recirculation LB
March 2022 D3.0 WG Recirculation LB
May intermediate version D3.1
Editorial reviews: MEC & MDR on D3.1
June Form SAB Pool
July 2022 D4.0 WG Recirculation LB
EC Request for conditional approval
Jul -- Sep 2022 D4.0-unchanged WG Recirculation LB (if required)
Sep 2022 D5.0; potentially unchanged
Oct 2022 EC telco EC approval to go to SA Ballot (conditional or unconditional)
August Initial SAB (D4.0)
October Initial SAB (D5.0)
January 2023 Recirculation SAB
July 2023 EC approval to RevCom
July 2023 RevCom/SASB approval

## Slide 5: Motion for WG (Recirculation ballot)
Move to request the 802.11 WG to approve the following motion:
Having approved comment resolutions for all of the comments received from LB 264 on TGbc D3.0 as contained in document 11-22/0686r16,
Instruct the editor to prepare Draft D4.0 incorporating these resolutions and additional changes to the draft as motioned per 11-18/2123r60,
Approve a 10 day Working Group Recirculation Ballot asking the question “Should TGbc D4.0 be forwarded to SA Ballot?”
In TG:
Mover / Second: Stephen McCann / Abhishek Patil
Y/N/A: 9/0/0

## Slide 6: Plans for Next Meeting & Upcoming Telcos
Telcos
Discuss feedback from voters having a ”standing no-vote”
Work on comment resolutions for comments received from D4.0 Recirc Ballot
Upcoming meeting
Comment resolution for comments on D4.0
Preparation for EC approval for SA Ballot
Weekly Telcos
Tuesdays, 10:00h – 11.00h ET (1 hours)

## Slide 7: References
Agenda for this week: 11-22/0863
Meeting / Chair’s Slide Deck: 11-22/0864
Meeting minutes: 11-22/0774
Snapshot Slide: 11-22/0865
Closing report: 11-22/0866
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268