## Summary Stats
CID RESOLUTION STATUS 2022-06-29: Last SA1-8000+ Database Snapshot 11-22/898r0
Comment Type | Ballot Total | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL Motioned | PERCENTAGE
Technical | 36 | [7 empty] | 0 | 0
General | 2 | [7 empty] | 0 | 0
Editorial | 27 | [7 empty] | 0 | 0
TOTAL | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLAN | JUL | AUG | SEP | OCT | NOV | DEC | JAN
Goal | JUL: D6.0: Ballot out of SEP 2022 meeting
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | TODO
Technical CIDS | JUL: 3; AUG: 35; NOV: 0
General CIDs | AUG: 2; NOV: 0
Editorial CIDs | AUG: 27; NOV: 0
Includes Withdrawn CIDs as Rejects

## CID Leaderboard
TECH CID Resolver | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL Motions | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Assaf Kasher | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Christian Berger | [7 empty] | 0 | 7 | 7 | 0 | 0 | 0 | 7
Jonathan Segev | [7 empty] | 0 | 1 | 1 | 0 | 0 | 0 | 1
Ali Raissinia | [7 empty] | 0 | 3 | 3 | 0 | 0 | 0 | 3
Nehru Bhandaru | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Erik Lindskog | [7 empty] | 0 | 2 | 2 | 0 | 0 | 0 | 2
Qi Wang | [7 empty] | 0 | 10 | 10 | 0 | 0 | 0 | 10
Tianyu Wu | [7 empty] | 0 | 2 | 2 | 0 | 0 | 0 | 2
Dibakar Das | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Youhan Kim | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Steve Shellhammer | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Ganesh Venkatesan | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [7 empty] | 0 | 5 | 5 | 0 | 0 | 0 | 5
Girish Madpuwar | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Yongho Seok | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Feng Jiang | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | [7 empty] | 0 | 5 | 5 | 0 | 0 | 0 | 5
Qinghua Li | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Jerome Henry | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 35
[8 empty] | UNASSIGNED | 3 |  |  |  | NET TODO= | 38
Negative likely indicates a duplicate resolution

## Motions
DB Action | DRAFT | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | CIDs/Text
JUN | [12 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
D5.1
D5.1
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
TOTAL | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
20
14

## ToDo Itemized
TECH/GENERAL CIDS TODO
| UNASSIGNED | Roy Want | Ali Raissinia | Qi Wang | Tianyu Wu | Erik Lindskog | Assaf Kasher | Christian Berger | Jonathan Segev | Niranjan Grandhe
| 8008 | 8004 | 8072 | 8003 | 8001 | 8057 |  | 8011 | 8043 | 8049
| 8009 | 8036 | 8073 | 8020 | 8048G | 8066 |  | 8012 |  | 8052G
| 8051 | 8039 | 8074 | 8058 |  |  |  | 8013 |  | 8054
|  | 8041 |  | 8059 |  |  |  | 8015 |  | 8055
|  | 8042 |  | 8060 |  |  |  | 8017 |  | 8056
|  |  |  | 8061 |  |  |  | 8018
|  |  |  | 8062 |  |  |  | 8053
8063
8064
8065
| 3 | 5 | 3 | 10 | 2 | 2 | 0 | 7 | 1 | 5
TECH-TODO | 38