## Summary Stats
CID RESOLUTION STATUS 2022-07-12: Last SA1-8000+ Database Snapshot 11-22/898r0
Comment Type | Ballot Total | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL Motioned | PERCENTAGE
Technical | 36 | JUN: 7; JUL: 9 | 16 | 44.4444
General | 2 | [7 empty] | 0 | 0
Editorial | 27 | [7 empty] | 0 | 0
TOTAL | 65 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 16
PLAN | JUL | AUG | SEP | OCT | NOV | DEC | JAN
Goal | JUL: D6.0: Ballot out of SEP 2022 meeting
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | TODO
Technical CIDS | JUL: 0; AUG: 36; SEP: 16; NOV: 20
General CIDs | JUL: 0; AUG: 2; SEP: 0; NOV: 2
Editorial CIDs | JUL: 0; AUG: 27; SEP: 0; NOV: 27
Includes Withdrawn CIDs as Rejects

## CID Leaderboard
TECH CID Resolver | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL Motions | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Assaf Kasher | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Christian Berger | JUN: 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0
Jonathan Segev | [7 empty] | 0 | 2 | 2 | 0 | 0 | 0 | 2
Ali Raissinia | JUL: 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Nehru Bhandaru | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Erik Lindskog | [7 empty] | 0 | 2 | 2 | 0 | 0 | 0 | 2
Qi Wang | JUL: 7 | 7 | 10 | 3 | 0 | 0 | 0 | 3
Tianyu Wu | [7 empty] | 0 | 2 | 2 | 0 | 0 | 0 | 2
Dibakar Das | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Youhan Kim | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Steve Shellhammer | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Ganesh Venkatesan | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [7 empty] | 0 | 5 | 5 | 0 | 0 | 0 | 5
Girish Madpuwar | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Yongho Seok | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Feng Jiang | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | [7 empty] | 0 | 5 | 5 | 0 | 0 | 0 | 5
Qinghua Li | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Jerome Henry | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 16 | 35 | 19 | 0 | 0 | 0 | 19
[8 empty] | UNASSIGNED | 3 |  |  |  | NET TODO= | 22
Negative likely indicates a duplicate resolution

## Motions
DB Action | DRAFT | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | CIDs/Text
JUN | [12 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
| D5.1 | 202206-01 | 2022-06-29 | 929r1 | Christian Berger |  |  |  |  | 7 |  |  | 8011, 8012, 8013, 8015, 8017, 8018, and 8053 (Total of 7 CIDs)
JUL
| D5.1 | 202207-01 | 2022-07-06 | 957r1 | Qi Wang |  |  |  |  | 7 |  |  | 8020, 8058, 8059, 8060, 8061, 8062 and 8063 (Total of 7 CIDs)
| D5.2 | 202207-02 | 2022-07-11 |  | Assaf Kasher |  |  |  |  | 0 |  |  | Minutes 1
| D5.3 | 202207-03 | 2022-07-11 |  | Assaf Kasher |  |  |  |  | 0 |  |  | Minutes 2
| D5.4 | 202207-04 | 2022-07-11 | 1075r0 | Christian Berger |  |  |  |  | 0 |  |  | Technical Contribution / clarification
| D5.5 | 202207-05 | 2022-07-11 | 1971r0 | Ali Raissinia |  |  |  |  | 2 |  |  | 8072 and 8073 (Total of 2 CIDs)
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
TOTAL | [6 empty] | 0 | 0 | 0 | 16 | 0 | 0
20
14

## ToDo Itemized
TECH/GENERAL CIDS TODO
| UNASSIGNED | Roy Want | Ali Raissinia | Qi Wang | Tianyu Wu | Erik Lindskog | Assaf Kasher | Christian Berger | Jonathan Segev | Niranjan Grandhe
|  | 8004 |  | 8003 | 8001 | 8057 |  | 8008 | 8043 | 8049
|  | 8036 |  | 8064 | 8048G | 8066 |  | 8009 | 8074 | 8052G
|  | 8039 |  | 8065 |  |  |  | 8051 |  | 8054
|  | 8041 | [7 empty] | 8055
|  | 8042 | [7 empty] | 8056
|  | 5 | 0 | 3 | 2 | 2 | 0 | 3 | 2 | 5
TECH-TODO | 22
Inc. General