## Summary Stats
CID RESOLUTION STATUS 2022-08-14: Last SA1-8000+ Database Snapshot 11-22/898r3
Comment Type | Ballot Total | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL Motioned | PERCENTAGE
Technical | 36 | JUN: 7; JUL: 19; AUG: 10 | 36 | 100
General | 2 | JUN: 0; JUL: 1; AUG: 1 | 2 | 100
Editorial | 27 | JUN: 0; JUL: 27 | 27 | 100
TOTAL | 65 | 7 | 47 | 11 | 0 | 0 | 0 | 0 | 65
PLAN | JUL | AUG | SEP | OCT | NOV | DEC | JAN
Goal | JUL: D6.0: Ballot out of SEP 2022 meeting
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | TODO
Technical CIDS | JUL: 0; AUG: 36; SEP: 36; NOV: 0
General CIDs | JUL: 0; AUG: 2; SEP: 2; NOV: 0
Editorial CIDs | JUL: 0; AUG: 27; SEP: 27; NOV: 0
|  |  | Includes Withdrawn CIDs as Rejects | TOTAL CIDS ToDO | 0

## CID Leaderboard
TECH + GEN CID Resolver | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL Motions | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Assaf Kasher | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Christian Berger | JUN: 7; JUL: 2; AUG: 4 | 13 | 13 | 0 | 0 | 0 | 0 | 0
Jonathan Segev | JUL: 2; AUG: 5 | 7 | 7 | 0 | 0 | 0 | 0 | 0
Ali Raissinia | JUL: 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Nehru Bhandaru | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Erik Lindskog | [7 empty] | 1 | 1 | 0 | 0 | 0 | 0 | 0 | bar: AUG
Qi Wang | JUL: 7; AUG: 1 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Tianyu Wu | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dibakar Das | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Youhan Kim | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Steve Shellhammer | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Ganesh Venkatesan | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | JUL: 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Girish Madpuwar | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Yongho Seok | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Feng Jiang | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | JUL: 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Qinghua Li | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Jerome Henry | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 7 | 20 | 11 | 0 | 0 | 0 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0
[8 empty] | UNASSIGNED | 0 |  |  |  | NET TODO= | 0
Negative likely indicates a duplicate resolution

## Motions
DB Action | DRAFT | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | CIDs/Text
JUN | [12 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
| D5.1 | 202206-01 | 2022-06-29 | 929r1 | Christian Berger |  |  |  |  | 7 |  |  | 8011, 8012, 8013, 8015, 8017, 8018, and 8053 (Total of 7 CIDs)
JUL
| D5.1 | 202207-01 | 2022-07-06 | 957r1 | Qi Wang |  |  |  |  | 7 |  |  | 8020, 8058, 8059, 8060, 8061, 8062 and 8063 (Total of 7 CIDs)
| D5.1 | 202207-02 | 2022-07-11 | 991r0 | Assaf Kasher |  |  |  |  | 0 |  |  | May - Jul (end June) Minutes
| D5.1 | 202207-03 | 2022-07-11 | 607r9 | Assaf Kasher |  |  |  |  | 0 |  |  | May Minutes
| D5.1 | 202207-04 | 2022-07-11 | 1075r0 | Christian Berger |  |  |  |  | 0 |  |  | Technical Contribution / clarification (#TC1075r0)
| D5.1 | 202207-05 | 2022-07-11 | 1071r0 | Ali Raissinia |  |  |  |  | 2 |  |  | 8072 and 8073 (Total of 2 CIDs)
| D5.1 | 202207-06 | 2022-07-12 | 1085r1 | Roy Want |  |  |  |  | 0 |  | 20 | See document 1085r1 for the full list
| D5.1 | 202207-07 | 2022-07-12 | 1093r1 | Roy Want |  |  |  |  | 4 |  |  | 8004, 8036, 8039 and 8041 (Total of 4 CIDs)
| D5.1 | 202207-08 | 2022-07-12 | 1099r1 | Jonathan Segev |  |  |  |  | 2 |  |  | 8043 and 8074 (Total of 2 CIDs)
| D5.1 | 202207-09 | 2022-07-14 | 1138r3 | Christian Berger |  |  |  |  | 2 |  |  | 8008 and 8009 (Total of 2 CIDs)
| D5.1 | 202207-10 | 2022-07-14 | 1106r1 | Roy Want |  |  |  |  | 1 |  | 7 | 8002E, 8021E, 8022E, 8024E, 8038E, 8068E, 8069E, and 8042 (Total of 8 CIDs)
| D5.1 | 202207-11 | 2022-07-14 | 1022r2 | Niranjan Grandhe |  |  |  |  | 1 | 1 |  | 8049 and 8052G (Total of 2 CIDs)
AUG
| D5.1 | 202208-01 | 2022-08-03 | 1167r1 | Qi Wang |  |  |  |  | 1 |  |  | 8003 (Total of 1 CID)
| D5.1 | 202208-02 | 2022-08-10 | 1304r0 | Erik Lindskog |  |  |  |  | 1 |  |  | 8066 (Total of 1 CID)
| D5.1 | 202208-03 | 2022-08-10 | 1256r1 | Jonathan Segev |  |  |  |  | 4 | 1 |  | 8064, 8065, 8001, 8048G, 8057 (total of 5 CIDs)
| D5.1 | 202208-04 | 2022-08-10 | 1323r1 | Christian Berger |  |  |  |  | 3 |  |  | 8054, 8055, 8056 (total of 3 CIDs)
| D5.1 | 202208-05 | 2022-08-10 | 898r3 | Roy Want |  |  |  |  | 1 |  |  | 8051 (Total of 1 CID)
| D5.1 | 202208-06 | 2022-08-10 | 898r3 | Roy Want |  |  |  |  | 0 |  |  | SA Recirculation Ballot for D6.0 based on 898r3
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
TOTAL | [6 empty] | 0 | 0 | 0 | 36 | 2 | 27
20
14

## ToDo Itemized
TECH/GENERAL CIDS TODO
| UNASSIGNED | Roy Want | Ali Raissinia | Qi Wang | Tianyu Wu | Erik Lindskog | Assaf Kasher | Christian Berger | Jonathan Segev | Niranjan Grandhe
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TECH-TODO | 0
Inc. General