## Slide 1
Task Group BF March 2023 Closing Report
Date: 2023-03-16
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the March 2023 session.

## Slide 3: TGbf (WLAN Sensing)– March 2023
Progress during March 2023 session
  3 meetings scheduled for TGbf (March 14 AM1, 15 AM2, 16 AM1)
  Assign the comments
  Start comment resolution for D1.0 (LB272)
    the Comment resolution for 23 CID are newly approved
    1.77% of all CC40 comments are now resolved (23/1302, Please refer to the figure)
Goals for the next two months
  Continued comment resolution for D1.0 (LB272)
  Requested 2 calls per week
Chart: P802.11bf D1.0 CR Status
| Technical | General | Editorial
Received | 815 | 28 | 459
Resolved | 19 | 0 | 4

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
   Nov 2022
   Jan 2023
  Recirculation LB (D2.0) Jan 2023  March 2023à July 2023
  Recirculation LB (D3.0) May 2023à Nov 2023
  Recirculation LB (D4.0) July 2023à Jan 2024
  Initial SA Ballot (D4.0) Sep 2023à March 2024
  Final 802.11 WG approval July 2024 à Jan 2025
  802 EC approval July 2024 à Jan 2025
  RevCom and SASB approval Sep 2024à March 2025
Timeline (Comment resolution for D1.0)
January 20, 2023
  802.11 Working group Motion passes：802.11bf (WLAN Sensing) Draft 1.0 and Initial Letter Ballot
Tuesday January 31, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB start for D1.0
Thursday March 2, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB end for D1.0
  Assign the comments

## Slide 5
  To be Confirmed:
  May Interim 2023 (May 14-19)
    May 15 (Monday PM 2), 16:00-18:00 Orlando time
    May 16 (Tuesday AM 1), 08:00-10:00 Orlando time
    May 16 (Tuesday AM 2), 10:30-12:30 Orlando time
    May 17 (Wednesday AM 1), 08:00-10:00 Orlando time
    May 17 (Wednesday AM 2), 10:30-12:30 Orlando time
    May 18 (Thursday AM 1), 08:00-10:00 Orlando time
    May 18 (Thursday AM 2), 10:30-12:30 Orlando time
  ** Note:
  when conflict with CAC, the call may be changed
  (April 2023 – May 2023 CAC calls: April 10, and May 1, 14)
  2. Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 6am-8am in Israel, Friday 5am – 7am in Central Europe), and Sang Kim will help to take the minutes for these slots.
Teleconference Times
  To be Confirmed:
    March 20 (Monday), 10：00 - 12:00 ET – Too close to March plenary
    March 21 (Tuesday), 10：00 - 12:00 ET
    March 23 (Thursday), 23：00 - 01:00 ET
    March 27 (Monday), 10：00 - 12:00 ET
    March 28 (Tuesday), 10：00 - 12:00 ET
    March 30 (Thursday), 23：00 - 01:00 ET
    April 3 (Monday), 10：00 - 12:00 ET
    April 4 (Tuesday), 10：00 - 12:00 ET- holiday
    April 6 (Thursday), 23：00 - 01:00 ET
    April 10 (Monday), 10：00 - 12:00 ET --CAC
    April 11 (Tuesday), 10：00 - 12:00 ET
    April 13 (Thursday), 23：00 - 01:00 ET
    April 17 (Monday), 10：00 - 12:00 ET
    April 18 (Tuesday), 10：00 - 12:00 ET
    April 20 (Thursday), 23：00 - 01:00 ET
    April 24 (Monday), 10：00 - 12:00 ET
    April 25 (Tuesday), 10：00 - 12:00 ET
    April 27 (Thursday), 23：00 - 01:00 ET
    May 1 (Monday), 10：00 - 12:00 ET -- CAC
    May 2 (Tuesday), 10：00 - 12:00 ET - holiday
    May 4 (Thursday), 23：00 - 01:00 ET
    May 8 (Monday), 10：00 - 12:00 ET
    May 9 (Tuesday), 10：00 - 12:00 ET
    May 11 (Thursday), 23：00 - 01:00 ET
 | Orlando time | Beijing Time | Time Central Europe | Israel | Eastern Time | Pacific time
AM1 | 08:00-10:00 | 20:00-22:00 | 14:00-16:00 | 15:00-17:00 | 08:00-10:00 | 05:00-07:00
AM2 | 10:30-12:30 | 22:30-00:30 | 16:30-18:30 | 17:30-19:30 | 10:30-12:30 | 07:30-09:30
PM1 | 13:30-15:30 | 01:30-03:30 | 19:30-21:30 | 20:30-22:30 | 13:30-15:30 | 10:30-12:30
PM2 | 16:00-18:00 | 04:00-06:00 | 22:00-24:00 | 23:00-01:00 | 16:00-18:00 | 13:00-15:00
Evening 1 | 19:30-21:30 | 07:30-09:30 | 01:30-03:30 | 02:30-04:30 | 19:30-21:30 | 16:30-18:30