## Slide 1: ARC Closing Report
Date: 2023-05-18
Authors:

## Slide 2: Abstract
This document is the closing report for ARC SC,
May 2023 Plenary Session

## Slide 3: Work Completed - 1
Agenda is here: 11-23/0576r5
IEEE Std 802 revision:
  Note that drafts and working documents are posting in the 802.1 area, and the EC’s Mentor area. (Talk to Joe Levy if you need help finding them.)
  We got an update from our (802.11) representative to this project, Joseph Levy. 802.11-specific comments are proceeding well/done.
  P802REVc has resolved most comments, but the few remaining ones need contribution or a fair bit of discussion. Will be done on teleconferences, targeting July session for next ballot.

## Slide 4: Work Completed - 2
IEEE Std 802 revision (continued):
  802.11 ARC was requested to take an action item to work on a definition for “IEEE 802 Network”. We noted that the IEEE Std 802 document is currently inconsistent (and arguably contradictory) between the definition and body text statements about what this term means/requires.
  ARC discussion concluded that this is complicated, when the wide breadth of 802 Standards are considered, and the resulting breadth of concepts included in “802 network”. We’ll work on this further on the reflector and on teleconferences, and finalize in July.

## Slide 5: Work Completed - 3
Annex G:
  Considered updated proposal for Annex G replacement with tutorial material/examples on how a “frame exchange sequence” relates to other 802.11 concepts: 11-23/0880r0
  Based on the feedback on the direction, the author (Harry Bims) will bring back more details in July.

## Slide 6: Monitoring/future activities
    Other items being tracked (but not actively worked unless/until contributions):
    “What is a STA?” (per REVmd discussion: 11-19/0106r0)
    Off-channel TDLS architecture
    MLME-RESET, versus MLME-JOIN, MLME-START, MLME-SCAN and MLME-END
      One aspect is how MAC address is set/controlled – related to IEEE 1609/TGbd activities

## Slide 7: Plans
Ongoing work:
Monitor IEEE P802REVc comment resolution
Annex G replacement phase 2, continued
Complete P802REVc homework to (re)define “IEEE 802 Network”
Monitoring/future activities, or other relevant topics, if any contributions
Teleconferences – Mondays, June 12 and June 26, 2pm ET, 1 hour, to discuss definition of “IEEE 802 Network”
Two meeting slots requested in July