## Slide 1: TGbe July Closing Report
Date: 2023-07-13
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 10 sessions during the July plenary
  Five Joint sessions, five MAC and two PHY ad-hoc sessions
    Discussed comment resolution documents
    All comments from LB271 are now resolved
  Instructed the editor to generate IEEE802.11 TGbe D4.0
    TGbe D4.0 is expected to be available by end of July 2023
Agenda is available in 11-23/919r13
Motions List is available in 11-23/442r19
Goals for September 2023:
  Complete comment assignments from recirculation LB on TGbe D4.0
  Start the comment resolution process
  Discuss any technical submissions
CID Distribution (~3340)
~10%
~80%
~10%

## Slide 3: Teleconference Plan
Will be sent with 10-day advanced notice
Following the TGbe usual patterns, accounting for workload

## Slide 4: TGbe Timeline And Status
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Letter Ballot May 2022
D3.0 Letter Ballot Jan 2023
D4.0 Letter Ballot July 2023
Initial SA Ballot Nov 2023
Final 802.11 WG approval Sept 2024
802 EC approval Oct 2024
RevCom and SASB approval Dec 2024