## Slide 1: TGbk 320MHz Positioning July Meeting Closing Report
Date: 2023-07-12
Authors:

## Slide 2: Abstract
This document is the TGbk 320MHz Positioning closing report for the IEEE 802.11 Plenary July 2023 meeting.

## Slide 3: July Meeting Progress and Targets Towards the Sep. Meeting
Work completed this week:
  Adopted 5 draft text submissions and expect to generate D0.2 coming out of the July meeting.
  Reviewed submission discussing measurement sequence (sequence frame formats, channel access, measurement sequences).
  Reviewed total of 6 technical and amendment text submissions.
  Roughly 70% completion towards D1.0 and WG ballot.
Jonathan Segev, Intel corporation
TGbk:
Specification framework (SFD)
Draft amendment
TGaz:
Usage model
Functional requirements
Specification framework
Draft amendment

## Slide 4: July Meeting Progress and Targets Towards the Sep. Meeting
Work completed this week: (con.)
  Reviewed program timelines, sub activities division and progress of individual sub activities toward D1.0.
  Roughly 70% completion towards D1.0 and WG ballot.
Targets towards the Sep. meeting:
  Generate P802.11bk draft 0.2 out of July meeting and targeting D0.7 out of the Sep. meeting.
  Continue review and adoption of amendment text.
  Consider earlier WG ballot readiness.

## Slide 5: TGbk Projected Timeline (previously)
Q2 2024
Q1 2024
Q3 2023
Q2 2023
Q1 2023
Q4 2023
Q3 2024
Q4 2024
Formation
Framework
802.11bk D1.0 amendment text
WG Ballot series
SA Ballot series
Framework completion
05/23
WG approval for initial WG ballot
09/23
WG approval for initial SA ballot
11be SA ballot
completion
11bk SA ballot completion
11bk EC
approval

## Slide 6: TGbk Projected Timeline (updated)
Q4 2023
Q4 2023
Q3 2023
Q2 2023
Q1 2023
Q3 2023
Q1 2024
Q1 2024
Formation
Framework
Framework completion
05/23
802.11bk D1.0 amendment text development
TB and NTB Meas. Sequence
TB and NTB negotiation
TX, RX LTF VECTORS
MAC Passive Ranging
EHT Tx Procedure
TOD Accuracy
PHY section EHT TB Ranging NDP
PHY section EHT Ranging NDP
MAC section pseudo random LTF sequence
PHY section pseudo random sequence mapping
Elements and frame formats (ctrl , man etc.)
WG ballot
11/23

## Slide 7: Scheduled TGbk telecons
  Tue. Aug. 1st 13:00-14:30 ET / 10:00 – 11:30 PT
  Tue. Aug. 15th 13:00-14:30 ET / 10:00 – 11:30 PT
  Tue. Aug. 29th 13:00-14:30 ET / 10:00 – 11:30 PT ┼
* - newly announced
** - meeting as part of the IEEE week, refer to WG agenda document for details.
┼ - Motion meeting, motions to be made available to chair 15 days in advance and announced to group 10 days in advance.