## Slide 1
Task Group BF September 2023 Closing Report
Date: 2023-09-14
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the September 2023 session.

## Slide 3: TGbf (WLAN Sensing)– September 2023
Progress during September 2023 session
  5 slots scheduled for TGbf (Sept 11 AM2, 12 AM1 & PM1, 13 AM2, 14 AM2)
  Comment resolution for D2.0 (LB276)
    the Comment resolution for 130 CID are newly approved or marked as “ready for motion”
    23.85% of all LB276 comments are now resolved or marked as “ready for motion”
    (130/545, Please refer to the figure)
Goals for the next two months
  Continue comment resolution for D2.0 (LB276)
  Requested 2 calls per week
Chart: P802.11bf D2.0 CR Status
| Technical | General | Editorial
Received | 257 | 19 | 269
Resolved | 46 | 8 | 76

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022 Nov 2022
   Jan 2023
  Recirculation LB (D2.0) Jan 2023  Mar 2023
   July 2023
  Recirculation LB (D3.0) May 2023  Nov 2023
  Recirculation LB (D4.0) July 2023 à Jan 2024
  Initial SA Ballot (D4.0) Sep 2023 à Mar 2024
  Final 802.11 WG approval July 2024à Jan 2025
  802 EC approval July 2024à Jan 2025
  RevCom and SASB approval Sep 2024à Mar 2025
Timeline (Comment resolution for D2.0)
July 14, 2023
  802.11 Working group Motion passes：802.11bf (WLAN Sensing) Draft 2.0 and Re-circulation Letter Ballot
Wed July 26, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB start for D2.0
Sun August 20, 2023 at 23:59 Eastern Time USA (11:59 PM)
  Initial LB end for D2.0
  Assign the comments
Target for Recirculation LB (D3.0) in November Plenary

## Slide 5
Teleconference Times (plan after September Interim)
  Confirmed:
    Sept 18 (Monday), 10：00 - 12:00 ET – Too close to Sept Interim
    Sept 19 (Tuesday), 10：00 - 12:00 ET
    Sept 21 (Thursday), 23：00 - 01:00 ET
    Sept 25 (Monday), 10：00 - 12:00 ET
    Sept 26 (Tuesday), 10：00 - 12:00 ET
    Sept 28 (Thursday), 23：00 - 01:00 ET
    Oct 2 (Monday), 10：00 - 12:00 ET – holiday
    Oct 3 (Tuesday), 10：00 - 12:00 ET – holiday
    Oct 5 (Thursday), 23：00 - 01:00 ET – holiday
    Oct 9 (Monday), 10：00 - 12:00 ET – CAC
    Oct 10 (Tuesday), 10：00 - 12:00 ET
    Oct 12 (Thursday), 23：00 - 01:00 ET
    Oct 16 (Monday), 10：00 - 12:00 ET
    Oct 17 (Tuesday), 10：00 - 12:00 ET
    Oct 19 (Thursday), 23：00 - 01:00 ET
    Oct 23 (Monday), 10：00 - 12:00 ET
    Oct 24 (Tuesday), 10：00 - 12:00 ET
    Oct 26 (Thursday), 23：00 - 01:00 ET
    Oct 30 (Monday), 10：00 - 12:00 ET – CAC
    Oct 31 (Tuesday), 10：00 - 12:00 ET
    Nov 2 (Thursday), 23：00 - 01:00 ET
    Nov 6 (Monday), 9：00 - 11:00 ET
    Nov 7 (Tuesday), 9：00 - 11:00 ET
    Nov 9 (Thursday), 22：00 - 00:00 ET
  To be Confirmed:
  November Plenary 2023 (Nov 12-17)
    Nov 13 (Monday PM 1), 13:30-15:30 Hawaii time
    Nov 13 (Monday PM 2), 16:00-18:00 Hawaii time
    Nov 14 (Tuesday AM 1), 08:00-10:00 Hawaii time
    Nov 14 (Tuesday AM 2), 10:30-12:30 Hawaii time
    Nov 15 (Wednesday AM 2), 10:30-12:30 Hawaii time
    Nov 15 (Wednesday PM 1), 13:30-15:30 Hawaii time
    Nov 16 (Thursday PM 1), 13:30-15:30 Hawaii time
    Nov 16 (Thursday PM 2), 16:00-18:00 Hawaii time
 | Hawaii time | Beijing Time | Time Central Europe | Israel | Eastern Time | Pacific time
AM1 | 08:00-10:00 | 02:00-04:00 | 19:00-21:00 | 20:00-22:00 | 13:00-15:00 | 10:00-12:00
AM2 | 10:30-12:30 | 04:30-06:30 | 21:30-23:30 | 22:30-00:30 | 15:30-17:30 | 12:30-14:30
PM1 | 13:30-15:30 | 07:30-09:30 | 00:30-02:30 | 01:30-03:30 | 18:30-20:30 | 15:30-17:30
PM2 | 16:00-18:00 | 10:00-12:00 | 03:00-05:00 | 04:00-06:00 | 21:00-23:00 | 18:00-20:00
Evening 1 | 19:30-21:30 | 13:30-15:30 | 06:30-08:30 | 07:30-09:30 | 00:30-02:30 | 21:30-23:30
5 Nov 2023 - Daylight Saving Time ends
Sunday, 5 Nov 2023, 02:00:00 clocks are set back 1 hour to Sunday, 5 Nov 2023, 01:00:00 local daylight time instead.
  ** Note:
  When conflict with CAC, the call may be changed.
  (Sept 2023 – Nov 2023 CAC calls: Oct 9, Oct 30)
  Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 6am-8am in Israel, Friday 5am – 7am in Central Europe), and Sang Kim will help to take the minutes for these slots.