## Slide 1: TGbh Closing Report
Date: 2023-09-14
Authors:

## Slide 2: Abstract
This document is the closing report for TGbh
“Randomized and Changing MAC addresses” (RCM)
September 2023 Session (mixed-mode)

## Slide 3: Work Completed
Agenda is here: 11-23/1341r5
Comment resolution on D1.0 spreadsheet: 11-23/1152r20
Motions: 11-22/0651r25
Resolved 135 of 294 comments. All (159) remaining are assigned. Identified 8 “topic areas” for comments.
Will jump ahead of 802.11be in amendment ordering
Still owe WBA a more detailed liaison response to their liaisons to us; will discuss on telecon (Oct 7) and in November: 11-21/0703r0, 11-21/1141r0, 11-22/0668r0, 11-22/0653r0

## Slide 4: LB274 comment resolution status
Chart: 
| Overall (Aug) | Overall (Sep) | Technical/General | Editorial
Completed (Motioned) | 105 | 127 | 62 | 65
Ready for Motion | 0 | 8 | 7 | 1
Submission Ready | 121 | 109 | 87 | 22
Assigned | 20 | 50 | 46 | 4
Unassigned | 48 | 0 | 0 | 0

## Slide 5: Timeline
  PAR approved Feb 2021
  First TG meeting Mar 2021
  D0.2 CC May 2022
  Initial WG Letter Ballot (D1.0) May 2023
  Recirculation LB (D2.0) Nov 2023
  Initial SA Ballot (D3.0) Mar 2024
  Final 802.11 WG approval Jul 2024
  802 EC approval Jul 2024
  RevCom and SASB approval Sep 2024

## Slide 6: Teleconferences
Tuesdays at 9:30am ET, 2 hours:
  Sep 26, Oct 3, 10, 17?, 24, 31*, Nov 7
Oct 17, is TBC (WFA week)
Oct 3 is dediated to WBA liaison response
November plans
4 slots
Complete comment resolution on D1.0 Initial Letter Ballot
Response to WBA liaisons