## Slide 1: REVme Closing Report – November 2023
Date: 2023-11-16
Authors:

## Slide 2: Work Completed
Continued with comment resolution to comments received in the initial SA ballot on D4.0
Note: D4.1 has been posted with P802.11az-2023 rolled in.

## Slide 3: Plans for January
Teleconferences scheduled
  Monday Nov 20 (announced in Sept), Friday Dec 1, 15, Jan 5, Monday Jan 8
  @ 10am ET for 2
Adhoc meeting on Dec 7-8 at IEEE SA headquarters in Piscataway, NJ
Complete comment resolution on initial SA ballot in the January interim.
Amendment roll-in (target completion by end of Dec):
  P802.11az-2023 – in D4.1
  P802.11ad-2023 – in progress
  P802.11bb-2023 – in progress
  P802.11bc-2023 – in progress

## Slide 4: TGme Timeline (No changes)
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB
July 2023 – D4.0 Recirculation
Sep 2023 – D5.0 Initial SA Ballot
Feb 2024 – D6.0 Recirculation SA Ballot (roll-in of published amendment 11az, 11bd, 11bc, 11bb)
May 2024 – D7.0 Recirculation SA Ballot
Jul 2024 – D8.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval