## Slide 1: TGbk 320MHz Positioning March Meeting Closing Report
Date: 2024-03-14
Authors:

## Slide 2: Abstract
This document is the TGbk 320MHz Positioning closing report for the IEEE 802.11 March 2024 plenary meeting.

## Slide 3: March Meeting Progress and Targets Towards the May Meeting
Work completed during this meeting:
  Reviewed, and approved resolution to 70 Technical and General CIDs.
  Reviewed 16 CR submissions and approved 22 motions.
  TG approved 1st recirculation ballot (WG motion expected later in this session).
  Reviewed and considered progress – no change to timelines.
Work expected towards March meeting:
  Generated P802.11bk D2.0.
  Run 15 day WG recirculation ballot.
  Consider ballot result and initiate MDR process.
Jonathan Segev, Intel corporation
Chart: LB279 Comments Totals by type
| Comments totals
Overall | 401
Editorial | 226
Technical | 163
General | 12

## Slide 4: TGbk Projected Timeline (previous)
Q2 2024
Q1 2024
Q3 2023
Q2 2023
Q1 2023
Q4 2023
Q3 2024
Q4 2024
Formation
Framework
Framework completion
05/23
802.11bk amendment text development
Initial WG ballot
Recirc 03/24
Final SA
11bk D2.0
Initial SA
07/24
Final WG ballot 7/24
11bk D3.0
MDR
MDR start
MDR cmp
D4.0
D5.0
Final SA
07/23
SA Recir.
10/24

## Slide 5: TGbk Projected Timeline (updated)
Q2 2024
Q1 2024
Q3 2023
Q2 2023
Q1 2023
Q4 2023
Q3 2024
Q4 2024
Formation
Framework
Framework completion
05/23
802.11bk amendment text development
Initial WG ballot
Recirc 03/24
11bk D2.0
Initial SA
07/24
Final WG ballot 7/24
11bk D3.0
MDR
MDR
start
MDR cmp
D4.0
D5.0
Final SA
11/24
SA Recir.
10/24

## Slide 6: Scheduled TGbk telecons
  Thu. Apr. 25th 11:00am PT / 13:00 ET (1:30)
  Tue. Apr. 30th 10:00am PT / 13:00 ET (2:00)
  Tue. May 7th 10:00am PT / 13:00 ET (2:00)
** - meeting as part of the IEEE week, refer to WG agenda document for details.
┼ - Motion meeting, motions to be made available to chair 15 days in advance and announced to group 10 days in advance.