## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-24/0883r6
Venue Date: | June 2024
First Author: | Mark Hamilton (Ruckus/CommScope)
Subject: | IEEE 802.11bh LB274 comments
Full Date: | 2024-06-01
Author(s): | Name(s) | Mark Hamilton
| Company: | Ruckus/CommScope
Address
Phone:
Fax:
| email: | mark.hamilton2152@gmail.com
Abstract: | This document contains the comments received on P802.11bh Initial SA ballot, and any resolutions approved by 802.11 TGbh.

## Revision History
Revision | Date | Description
0 | 2024-05-11 | Initial revision. Initial SA (D4.0) Ballot comments
1 | 2024-05-12 | Renumbered CIDs to be unique from prior ballots
2 | 2024-05-13 | Noted CIDs that are in 11-24/0885. Several are Ready for motion as of May 12, EVE, but resolutions need to be copied into those columns. Marked the Notes column in green as a placeholder, for now.
3 | 2024-05-14 | Captured agreed resolutions, per presentations Mon/Tues of Warsaw session
4 | 2024-05-27 | Approved resolutions per motion 39. Added assignee and submission for CIDs in submitted documents. Flagged CIDs: Red - unassigned; Blue - Ready for Motion; Green - Completed (motioned)
5 | 2024-05-28 | Updates from June 28 teleconference
6 | 2024-06-01 | CID 3120 Ready for motion. Several CIDs assigned to Graham, docs 11-24/968 and 11-24/916
7
8
9
10

## Comments
CID | Ballot Comment ID | Name | Category | Page | Subclause | Line | Comment | Must be Satisfied | Proposed Change | Assignee | Submission | Resolution Type | Resolution Text | Motion Number | Notes | ACCEPTED | REJECTED | REVISED | Notes
3001 | 329287 | Wullert, John | Technical | 38 | 12.2.12.2 | 32 | The sentence is confusing because the phrase "directed or broadcast" is not a member of the list frames where the non-AP STA can use the IRM, but a description of the types of probe frames. | No | Rephrase as "The non-AP STA may also use that IRM as its TA for any directed or broadcast probe frames, public Action frames, Authentication frames, and (Re)Association frames that it may transmit when it intends to be identified." | Graham Smith | 11-24/916
3002 | 329288 | Wullert, John | Editorial | 52 | AF.4 | 30 | Improper verb form - "generate" should be "generates" | No | Rephrase as "An AP that receives an opaque device identifier extracts the original identity and generates a new opaque device identifier for the STA." | Carol Ansley | 11-24/952
3003 | 329319 | Yang, Jay | Technical | 34 | 12.2.12.1 | 44 | Device ID has the long term property, but if the AP assign non-ap STA with a Device ID that is used in the PASN procedure, the long term property will be broken. Further, the Device ID in PASN is required to be encrypted, but there is no such limition in 4HS. Therefore the characteristic of Device ID in 4HS and PASN is still different. | Yes | Seperate Device ID in 4HS from PASN procedure, e.g. define PASN ID in PASN procedure. | Yan Li | 11-24/0789 | [7 empty] | PASN ID
3004 | 329320 | Yang, Jay | Technical | 26 | 9.4.2.19.7 | 7 | IRM included in TA field of probe request, and thus "IRM in the Address 1" should be "IRM in the Address 2" | No | change "IRM in the Address 1" to "IRM in the Address 2" in L7P26 | Jay Yang | 11-24/0893
3005 | 329321 | Yang, Jay | Technical | 26 | 9.4.2.19.7 | 8 | the probe request should be sent to an unassociated AP, | No | change "it transmits" to "it transmits to an unassociated AP" in both L8P26 and L18P26. | Jay Yang | 11-24/0893 | [7 empty] | Discuss
3006 | 329322 | Yang, Jay | Technical | 31 | 11.10.9.1.1 | 60 | IRM should be in TA field in probe request, and thus "the Address 1 field" should be "the Address 2 field" | No | change "the Address 1 field" to "the Address 2 field" in L60P26. | Jay Yang | 11-24/0895
3007 | 329323 | Yang, Jay | Technical | 40 | 12.13.3.2 | 40 | the verify on Encrypted Data element is missing, please add it in. | Yes | add the Verify or decrypt on the Encrypted Data element when STA receives the second PASN frame, also when the AP receives the third PASN frame | [9 empty] | Submission Required
3008 | 329403 | Smith, Graham | Technical | 17 | 3.2 | 9 | "device identification (ID): [device ID] An ID that a network can provide to a non-access-point (non-AP) station (STA) to allow the non-AP STA to identify itself to a known network at a future time.[84, 65]". Surely it is to the same network? | Yes | Replace cited with "device identification (ID): [device ID] An ID that a network can provide to a non-access-point (non-AP) station (STA) to allow the non-AP STA to identify itself to a known that same network at a future time." | Graham Smith | 11-24/0968 | [7 empty] | Typo in Proposed Change?
3009 | 329404 | Smith, Graham | Technical | 28 | 9.4.2.316 | 4 | "When the Device ID element is sent from a non-AP STA to an AP, the Device ID Status field is reserved". What does reserved mean? All zeros or not present? In the IRM section we say "not present" . We should use the the same here. In addition, this needs to be moved ahead of "The Device ID field contains a device ID" as it comes before the device ID in the element. | No | Replace cited text with "When sent from a non-AP STA to an AP, the Device ID Status field is not present ." and move to Page 27 ahead of line 63. | Jay Yang | 11-24/0893
3010 | 329405 | Smith, Graham | Technical | 29 | 9.4.2.319 | 6 | "The PASN Encrypted Data element contains an Encrypted Data field to be encrypted by the KEK." Is it encrypted or not? It says "to be encrypted", so this data is not encrypted which is also clear from Table 9-417c. Hence the term "encrypted data" is misleading, it is data that will be encrypted, or "data for encryption". | No | Replace "Encrypted" with "Encryption" at the following locations 29.3, 29.6, 29.10 (in Figure 9-1072d), 29.15, 29.20, 29.21, 29.26, 29.44. | Graham Smith | 11-24/0968
3011 | 329406 | Smith, Graham | Editorial | 34 | 12.2.12.1 | 58 | "...when dot11PASNActivated is true, and has dot11DeviceIDActivated equal to true shall set…" Commas need changing | No | Replace cited with: "".. when dot11PASNActivated is true and has dot11DeviceIDActivated equal to true, shall set…" | Carol Ansley | 11-24/952
3012 | 329407 | Smith, Graham | Technical | 35 | 12.2.12.1 | 28 | "When using PASN authentication, in the Device ID element in the first PASN frame". I think that it should be "a Device ID element". Similar for the other 5 bullets. | No | At Page 35 lines 28,29,30, 35, 36, 37, replace "the Device ID" with "a Device ID", | Jay Yang | 11-24/0885 | Accepted |  | 39 |  |  |  |  | Resolved
3013 | 329408 | Smith, Graham | Technical | 35 | 12.2.12.1 | 41 | "A STA may delete a stored device ID at any point in time for implementation specific reasons (for example, configuration changes have lost the device ID, or sufficient time has passed since the last association to the ESS)." Do we really need to say this? We don't want this to happen. At least relegate this to a note. | No | Make cited sentence a NOTE. Replace "may" with "might". NOTE: A STA may might delete a stored device ID at any point in time for implementation specific reasons (for example, configuration changes have lost the device ID, or sufficient time has passed since the last association to the ESS)." | Jay Yang | 11-24/0885 | Revised | Remove the text in the parenthesis (in P35/41) | 39 |  |  |  |  | Resolved
3014 | 329409 | Smith, Graham | Editorial | 35 | 12.2.12.1 | 60 | The paragraph at P35.58 is on PASN. It would be better to move this to Page 36 just preceeding line 20 where the PASN explanation is given. | No | Move paragraph to just before P36.20. | Carol Ansley | 11-24/952
3015 | 329410 | Smith, Graham | Technical | 36 | 12.2.12.1 | 20 | When using PASN, the device ID must change every authentication. If the same network wanted to provide a permanent device ID to that non-AP STA, then it is in trouble. We should have a way such that a temporary ID can be used, that is seperate from the permanent ID. | No | As the ID used with PASN is a temporary ID, it is proposed to use a different term - PASN ID. A proposal will be presented. | Yan Li | 11-24/0789 | [7 empty] | PASN ID
3016 | 329417 | Smith, Graham | Technical | 27 | 9.4.2.316 | 32 | As the Device ID Status filed is omitted when sent from non-AP STA to AP, the Octets should be "0 or 1". | Yes | At 27.33 under "Device ID Status" change "1" to "0 or 1" | Jay Yang | 11-24/0893
3017 | 329418 | Smith, Graham | Editorial | 35 | 12.2.12.1 | 22 | "A STA should not send a frame containing a device ID (sub)element to any STA unless the receiving STA sets the Device ID Active field to 1 in the Extended RSN Capabilities field." Should be .."unless the receiving STA has set the…" | Yes | At 35.22 change "...unless the receiving STA sets the…" to "...unless the receiving STA has set the…" | Carol Ansley | 11-24/952
3018 | 329419 | Smith, Graham | Editorial | 35 | 12.2.12.1 | 25 | "using the procedures described below". Seems strange. Better to use "as follows" | Yes | At 35.25 Change "If a non-AP STA has a device ID configured, then it shall provide a device ID using the procedures described below:" to "If a non-AP STA has a device ID configured, then it shall provide a device ID as follows:" | Carol Ansley | 11-24/952
3019 | 329420 | Smith, Graham | Editorial | 35 | 12.2.12.1 | 34 | "An AP shall provide a device ID using the procedures described below:" Seems strange, better to use "as follows" | Yes | At 35.34 change "An AP shall provide a device ID using the procedures described below:" to "An AP shall provide a device ID as follows:" | Carol Ansley | 11-24/952
3020 | 329421 | Smith, Graham | Technical | 35 | 12.2.12.1 | 42 | A STA may delete a stored device ID at any point in time for implementation specific reasons (for example, configuration changes have lost the device ID," Hmm…if the STA has lost the device ID, then surely it has been effectively deleted. So we are saying that a STA may lose a device ID, and that is OK? Not sure this is a good example. I would delete it and just keep the "long time" example. | Yes | At 35.42 delete "configuration changes have lost the device ID, or" | Jay Yang | 11-24/0885 | Revised | Remove the text in the parenthesis (in P35/41) | 39 |  |  |  |  | Resolved
3021 | 329492 | Huang, Po-Kai | Technical | 41 | 12.7.3 | 12 | For AKM 21 row, When Base AKMP is 21, i.e., PASN, 128 KEK_bits may not align with the security strength when pairwise cipher uses GCMP-256. Similar consideration for AKM 26 row. Suggest to align the KEK_bits based on pairwise cipher. | Yes | For AKM 21 row, change "128 if Base AKMP is 00-0F-AC:21" to "128 if Base AKMP is 00-0F-AC:21 and pairwise cipher is not 00-0F-AC:9 or 00-0F-AC:10. 256 if Base AKMP is 00-0F-AC:21 and pairwise cipher is 00-0F-AC:9 or 00-0F-AC:10." For AKM 26 row, change "256" to "256 if pairwise cipher is not 00-0F-AC:9 or 00-0F-AC:10. 512 if pairwise cipher is 00-0F-AC:9 or 00-0F-AC:10" | Po-Kai Huang | 11-24/891 | Rejected | The comment has been withdrawn by the commenter | [5 empty] | Ready for motion
3022 | 329523 | Yang, Jay | Technical | 23 | 9.3.3.5 | 6 | According the rule defined in 4.5.3.4, Reassociation procedure can be used for a STA to change its associaton attributes with the same AP. That's, the STA should disconnect from one AP, and then reassociate with the same AP due to association attributes changing reason. In that case, 11bh identifier also can be used. | Yes | change "Association" to "Re(association)" to cover the case mentioned above, and do the same change in other propreciated place as well. | Graham Smith | 11-24/0968
3023 | 329770 | Stacey, Robert | Editorial | 19 | 6.4 | 7 | Editing instructions are one of the following: change, delete, insert, replace (see 14.33). | No | Review this and other editing instructions to use the correct verb. (e.g., this one should be "Insert a new row in Table 9-1 as follows:" | Carol Ansley | 11-24/952
3024 | 329771 | Stacey, Robert | Technical | 27 | 9.4.2.316 | 40 | The Device ID Length field is not a length; it's a field. | No | Change to "The Device ID Length field is set to the number of octets in the Device ID field." ("is set to" or "indicates"; I prefer "is set to" because indicates is not specific on the encoding) | Graham Smith | 11-24/916 | Revised | Change cited text to “The Device ID Length field is set to the number of octets in the Device ID field." | [5 empty] | Ready for motion
3025 | 329772 | Stacey, Robert | Technical | 28 | 9.4.2.316 | 1 | The note, because it contains "optionally", is not purely informative. In this context "optionally" is equivalent to "might". | No | Change the note to read "NOTE--The device ID might be constructed as an opaque identifier as described in 12.2.12.1 (Device ID mechanism)". I would remove the additional reference to Annex AF; the first reference is all the reader needs. | Jay Yang | 11-24/0893
3026 | 329773 | Stacey, Robert | Technical | 28 | 9.4.2.317 | 27 | "contains one of the values"; well of course it does, but the table is not just a list of values, it assigns meaning to those values. | No | Change the sentence at 28.24 to read "The IRM Status field is present if the element is sent to a non-AP STA and otherwise not present" (so that we have one statement on presence or absence). Change the statement at 28.26 to read "The IRM Status field is defined in Table 9-417b" For consistency, change the statement at 28.44 and 28.47 to "The IRM field is present if the element is sent to an AP and otherwise not present." and "The IRM field contains a MAC address.", respectively. | Graham Smith | 11-24/0968
3027 | 329774 | Stacey, Robert | Technical | 17 | 3.2 | 13 | "can be used" defines ability but ability is not what the definition is for. The definition is mixing behavior (what the non-AP STA does with the IRM) with what the IRM itself is. | No | Change the definition to "A MAC address that with high probability uniquely identifies a non-AP STA." It might be useful to add "The IRM is not sent in the clear so that the non-AP STA identity is protected." (or similar statement on purpose). | Graham Smith | 11-24/0968
3028 | 329776 | Stacey, Robert | Technical | 17 | 3.2 | 9 | "identification" is an action or process. So one would expect that the "device identification" definition be about an action or process (which it is not). "Identification" would not normally be abbreviated as ID. Expanding it in the definition makes it read "An identification that a network can provide.." making it sound like a thing (not an action). "can provide" is mixing behavior (what the network does with the device ID) and meaning (what the device ID is). "to allow a non-AP STA to identify itself" implies that the AP is providing permission for the non-AP STA to identify itself and not just providing the means for the non-AP STA to identify itself. | Yes | Change the term to "device identifier". Change the definition to "A value provided by an AP to a non-AP STA, that if returned by the non-AP STA to the AP in a future association, allows the AP or another AP in the ESS to identify the non-AP STA." Update the "measurement identifier" term along similar lines. | Graham Smith | 11-24/0968
3029 | 329777 | Stacey, Robert | Technical | 18 | 4.5.4.10 | 15 | "can" defines ability; "might" more appropriate here. It is not clear why one identifier is "provided" and the other "used". The second sentence seems unnecessary since the mechanisms are introduced in the context of "mitigate this sort of traffic analysis". | No | Change the first sentence to "Such a STA, might identify itself to the AP (and only the AP) by providing to the AP a device ID previously allocated to the non-AP STA by the network and/or by using as its MAC address the IRM provided by the non-AP STA to the network in the previous association." and remove the second sentence. | Graham Smith | 11-24/0968
3030 | 329778 | Stacey, Robert | Technical | 27 | 9.4.2.240 | 6 | The distinction between a feature being "active" vs "supported" is not clear, particularly in the context of on-air signaling (as opposed to the MIB). In this case we don't even have a capability indication for the feature and so "active" appears to be a poor substitute for "capability" (i.e., support). And this is doubly true since we are using it in a "Capability" element. We might want "active" semantics in the MIB where an management entity can enable or disable a feature. But we don't need to reflect this in the OTA signaling; as for as the OTA protocol is concerned the feature is either supported or not supported. It a management entity has not activated it, then it is not supported. | Yes | Change "Device ID Active" to "Device ID Support". Change "IRM Active" to "IRM Support". At 34.51 change "A non-AP STA that has dot11DeviceIDActivated equal to true indicates the device ID mechanism is activated by setting the Device ID Active field to 1..." to "A non-AP STA that has dot11DeviceIDActivated equal to true shall set the Device ID Support field to 1 to indicate that the device ID mechanism is supported..." (note the shall -- normative requirement to keep the MIB and OTA signaling aligned) At 37.52 change "An AP that has dot11IRMActivated equal to true advertises activation of the IRM mechanism by setting the IRM Active field to 1..." to "An AP that has dot11IRMActivated equal to true shall set the IRM Support field to 1 to indicate that the IRM mechanism is supported..." At 37.54 change "A non-AP STA that has dot11IRMActivated equal to true indicates the IRM mechanism is active by setting the IRM Active field to 1..." to "A non-AP STA that has dot11IRMActivated equal to true shall set the IRM Support field to 1 to indicate that the IRM mechanism is supported.." | Robert Stacey | 11-24/919
3031 | 329779 | Stacey, Robert | Technical | 38 | 12.2.12.2 | 31 | association is not requested | Yes | Change "the next time it requests association to any AP in that same ESS" to "the next time it associates with an AP in that same ESS" | Graham Smith | 11-24/916
3032 | 329780 | Stacey, Robert | Editorial | 24 | 12.2.12.1 | 46 | Since we use the term "an AP with dot11DeviceIDActivated equal to true" a lot, we might want to define something a little shorter and easier to read. | No | Add a sentence "An AP that has dot11DeviceIDActivated equal to true is referred to as an device ID capable AP. A non-AP STA that has dot11DeviceIDActivated equal to true is referred to as an device ID capable non-AP STA." And the use the new terms from then on. Similarly for the IRM mechanism. | Carol Ansley | 11-24/952
3033 | 329781 | Stacey, Robert | Editorial | 37 | 12.2.12.2 | 50 | "Identifiable random MAC address (IRM) operation" in the title but "IRM mechanism" elsewhere. | No | Change title to "Identifiable random MAC address (IRM) mechanism". At 48.28, change "IRM operation" to "IRM mechanism" | Graham Smith | 11-24/916
3034 | 329782 | Stacey, Robert | Editorial | 38 | 12.2.12.2 | 27 | "When associating or authenticating using PASN for the first time" is ambiguous (one does not associate using PASN). | No | Change to "When associating for the first time or authenticating using PASN for the first time..." | Graham Smith | 11-24/916
3035 | 329783 | Stacey, Robert | Editorial | 30 | 12.2.13 | 38 | Keep the subclause headings concise. "in PASN" is not correct since PASN is a protocol (mechanism). | No | Change to "Encrypting the Encrypted Data field for PASN" | Carol Ansley | 11-24/952
3036 | 329972 | Patwardhan, Gaurav | Technical | 18 | 4.5.4.10 | 15 | Change from 'STA' to 'non-AP STA' in this paragraph for the newly added text. A separate comment to be submitted to REVme for the baseline text. | Yes | as in comment | Graham Smith | 11-24/0968
3037 | 329973 | Patwardhan, Gaurav | Technical | 29 | 9.4.2.318 | 1 | Althougth there is a definition of 'measurement ID' in Clause 3, it by itself is not enough for the element description in Subclause 9.4.2.x . Here in 9.4.2.318 there has to be more detailed description of the same. Atleast mentioning what form it contains, eg: A string with alphanumeric characters, etc. If not specific text, then a note would also suffice. Implementers need to know what to broadly expect in such fields. | Yes | as in comment | Jay Yang | 11-24/0895
3038 | 329974 | Patwardhan, Gaurav | Technical | 35 | 12.2.12.1 | 22 | Change “...unless the receiving STA...” to “...unless the intended receiver STA…” to make it clear | Yes | as in comment | Jay Yang | 11-24/0885 | Rejected | The "receiving STA” means it’s a determined STA. While “intended receiver STA” means it’s a potential receiver STA. The transmitter may broadcast the Device ID element if we walk on this direction. It does not align with current feature design. | 39 |  |  |  |  | Resolved
3039 | 329975 | Patwardhan, Gaurav | Technical | 35 | 12.2.12.1 | 29 | Change to “(Re)Association Request” frame. | Yes | as in comment | Jay Yang | 11-24/0885 | Rejected | According the to rule defined in 4.5.3.4 Reassociation.”The reassociation service is invoked to “move” a current association of a non-AP STA from one AP to another “ And “Reassociation also enables changing association attributes of an established association while the non-AP STA remains associated with the same AP." The above two cases are based on not losing connection with the ESS. While 11bh group intends to address the identification with RCM before association, and thus Reassocation is out of 11bh scope. | 39 |  |  |  |  | Resolved
3040 | 329976 | Patwardhan, Gaurav | Technical | 35 | 12.2.12.1 | 36 | Change to “(Re)Association Request” frame. | Yes | as in comment | Jay Yang | 11-24/0885 | Rejected | According the to rule defined in 4.5.3.4 Reassociation.”The reassociation service is invoked to “move” a current association of a non-AP STA from one AP to another “ And “Reassociation also enables changing association attributes of an established association while the non-AP STA remains associated with the same AP.” The above two cases are based on not losing connection with the ESS. While 11bh group intends to address the identification with RCM before association, and thus Reassocation is out of 11bh scope. | 39 |  |  |  |  | Resolved
3041 | 329977 | Patwardhan, Gaurav | Technical | 35 | 12.2.12.1 | 41 | Move the example to a note as it does not add anything of value to the normative language | Yes | as in comment | Jay Yang | 11-24/0885 | Revised | Remove the text in the parenthesis (in P35/41) | 39 |  |  |  |  | Resolved
3042 | 329978 | Patwardhan, Gaurav | Technical | 35 | 12.2.12.1 | 50 | Swap the order of paragraphs at L61 and L50 because the one at L61 is more specific and should come first and then L50 is a catchall for all other situations. Otherwise there is ambiguity in reading the text. | Yes | as in comment | Jay Yang | 11-24/0885 | Revised | At P35.50, replace “When an AP with dot11DeviceIDActivated equal to true receives a frame containing a device ID from a non-AP STA and the AP recognizes the received device ID, the AP shall perform one of the following Actions...” with “When an AP with dot11DeviceIDActivated equal to true receives a frame that is not a PASN frame, containing a device ID from a non-AP STA and the AP recognizes the received device ID, the AP shall perform one of the following actions..” | 39 |  |  |  |  | Resolved
3043 | 329979 | Patwardhan, Gaurav | Technical | 36 | 12.2.12.1 | 11 | Should be a stronger condition, i.e. a “shall” instead of a “may” considering the AP was not able to determine the non-AP STA’s identity | Yes | as in comment | Jay Yang | 11-24/0885 | Revised | Replace “may” with” shall” in P36L11 | 39 |  |  |  |  | Resolved
3044 | 329980 | Patwardhan, Gaurav | Editorial | 37 | 12.2.12.1 | 45 | Rename to Annex AF | Yes | as in comment | Carol Ansley | 11-24/952
3045 | 329981 | Patwardhan, Gaurav | Technical | 38 | 12.2.12.2 | 42 | For checking whether the IRM is already in use within the ESS a note needs to be added to the effect of “Mechanism to synchronize the storage of IRMs throughout an ESS is out of scope for this standard.” Alternatively, add this point to the Note 1 on the same page at L21. | Yes | as in comment | Graham Smith | 11-24/916
3046 | 329982 | Patwardhan, Gaurav | Technical | 38 | 12.2.12.2 | 53 | Remove the sentence “In so doing, the AP identifies the non-AP STA” as it provides no value here. | Yes | as in comment | Graham Smith | 11-24/916
3047 | 329983 | Patwardhan, Gaurav | Technical | 39 | 12.2.12.2 | 8 | Instead of “… and the IRM field is not present.”, it should be “… and the IRM field is present.” | Yes | as in comment | Graham Smith | 11-24/916
3048 | 329984 | Patwardhan, Gaurav | Technical | 39 | 12.2.12.2 | 18 | Remove the word ‘state’ at the end of the sentence as it changes the meaning of the sentence. | Yes | as in comment | Graham Smith | 11-24/916
3049 | 329985 | Patwardhan, Gaurav | Editorial | 39 | 12.2.12.2 | 23 | Typo. Should be “.. in an ESS” instead of “… in as ESS”. | Yes | as in comment | Carol Ansley | 11-24/952
3050 | 329986 | Patwardhan, Gaurav | Technical | 39 | 12.2.12.2 | 27 | Sentence does not read well. Reword to “A non-AP STA may use that address for active scanning for an AP in that ESS.” I think we have already established in the prior subclause text that the IRM is distributed to APs across the ESS. | Yes | as in comment | Graham Smith | 11-24/916
3051 | 329987 | Patwardhan, Gaurav | Editorial | 39 | 12.2.12.2 | 30 | Typo. Should be “AP(s)” | Yes | as in comment | Carol Ansley | 11-24/952
3052 | 329988 | Patwardhan, Gaurav | Editorial | 39 | 12.2.12.2 | 32 | The correct preposition is ‘for’ instead of ‘in’. The sentence would read as “… for each association..” | Yes | as in comment | Carol Ansley | 11-24/952
3053 | 329989 | Patwardhan, Gaurav | Editorial | 39 | 12.2.13 | 46 | Typo. It should be ‘… shall be used as derived a part of.. “ | Yes | as in comment | Carol Ansley | 11-24/952
3054 | 330045 | McCann, Stephen | Editorial | 35 | 12.2.12.1 | 15 | This is the first time that ESS is referenced in this clause | No | Change "the ESS" to "an ESS" | Carol Ansley | 11-24/952
3055 | 330046 | McCann, Stephen | Technical | 35 | 12.2.12.1 | 42 | The text "since the last association to the ESS", is incorrect as associations are between peer STAs. | Yes | Change the cited text to "since the last association to an AP in the ESS" | Jay Yang | 11-24/0885 | Revised | Remove the text in the parenthesis (in P35/41) | 39 |  |  |  |  | Resolved
3056 | 330047 | McCann, Stephen | Technical | 38 | 12.2.12.2 | 27 | The text "When associating or authenticating using PASN for the first time to an ESS", is incorrect as associations are between peer STAs. | Yes | Change the cited text to "When associating or authenticating using PASN for the first time to an AP in an ESS" | Graham Smith | 11-24/0916
3057 | 330048 | McCann, Stephen | Technical | 38 | 12.2.12.2 | 20 | I think it needs to be clarified within the note that the IRM is distributed throughout the APs in the ESS and not the ESS itself. | No | Change "distribute IRMs throughout the ESS" to "distribute IRMs throughout the APs in the ESS" | Graham Smith | 11-24/916 | Revised | At cited sentence change to “distribute IRMs to the APs in the ESS" And at 35.18 | [5 empty] | Ready for motion
3058 | 330049 | McCann, Stephen | Technical | 38 | 12.2.12.2 | 42 | I think it needs to be clarified that the IRM is used by APs within the ESS and not the ESS itself. | Yes | Change "If a newly provided IRM is already in use within the ESS" to "If a newly provided IRM is already in use by an AP of the ESS" | Graham Smith | 11-24/916 | [7 empty] | Discuss
3059 | 330050 | McCann, Stephen | Technical | 39 | 12.2.12.2 | 28 | I think it needs to be clarified that the IRM is used by APs within the ESS and not the ESS itself. | Yes | Change "A non-AP STA that has provided an IRM to an ESS" to "A non-AP STA that has provided an IRM to an AP within the ESS" | Graham Smith | 11-24/916
3060 | 330051 | McCann, Stephen | Editorial | 34 | 12.2.12 | 24 | TA (Transmission Address) requires an article. | No | Change "TA" to "a TA" at the cited location. Change "TA" to "the TA" at P34L25. | Carol Ansley | 11-24/952
3061 | 330052 | McCann, Stephen | Editorial | 34 | 12.2.12 | 36 | device ID requires an article. | No | Change "Device ID" to "The device ID" at the cited location. | Carol Ansley | 11-24/952
3062 | 330053 | McCann, Stephen | Editorial | 34 | 12.2.12 | 37 | The sentence "If an AP and a non-AP STA both have both IRM and device ID activated..." has a couple of typos. | No | Change the cited sentence to "If an AP and a non-AP STA have both an IRM and a device ID activated...". | Carol Ansley | 11-24/952
3063 | 330054 | McCann, Stephen | Editorial | 36 | 12.2.12.2 | 8 | The sentence "If an AP sets Device ID (sub)element or Device ID KDE with the Device ID Status field set to 1…" has a couple of typos. | No | Change the cited sentence to "In an AP, if the Device ID Status field in a Device ID (sub)element or Device ID KDE is equal to 1…." | Carol Ansley | 11-24/952
3064 | 330055 | McCann, Stephen | Editorial | 35 | 12.2.12.1 | 18 | In the 802.11 baseline the usual phrase is "out of scope of this standard". | No | Change "out of scope for this standard" to "out of scope of this standard" and also on P38L20. | Carol Ansley | 11-24/952
3065 | 330056 | McCann, Stephen | Editorial | 36 | 12.2.12.1 | 12 | I don't think quotes are required for Not Recognized. | No | Remove the quote marks around Not Recognized. | Carol Ansley | 11-24/952
3066 | 330057 | McCann, Stephen | Editorial | 39 | 12.2.12.2 | 11 | "recognized" should be capitialised. | No | Change "Not recognized" to "Not Recognized". | Carol Ansley | 11-24/952
3067 | 330058 | McCann, Stephen | Technical | 25 | 9.4.2.19.7 | 60 | Some of the "set to" statements are within conditionals and should be "equal to" | Yes | Change "set to" to "equal to", starting at the end of line 60. | Jay Yang | 11-24/0893
3068 | 330059 | McCann, Stephen | Technical | 26 | 9.4.2.19.7 | 1 | Some of the "set to" statements are within conditionals and should be "equal to" | Yes | Change "When included in a Beacon request with the Data field set to other than 1" to "When included in a Beacon request with the Data field not equal to 1". | Jay Yang | 11-24/0893
3069 | 330060 | McCann, Stephen | Editorial | 39 | 12.2.12.2 | 9 | Change the "set to" text in this sentence to make it clear. | No | Change "set to indicate Recognized" to "set to Recognized" | Carol Ansley | 11-24/952
3070 | 330061 | McCann, Stephen | Editorial | 39 | 12.2.12.2 | 10 | Change the "set to" text in this sentence to make it clear. | No | Change "set to indicate Not recognized" to "set to Not Recognized" | Carol Ansley | 11-24/952
3071 | 330063 | Montemurro, Michael | Technical | 18 | 4.5.4.10 | 14 | "To mitigate this sort of traffic …." could be improved. | Yes | Change "To mitigate this sort of traffic..." to "To mitigate traffic analysis and tracking…" | Graham Smith | 11-24/916 | Accepted | [6 empty] | Ready for motion
3072 | 330064 | Montemurro, Michael | Technical | 29 | 9.4.2.319 | 3 | Given that this encrypted data element could be used for other purposes in the future, let's drop the PASN | Yes | Change "PASN Encrypted Data element" to "Encrypted Data element" throughout. Locations are: 24.26, 24.38, 29.3, 29.15, 29.21, 29.26, 29.44, 39.37, 39.41, 39.58, 44.25, 44.26, 44.27, 44.32, 44.33, 44.34, 44.60, 44.61, 44.52, 44.64 | Graham Smith | 11-24/0968
3073 | 330065 | Montemurro, Michael | Technical | 34 | 12.2.12 | 31 | Both mechanisms require the dot11PrivacyActivated is equal to true. Otherwise the device uses its universal MAC address. | Yes | At 34.30, insert the following sentences at the beginning of the paragraph: "MAC privacy enahancements is required in order to use the device ID mechanism or the IRM mechanism. non-AP STA shall set dot11PrivacyActivated equal to true to use either of these mechanisms." | Graham Smith | 11-24/916
3074 | 330066 | Montemurro, Michael | Technical | 35 | 12.2.12.1 | 1 | "intends to use" should just be "uses" | Yes | At cited location, change "intends to use" to uses | Jay Yang | 11-24/0885 | Accepted |  | 39 |  |  |  |  | Resolved
3075 | 330067 | Montemurro, Michael | Technical | 36 | 12.2.12.1 | 5 | The MAC address is bound to the device ID, not the Address 2 field. | Yes | Change "the shared identity state with the AP or ESS (as per the concepts of 12.2.12) is now bound to the Address 2 field in the Association Request frame" to "the shared identity state with the AP or ESS (as per the concepts of 12.2.12) is now bound to the MAC Address in the Address 2 field in the Association Request frame" | Jay Yang | 11-24/0885 | Revised | Change the cited text to “the shared identity state with the AP or ESS (as per the concepts of 12.2.12) is now bound to the MAC address in the Address 2 field in the Association Request frame” | 39 |  |  |  |  | Resolved
3076 | 330068 | Montemurro, Michael | Technical | 36 | 12.2.12.1 | 20 | I know that this example shows an ESS, but with PASN AP1 and AP2, do not have to be infrastructure APs in an ESS. | Yes | Change "The example illustrates a non-AP STA performing PASN to establish FTM session(s) in an ESS containing AP1 and AP2." to "The example illustrates a non-AP STA performing PASN to establish FTM session(s) with AP1 and AP2. It is assumed that AP1 and AP2 have the capability to synchronize updates to the device ID for the non-AP STA." | Jay Yang | 11-24/0885 | Rejected | First, this is explicitly an example, so it doesn't need to cover all cases. Second, the TG has not discussed the sharing of an identity beyond the ESS, and that potentially raises privacy concerns. | 39 |  |  |  |  | Resolved
3077 | 330069 | Montemurro, Michael | Technical | 38 | 12.2.12.2 | 38 | The sentence looks to be specific to PASN, but I don't think it is. Also, there are restrictions on what MAC address can be used. | Yes | Change "When associating or authenticating using PASN for the first time to an ESS, the non-AP STA may use any MAC address." to "When associating to an AP in an ESS or authenticating using PASN for the first time, the non-AP STA may use any Local MAC address." | Graham Smith | 11-24/916
3078 | 330070 | Montemurro, Michael | Technical | 32 | 12.2.12.2 | 33 | Poor use of terminology | Yes | Change "… that IRM as its TA for any probes," to "that IRM as a TA for any Probe Request frames," | Graham Smith | 11-24/916 | Revised | Change "… that IRM as its TA for any probes," to "…that IRM as the TA for any Probe Request frames," Note to editor, P38.32 | [5 empty] | Ready for motion
3079 | 330071 | Montemurro, Michael | Technical | 38 | 12.2.12.2 | 42 | It's the new IRM. | Yes | Change "If a newly provided IRM" to "If a new IRM" | Graham Smith | 11-24/916
3080 | 330072 | Montemurro, Michael | Technical | 38 | 12.2.12.2 | 44 | If there's a duplicate, which STA should the AP send the Duplicate IRM frame to? | Yes | Change "the AP should send a Duplicate IRM frame (see 9.6.36.2) to the non-AP STA indicating to the STA that the provided IRM is a duplicate. The non-AP STA may then respond with a New IRM frame (see 9.6.36.3 ), which provides a new IRM to the AP." to "the AP should send a Duplicate IRM frame (see 9.6.36.2) to the non-AP STA that provided the new IRM indicating that the new IRM is a duplicate of another Local MAC address. The non-AP STA may then respond with a New IRM frame (see 9.6.36.3 ) to provide an updated new IRM to the AP." | Graham Smith | 11-24/916
3081 | 330073 | Montemurro, Michael | Technical | 38 | 12.2.12.2 | 42 | This set of requirements is silent of the use of IRM with FT. However I don't see why IRM cannot be used in FT initial Association. | Yes | Insert the following sentence after the first sentence of the paragraph at 38.55: "A non-AP STA may indicate the IRM mechanism is activated in an association request frame as part of an initial mobility domain association." | Graham Smith | 11-24/916
3082 | 330074 | Montemurro, Michael | Technical | 35 | 12.2.12.1 | 35 | There is no reason why a non-AP STA could not use Device ID as part of FT initial Association | Yes | Insert the following paragraph at 35.14. "A non-AP STA and AP with dot11DeviceIDActivated equal to true may use the device ID mechanism as part of an initial mobility domain association." | Jay Yang | 11-24/0885 | Rejected | The current text says “When not using PASN or FILS authentication, in the Device ID KDE in message 3 of the 4-way handshake ” already cover the case the commenter mentioned. No need further change. | 39 |  |  |  |  | Resolved
3083 | 330076 | Huang, Po-Kai | Technical | 34 | 12.2.12 | 26 | There has been confusions during offline discussion that IRM can be used to change MAC address during association. Although the description for the IRM specifies that it is used during the "next preassociaiton exchanges...", but I think the confusion is whether the "next" is applied to all the description. Suggest to add next for all the following descriptions. | Yes | change "during its next preassociation exchanges, PASN authentication, and/or association and associated exchanges with that AP." as "during its next preassociation exchanges, next PASN authentication, and/or next association and next associated exchanges with that AP." | Graham Smith | 11-24/916 | Accepted |  |  | Ready for motion |  |  |  | Ready for motion
3084 | 330276 | Thomas, Angela | Technical | 17 | 3.2 | 9 | The text "device identification (ID): [device ID]” implies that “ID” is an abbreviation for “identification”. However, “ID” does not seem to be in the abbreviation list of the base standard. Also, on P17L17, "measurement identifier (ID): [measurement ID]” implies that “ID” is an abbreviation for “identifier". | Yes | Specify that “ID” is an abbreviation for ‘identifier” and adjust these two definitions accordingly. | Graham Smith | 11-24/0968 | [7 empty] | Discuss
3085 | 330277 | Thomas, Angela | Technical | 17 | 3.2 | 13 | Per definition of IRM (“A MAC address that can be used by a non-access point (non-AP) station (STA) to identify itself to a network”), any MAC address that can be used by such a STA to identify itself to a network is (“by definition") an IRM. This definition is inconsistent with the draft. Note that a definition-like sentence in 12.2.12.2 (“"An IRM is a MAC address that is constructed from the locally administered address space.”) is also inadequately limited. In fact, given that the “R” in IRM stands for “random”, the concept of randomness should be included in the definition. | Yes | Create a definition with a meaningful limitation, including the requirement for randomness; e.g. : "A MAC address selected randomly from among the Administratively Assigned local identifiers specified in IEEE Std 802 and used by a non-access point (non-AP) station (STA) to identify itself to a network." | Graham Smith | 11-24/916 | Revised | Incoroproate the changes shown in 11-24/916r1 (https://mentor.ieee.org/802.11/dcn/24/11-24-0916-01-00bh-cids-on-irm.docx) for CID 3085 | [5 empty] | Ready for motion
3086 | 330278 | Thomas, Angela | Technical | 28 | 9.4.2.317 | 45 | The text indicates that the IRM field contains a MAC address, without limitation. In fact, only specific forms are permitted, per 12.12. It would be helpful to refer the reader to this fact. The same comment also applies elsewhere (e.g., P31L24). | Yes | Change to "The IRM field contains an IRM, as specified in 12.2.12.2, when sent from a non-AP STA to an AP." | Graham Smith | 11-24/916 | Rejected | The IRM is a MAC address and convention in clause 9 is to define the content of frame fields. The IRM MAC address form is specified in the operational procedures. | [5 empty] | Ready for motion
3087 | 330279 | Thomas, Angela | Editorial | 34 | 12.2.12 | 36 | Grammar problem in "prior to and while it is associated.” | No | Change to "prior to association and during associated state.” | Carol Ansley | 11-24/952
3088 | 330280 | Thomas, Angela | Technical | 38 | 12.2.12.2 | 24 | The paragraph "An IRM is a MAC address that is constructed from the locally administered address space. A non-AP STA should construct randomized IRMs according to IEEE Std 802-2014 and IEEE Std 802c-2017.” has several problems. | Yes | If the IRM is defined precisely in the definition section, then this sentence may be unnecessary. Alternatively, change to: “An IRM is selected randomly from among the Administratively Assigned local identifiers specified in IEEE Std 802.” See also comments targeted to P38L27 and P38L28 for additional changes proposed to this material. | Graham Smith | 11-24/916
3089 | 330281 | Thomas, Angela | Technical | 38 | 12.2.12.2 | 27 | The notion of a “first time” association or authentication is problematic. It seems clear that a such a circumstance should occur even if it’s not the first time; e.g., if the device has been fully reset, and probably in other cases as well. Those cases are not addressed in the draft. | Yes | Change “for the first time to an ESS, the non-AP STA” to “, a non-AP STA without an IRM that it has previously provided to the ESS”. See also comments targeted to P38L24 and P38L28 for additional changes proposed to this material.. | Graham Smith | 11-24/916
3090 | 330282 | Thomas, Angela | Technical | 38 | 12.2.12.2 | 28 | The text "the non-AP STA may use any MAC address” is problematic. Does it mean that any possible identifier that meets the conditions (e.g., per IEEE Std 802) to be used as an IEEE 802 MAC address is an eligible MAC address in this circumstance? For example, could it be a a multicast address? Could be be an EUI under an OUI assigned to an entity who does not condone this use? The answer to these questions needs to be “no”. | Yes | Join with the prior paragraph, using the resolution proposed in the comments targeted to P38L24 and P38L27, so that the first two sentence of the combined paragraph are replaced by: "When associating or authenticating using PASN, a non-AP STA without an IRM that it has previously provided to the ESS may use any IRM selected randomly from among the Administratively Assigned local identifiers specified in IEEE Std 802." | Graham Smith | 11-24/916
3091 | 330283 | Thomas, Angela | Technical | 39 | 12.2.12.2 | 21 | As mentioned in the comment targeted to P38L27, the concept of “initial” should be generalized. | No | Revise accordingly. | Graham Smith | 11-24/0968
3092 | 330284 | Thomas, Angela | Technical | 39 | 12.2.12.2 | 21 | The text “would ignore that” is non-normative, which is appropriate given its location within a note. But is there a normative statement elsewhere specifying this behavior? | No | Revise accordingly. | Graham Smith | 11-24/0968 | [7 empty] | Discuss
3093 | 330285 | Thomas, Angela | Technical | 39 | 12.2.12.2 | 32 | The text “ought to” is not typically used in IEEE standard. It appears to be intended to mean “should”. Such text should be within a normative paragraph, not in a note. Also, consider the overlap with P38L29 ("Each time the non-AP STA associates with an AP in an ESS, it may provide a new IRM to the AP during association.”), which uses the very weak word “may" . | Yes | Revise accordingl; e.g., change NOTE 3 to: "Changing the IRM in each assocaition or PASN preassociation conttributes to privacy enhancement." | Graham Smith | 11-24/0968
3094 | 330286 | Rannow, R K | Technical | 34 | 12.2.12 | 38 | The Note starting on line 35 is ambiguous: The IRM mechanism and the device ID mechanism are independent. IRM allows an AP to recognize a non-AP STA prior to and while it is associated. Device ID allows an AP to identify a non-AP STA while it is associated. A device ID is allocated by an AP, and an IRM is selected by a non-AP STA. If an AP and a non-AP STA both have both IRM and device ID activated, the non-AP STA might provide both an IRM and a device ID during association or PASN authentication.[262,107, 36, 230] | No | The IRM mechanism and the device ID mechanism are independent. IRM allows an AP to recognize a non-AP STA prior to and while it is associated. Device ID allows an AP to identify a non-AP STA while it is associated. A device ID is allocated by an AP, and an IRM is selected by a non-AP STA. If an AP and a non-AP STA both have the IRM and device ID activated, the non-AP STA may provide an IRM and a device ID during association or PASN authentication. | Graham Smith | 11-24/916 | Rejected | It's a Note, hence "might" not "may" | [5 empty] | Ready for motion
3095 | 330329 | Rolfe, Benjamin | Technical | 39 | 12.213 | 61 | "If the Encrypted Data field uses an AEAD cipher, the Encrypted Data field shall not be padded and the AAD for the encipherment operation shall not be used and the number of AAD components is zero" Based upon my (limited) understanding of AEAD cipher (that it is a stream cipher), this is a statement of fact, not a normative statement - no padding is used with stream ciphers. Also the second part is poorly specified (using "shall not") | Yes | Change to: If the Encrypted Data field uses an AEAD cipher, the Encrypted Data field need not be padded. The number of AAD components shall be zero. | [9 empty] | Discuss
3096 | 330330 | Rolfe, Benjamin | Technical | 34 | 12.2.12 | 21 | "A may then report back to the AP during a future association or PASN authentication" is a rather vague statement of a requirement, which I think is meant to be an informative, not normative, statement. This appears to be stating a possibility, not an optional requirement (in which case some additional information is needed to implement the option). In this case "will" is more correct as that is how this first scheme is intended to work. | Yes | change "may" to "will" | Graham Smith | 11-24/916 | Rejected | It's not compulsary. It's optional. Hence "may" is correct. | [5 empty] | Ready for motion
3097 | 330331 | Rolfe, Benjamin | Technical | 34 | 12.2.12 | 9 | This looks like incorrect use of "may" (an optional requirement). It seems to be stating an objective for this clause. | Yes | Delete sentence. Change first sentence of next paragraph to "When a non-AP STA is randomly changing it's MAC address while not associated (see 4.5.4.10 (MAC privacy enhancements)) this presents a problem for the network in that it is unable to identify a non-AP STA that previously associated and is not able to apply cached information (“shared identity state”) from the previous association to the current association (see 12.2.10). | Graham Smith | 11-24/916
3098 | 330332 | Rolfe, Benjamin | Technical | 52 | AF.4 | 32 | Use of normative language ("should") in an informative clause. | Yes | change to: A new opaque identifier is generated with a pad length that differs from the pad length of the previously wrapped identifier. | Graham Smith | 11-24/0968
3099 | 330333 | Rolfe, Benjamin | Technical | 51 | AF.1 | 25 | Use of normative language in an informative clause ("may"). | Yes | "This annex provides an example scheme for generating opaque identifiers suitable for use in the Device ID field of the Device ID element" | Graham Smith | 11-24/0968
3100 | 330334 | Rolfe, Benjamin | Technical | 48 | B | 64 | Normative language ("may") in a footnote (which are informative). Yes, this one is all over 802 standards. Sign. Here's the same suggestion I've made to other groups for other standards. | Yes | change to: " Copyright release for PICS proforma: Users of this standard are granted permission to freely reproduce the PICS proforma in this annex so that it can be used for its intended purpose. Permission is further granted to publish the completed PICS. | Graham Smith | 11-24/0968
3101 | 330335 | Hamilton, Mark | Technical | 31 | 11.10.9.1.1 | 62 | [XG] Why RA (Address 1) in the Probe Request can be an IRM? It should be TA. | Yes | Change to "the Address 2" | Jay Yang | 11-24/0895
3102 | 330336 | Hamilton, Mark | Editorial | 38 | 12.2.12.2 | 30 | Missing space after full stop. | No | Insert a space. | Carol Ansley | 11-24/952
3103 | 330337 | Hamilton, Mark | Technical | 38 | 12.2.12.2 | 30 | "The non-AP STA may then use that IRM as its TA the next time it requests association to any AP in that same ESS." This isn't entirely clear that it is trying to say the IRM is going to be used some time in the future. The next sentence is even worse. | Yes | Suggest adding "after it leaves the ESS (disassociates) and then the next time (some time later) when it returns and requests association to any AP in the same ESS, including Authentication and Association frames." Change the next sentence to "The non-AP STA may also use that IRM after it disassociated from the ESS, for any probes, directed or broadcast, or public Action frames sent to any AP in the ESS. | Graham Smith | 11-24/916
3104 | 330338 | Hamilton, Mark | Editorial | 46 | 12.13.7 | 14 | Spurious hyphen at start of paragraph | No | Delete the hyphen. | Carol Ansley | 11-24/952
3105 | 330339 | Hamilton, Mark | Editorial | 45 | 12.13.7 | 23 | NOTE needs an "M-dash" | No | Change hyphen to an "M-dash" | Carol Ansley | 11-24/952
3106 | 330340 | Hamilton, Mark | Technical | 45 | 12.13.7 | 17 | This "or" is ambiguous. | Yes | Change the phrase to "the AKMP is neither PASN AKMP nor PAS with defined key wrap AKMP" | Graham Smith | 11-24/0968
3107 | 330341 | Hamilton, Mark | Technical | 45 | 12.13.7 | 41 | Should this "and" be an "or", so the condition applies when dot11KEKPASNActivated is false? | Yes | Change "and" to "or" | Graham Smith | 11-24/0968
3108 | 330342 | Hamilton, Mark | Editorial | 46 | 12.13.7 | 47 | Extended Capabilities should be capitalized | Yes | Change "extended capabilties" to "Extended Capabilities" | Carol Ansley | 11-24/952
3109 | 330343 | Hamilton, Mark | Technical | 46 | 12.13.7 | 10 | "The Key ID in the PTKSA (see 12.6.1.1.6 (PTKSA)) resulting from PASN authentication shall be 3 0." It's either 3 or 0. | Yes | The correct text will need to be taken from the next REVme update (this is wrong in the baseline), and kept in synch. | Graham Smith | 11-24/0968 | [7 empty] | REVme baseline
3110 | 330344 | Hamilton, Mark | Technical | 39 | 12.2.13 | 57 | This text is not explicit about how many 0x00 octets are required. | Yes | Replace "zero or more 0x00 octets" with "a number of 0x00 octets such that the length of the Encrypted Data field is at least 16 octets and a muiltple of 8 octets. | Graham Smith | 11-24/0968
3111 | 330345 | Hamilton, Mark | Editorial | 37 | 12.212.1 | 45 | "Annex AD" should be "Annex AF", and use a hot link. | Yes | Fix the xref spelling, and make a hot link | Carol Ansley | 11-24/952
3112 | 330346 | Hamilton, Mark | Technical | 25 | 9.4.2.1 | 27 | Measurement ID element (which does go in Probe Request, for example) has no Element ID (and the other attributes) in 9.4.2.1. | Yes | Insert a row after the IRM row, with: Measurement ID (9.4.2.318), 255, 140, No, No. Change PASN Encrypted Data row to ID extension of 141. | Jay Yang | 11-24/0893
3113 | 330347 | Hamilton, Mark | Technical | 27 | 9.4.2.316 | 63 | Neither "device ID" nor "measurement ID" are ever specified. | Yes | Add to the end of the sentence, "that is a sequence of up to xxx octets". (Need to choose what xxx is.) Same thing at 29.1. | Jay Yang | 11-24/0893
3114 | 330348 | Hamilton, Mark | Technical | 35 | 12.2.12.1 | 22 | If this is an element (or subelement) name, then it is capitalized | Yes | Change "device ID" to "Device ID" | Jay Yang | 11-24/0885 | Accepted |  | 39 |  |  |  |  | Resolved
3115 | 330349 | Hamilton, Mark | Editorial | 41 | 12.7.6.1 | 59 | Need to restructure EAPOL-Key PDU messages into REVme's new style | Yes | Replace the list of combinations with the bracketed style for optional fields, per REVme | Carol Ansley | 11-24/952 | [7 empty] | REVme baseline
3116 | 330350 | Hamilton, Mark | Editorial | 31 | 11.3.3 | 38 | "Unicast SA Query" is not the correct quote from the baseline. | Yes | Change "Unicast SA Query" to "SA Query Request and SA Query Response frames sent to an individual address" | Carol Ansley | 11-24/952
3117 | 330351 | Hamilton, Mark | Editorial | 41 | 12.7.3 | 11 | Table row for "00-0F-AC:21" should have "N/A" with strikethrough in the cells with new text added. | Yes | Per comment. | Carol Ansley | 11-24/952
3118 | 330352 | Hamilton, Mark | Editorial | 41 | 12.7.3 | 3 | Cleanup editing instructions | Yes | Change Editor's instructions to "Modify and add the follow rows…". Have all the text in the 00-0F-AC:26 row with underscore. | Carol Ansley | 11-24/952
3119 | 330353 | Hamilton, Mark | Editorial | 45 | 12.13.7 | 41 | The field name is "KEK in PASN" (no "the") | Yes | Delete "the" in "KEK in the PASN field" | Carol Ansley | 11-24/952
3120 | 330354 | DeLaOlivaDelgado, Antonio | Technical | 18 | 4.5.4.10 | 14 | We mention in this clause a summary of IRM and device ID, should not we say something about the measurement ID? | No | Add a phrase describing also the operation of the measurement ID. | Antonio de la Oliva | 11-24/904 | Revised | Revise: Modify paragraph: To mitigate this sort of traffic analysis a STA can support the ability to periodically and randomly change its MAC addresses and reset counters and seeds prior to association. Such a STA, upon reconnecting to a network, can provide either a device ID previously provided by the network or can use an identifiable random MAC address (IRM) the STA previously provided to the network or both. Either approach allows the network to recognize the STA while providing protection against third party tracking or traffic analysis. While discovering networks, a STA can refrain from gratuitously transmitting Probe Request frames containing SSIDs of favored BSS networks. [212, 45, 68, 52, 87, 213, 200, 201, 279, 202] With: To mitigate this sort of traffic analysis a STA can support the ability to periodically and randomly change its MAC addresses and reset counters and seeds prior to association. Such a STA, upon reconnecting to a network, can provide either a device ID previously provided by the network or can use an identifiable random MAC address (IRM) the STA previously provided to the network or both. Such a STA can also use a measurement ID, previously provided by the network, to assist while performing beacon report measurement procedures. These mechanisms [3120] allow the network to recognize the STA while providing protection against third party tracking or traffic analysis. While discovering networks, a STA can refrain from gratuitously transmitting Probe Request frames containing SSIDs of favored BSS networks. [212, 45, 68, 52, 87, 213, 200, 201, 279, 202] Editor, in definition of measurement ID please do the following change: measurement identifier (ID): change "radio measurement procedure" to "beacon report measurement procedure" | [5 empty] | Ready for motion
3121 | 330355 | DeLaOlivaDelgado, Antonio | Technical | 19 | 6 | 1 | In clause 6 there is the MLME-MREQUEST SAP which if I am not wrong specifies the measurement request, should not we have the measurement ID in any of the SAPs? is this something that does not need to be exchanged within any SAP? | No | Please check if any of the SAPs requires inclusion of the measurement ID as in the case of the IRM and deviceID. | Antonio de la Oliva | 11-24/931
3122 | 330356 | DeLaOlivaDelgado, Antonio | Technical | 28 | 9.4.2.317 | 16 | The IRM status length is 0 or 1, for coherence we should have the same as in the status of device ID, which is always present but reserved in one direction. | No | Either change device ID Status length to 0 or 1 (and say it is not present) or change IRM status to 1 and indicate it is reserved. | Antonio de la Oliva | 11-24/931
3123 | 330357 | Lalam, Massinissa | Editorial | 29 | 9.4.2.319 | 44 | Replace "The format of the PASN Encrypted Data element is shown in Figure 9-1072e (Device ID subelement format)." with "The format of the PASN Encrypted Data element when Subelement ID equals Device ID is shown in Figure 9-1072e (Device ID subelement format)." | Yes | As in comment | Carol Ansley | 11-24/952
3124 | 330358 | Lalam, Massinissa | Editorial | 29 | 9.4.2.319 | 63 | Replace "The format of the IRM subelement is shown in Figure 9-1072f (IRM subelement format)." with "The format of the PASN Encrypted Data element when Subelement ID equals IRM is shown in Figure 9-1072f (IRM subelement format)." | Yes | As in comment | Carol Ansley | 11-24/952
3125 | 330359 | Lalam, Massinissa | Editorial | 34 | 12.2.12 | 30 | Replace "The two mechanisms both allow the network […]" with "The two mechanisms allow the network […]" | No | As in comment | Carol Ansley | 11-24/952
3126 | 330360 | Lalam, Massinissa | Editorial | 34 | 12.2.12 | 38 | Consider replacing the sentence in NOTE 1 "If an AP and a non-AP STA both have both IRM and device ID activated, the non-AP STA might provide both an IRM and a device ID during association or PASN authentication" with "If both an AP and a non-AP STA have IRM and device ID activated, the non-AP STA might provide both an IRM and a device ID during association or PASN authentication" | No | As in comment | Carol Ansley | 11-24/952
3127 | 330361 | Lalam, Massinissa | Technical | 35 | 12.2.12.1 | 25 | "If a non-AP STA has a device ID configured, then it shall provide a device ID using the procedures described below" seems to indicated the non-AP STA must transmit its device ID. Also I don't know what is "a device ID configured". Maybe rephrase such as: "If a non-AP STA that has dot11DeviceIDActivated equal to true wants to provide a stored device ID, then it shall provide the devide ID using the procedures described below" | Yes | As in comment | Jay Yang | 11-24/0885 | Revised | Change the cited text to “If a non-AP STA has been provided a device ID, then it may provide that device ID. When it provides the device ID, then it shall use the procedures described below” | [5 empty] | Ready for motion
3128 | 330362 | Lalam, Massinissa | Technical | 35 | 12.2.12.1 | 34 | Replace "An AP shall provide a device ID using the procedures described below" with "An AP that has dot11DeviceIDActivated equal to true shall provide a device ID using the procedures described below" | Yes | As in comment | Jay Yang | 11-24/0885 | Rejected | The current draft already has text “A STA should not send a frame containing a device ID (sub)element to any STA unless the receiving STA sets the Device ID Active field to 1 in the Extended RSN Capabilities field”. No need to duplicate the condition in every sentence. | [5 empty] | Ready for motion
3129 | 330363 | Lalam, Massinissa | Editorial | 40 | 12.7.2 | 1 | Remove the extra closing bracket in "12.7.2 EAPOL-Key frames)" | No | As in comment | Carol Ansley | 11-24/952
3130 | 330364 | Lalam, Massinissa | Editorial | 51 | AF | 18 | Consider renaming "(informative) Example opaque device identifier scheme" as "(informative) Example of an opaque device identifier scheme" | No | As in comment | Carol Ansley | 11-24/952
3131 | 330368 | Mutgan, Okan | Technical | 37 | 12.2.12.1 | 42 | Draw example figures of the signaling for IRM and device ID, preferably each mechanism with identifier recognized or not recognized. (Previous letter ballot consists of several comments that are not completely clear about the signaling procedures) | No | As in comment. | Okan Mutgen | 11-24/0898 | Revised | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0898-01-00bh-sa-cr-for-cid3131.docx. | [5 empty] | PASN ID updates needed (11-24/0789)
3132 | 330369 | Mutgan, Okan | Technical | 39 | 12.2.13 | 38 | "Section 12.2.13 Encryption of the Encrypted Data field in the PASN Encrypted Data element in PASN seems to fit under the PASN subclause better (12.13 Preassociation security negotiation). Move this subsection to PASN subclause (12.13 Preassociation security negotiation) and add a different subsection or note here simply saying that ""When using PASN authentication, device ID element and IRM element should be carried in the Encrypted Data field of the PASN Encrypted Data element shall be encrypted in the second PASN frame (if present) and in the third PASN frame (if present), as defined in 12.13.X Encryption of the Encrypted Data field in the PASN Encrypted Data element in PASN""" | No | As in comment. | Okan Mutgen | 11-24/0918 | Revised | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0918-01-00bh-sa-cr-for-cid3132.docx | 39 |  |  |  |  | Resolved
3133 | 330370 | Harkins, Daniel | Technical | 35 | 12.2.12.1 | 30 | Passing the Device ID in message 3 of the 4-way handshake is too late. The device has already authenticated and to properly authenticate a device its identiy must be determined already. | Yes | add the Device ID to associate requests and responses even when you're not doing FILS. When this is done it will also be necessary to make Annex AF normative and move it into section 12. | Jay Yang | 11-24/0885 | Rejected | This topic is already discussed many times, and The group have run a motion “ Motion #29: CIDs 239, 243, 242 Approve resolution of CID 239, 243, 242 with Revised: Incorporate the changes in 11-24/0068r1. Moved: Dan Harkins Second: Stuart Kerry Result: Yes: 8, No: 19, Abstain: 12 (Motion fails)” The group does not reach consensus on this direction. | [5 empty] | Ready for motion
3134 | 330371 | Harkins, Daniel | Technical | 36 | 12.2.12.1 | 2 | what does the non-AP STA do with this binding?It assumes there's a binding…but what does it do with that knowledge? How does it use this binding? | Yes | define what the binding implies and how knowledge of the binding is used or get rid of the paragraph | Mark Hamilton
3135 | 330388 | RISON, Mark | Editorial | 39 | 12.2.13 | 45 | "PASN Encrypted Data , the KEK shall be used" should not have a space before the comma | Yes | As it says in the comment | Carol Ansley | 11-24/952
3136 | 330389 | RISON, Mark | Editorial | 45 | 12.13.7 | 38 | "a KEK and a KDK are derived" wrong verb | Yes | Change "and" to "and/or" | Carol Ansley | 11-24/952
3137 | 330390 | RISON, Mark | Technical | 51 | AF.2 | 57 | "The maximum amount of padding is determined by the size of identifier being padded and the value of n, and is equal to 237 minus the sum of the length of the identifier and n. " -- it is not clear where 237 comes from. Also, units are missing but assuming 237 is in octets then there seems to be a dimension error since n is in bits, although it is only defined later on in the subannex | Yes | Change to "Any amount of padding can be added, as long as the resulting opaque identifier can fit in the Device ID element (in the Device ID field thereof)."
3138 | 330391 | RISON, Mark | Editorial | 25 | 9.4.2.19.7 | 60 | "with a Length field set to 1" should be "with the Length field set to 1" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3139 | 330392 | RISON, Mark | Editorial | 31 | 11.10.9.1.1 | 50 | " measurement request is Active" should be " Measurement request is Active" | Yes | As it says in the comment. Ditto at 32.25 | Jay Yang | 11-24/0895
3140 | 330393 | RISON, Mark | Editorial | 31 | 11.10.9.1.1 | 62 | "measurement request" should be "Measurement request" | Yes | As it says in the comment | Jay Yang | 11-24/0895
3141 | 330394 | RISON, Mark | Editorial | 32 | 11.10.9.1.1 | 17 | "measurement request" should be "Measurement request" | Yes | As it says in the comment | Jay Yang | 11-24/0895
3142 | 330395 | RISON, Mark | Editorial | 17 | 3.2 | 9 | "a device ID" is not defined. CID 105's resolution claims "device ID" is defined in 3.2, but 3.2 defines "device identification" not "device identifier" | Yes | I'm not sure whether we're allowed to have a single term expand to two things. If we are, then extend the definition of "device ID" to cover "device identifier" too | Carol Ansley | 11-24/952
3143 | 330396 | RISON, Mark | Editorial | 17 | 3.2 | 16 | "(ID):" should be emboldened | Yes | As it says in the comment | Carol Ansley | 11-24/952
3144 | 330397 | RISON, Mark | Editorial | 35 | 12.2.12.1 | 22 | "device ID (sub)element" should be "Device ID (sub)element" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3145 | 330398 | RISON, Mark | Technical | 35 | 12.2.12.1 | 27 | Why is a Device ID element included in the first PASN frame but a Device ID subelement included in the second one? | Yes | Make it a subelement in both cases | Jay Yang | 11-24/0885 | Revised | Device ID is a standalone element in the first PASN frame, while Device ID is a subelment in the PASN Encrypted Data element(for encryption reason). However, we found other place that is not consistent in P35L63. TGbh editor: change “Device ID element” to “Device ID subelement” in P35L63, | [5 empty] | Ready for motion
3146 | 330399 | RISON, Mark | Editorial | 35 | 12.2.12.1 | 22 | "unless the receiving STA sets the Device ID Active field to 1" -- "sets" should be "set" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3147 | 330400 | RISON, Mark | Technical | 35 | 12.2.12.1 | 42 | " some time has passed" -- not clear how much time some time is | Yes | Change to " an implementation defined amount of time has passed" | Jay Yang | 11-24/0885 | Revised | Remove the text in the parenthesis (in P35/41) | [5 empty] | Ready for motion
3148 | 330401 | RISON, Mark | Editorial | 34 | 12.2.12 | 13 | We don't normally define things using scare quotes. We define them by using italics | Yes | Change to use italics | Carol Ansley | 11-24/952
3149 | 330402 | RISON, Mark | Technical | 51 | AF.1 | 30 | It is not clear what "distinct ESSs" are. CID 187 rejected a change to "multiple ESSes" on the basis that "You can't know whether you have multiple objects unless you have a way of identifying distinct--i.e. recognizably different--instances of said object." | Yes | Add a definition of ESS distinctiveness | Graham Smith | 11-24/0968
3150 | 330403 | RISON, Mark | Editorial | 18 | 4.5.4.10 | 16 | "an identifiable" has two extraneous spaces | Yes | Delete two spaces (also in nearby words; also e.g. at 39.20) | Carol Ansley | 11-24/952
3151 | 330404 | RISON, Mark | Technical |  | 9.3.3 |  | Shouldn't the order numbers depend on the baseline? | Yes | Ensure no duplication or gaps | Graham Smith | 11-24/0968
3152 | 330405 | RISON, Mark | Editorial | 25 | 9.4.2.1 | 24 | "PASN Encrypted Data element" should not have the "element" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3153 | 330406 | RISON, Mark | Technical | 26 | 9.4.2.19.7 | 10 | "The Measurement ID element has the format defined in 9.4.2.315 (Measurement ID element). The Measurement ID element is optionally included in a Beacon request to request that the responding STA include the provided Measurement ID element in the Probe Request frames it transmits." -- but this is about the subelements of the Beacon request, so s/element/subelement/g I presume. However, the payload of the subelement has to be incldued in the probe requests as the payload of the element | Yes | As it says in the comment | Jay Yang | 11-24/0893
3154 | 330407 | RISON, Mark | Editorial | 26 | 9.4.2.23.3 | 37 | "00-0f-AC" should be "00-0F-AC" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3155 | 330408 | RISON, Mark | Editorial | 27 | 9.4.2.240 | 16 | "deriving KEK" should be "deriving a KEK" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3156 | 330409 | RISON, Mark | Technical | 27 | 9.4.2.313 | 40 | "The Device ID Length field is the length of the Device ID field" missing units | Yes | Add "in octets" | Jay Yang | 11-24/0893
3157 | 330410 | RISON, Mark | Editorial | 28 | 9.4.2.313 | 4 | "When the Device ID element is sent from a non-AP STA to an AP, the Device ID Status field is reserved." -- this should be immediately after the "When ... from AP to ..." para | Yes | As it says in the comment | Carol Ansley | 11-24/952
3158 | 330411 | RISON, Mark | Technical | 27 | 9.4.2.313 | 45 | "from an AP to a non-AP STA" -- "to a non-AP STA" is unnecessary verbiage | Yes | Delete the latter cited text | Jay Yang | 11-24/0893
3159 | 330412 | RISON, Mark | Technical | 28 | 9.4.2.313 | 4 | "from a non-AP STA to an AP" -- "from a non-AP STA" is unnecessary verbiage | Yes | Delete the latter cited text | Jay Yang | 11-24/0893
3160 | 330413 | RISON, Mark | Editorial | 28 | 9.4.2.314 | 37 | "Indicates that the IRM has not been recog- nized" -- weird word-break | Yes | Don't hyphenate | Carol Ansley | 11-24/952
3161 | 330414 | RISON, Mark | Technical | 29 | 9.4.2.316 | 6 | "The PASN Encrypted Data element contains an Encrypted Data field to be encrypted by the KEK" -- I don't understand what the future tense is about here. On the air it has been encrypted | Yes | Change to "The PASN Encrypted Data element contains an Encrypted Data field encrypted with the KEK" | Graham Smith | 11-24/0968
3162 | 330415 | RISON, Mark | Editorial | 29 | 9.4.2.316 | 60 | "Device ID status field" should be "Device ID Status field" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3163 | 330416 | RISON, Mark | Editorial | 30 | 9.4.2.316 | 12 | "The Length field is defined in 9.4.3." missing (Subelements) which makes me worry a xref is going to be missed | Yes | As it says in the comment | Carol Ansley | 11-24/952
3164 | 330417 | RISON, Mark | Editorial | 30 | 9.4.2.316 | 14 | "IRM status field" should be "IRM Status field" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3165 | 330418 | RISON, Mark | Editorial | 31 |  |  | 9.4.1.1.1 should be 9.4.1.11 (2x) | Yes | As it says in the comment | Carol Ansley | 11-24/952
3166 | 330419 | RISON, Mark | Editorial | 32 |  | 29 | "STA's Probe Request" should have a sexy apostrophe and have " frame" appended (2x) | Yes | As it says in the comment (also 2x at 45.9; also at 32.22) | Carol Ansley | 11-24/952
3167 | 330420 | RISON, Mark | Technical | 32 | 11.10.9.1.1 | 29 | "To enhance the privacy, the AP shall assign a new measurement ID for each measurement exchange." is ambiguous -- does it mean "if the AP wants to enhance the privacy, it shall" or does it mean "The AP shall (because doing so enhances privacy)" | Yes | Change "To enhance the privacy, the" to "The" | Jay Yang | 11-24/0895
3168 | 330421 | RISON, Mark | Editorial | 42 | 12.7.6.3 | 37 | "1 when using an AEAD cipher or if the Device ID KDE is included or 0 otherwise" would be better with a comma after "included" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3169 | 330422 | RISON, Mark | Editorial | 42 | 12.7.6.3 | 50 | "the conditions at 12.2.12.1" -- wrong preposition | Yes | Change at to in. Ditto at 43.4 | Carol Ansley | 11-24/952
3170 | 330423 | RISON, Mark | Editorial | 43 | 12.13.2 | 32 | "When PASN AKMP" missing article | Yes | As it says in the comment | Carol Ansley | 11-24/952
3171 | 330424 | RISON, Mark | Technical | 43 | 12.13.2 | 32 | "the AP with dot11KEKPASNActivated equal to true" is confusing | Yes | Change to "an AP that has dot11... equal to true" | Graham Smith | 11-24/0968
3172 | 330425 | RISON, Mark | Technical | 45 | 12.13.7 | 18 | "if the Base AKMP is PASN AKMP or PASN with defined key wrap" should be +" AKMP" | Yes | As it says in the comment | Graham Smith | 11-24/0968
3173 | 330426 | RISON, Mark | Technical | 44 | 12.13.3.2 | 59 | "ncluding a PASN Encrypted Data element and an IRM element as defined in 9.4.2.314 (IRM element) in the PASN Encrypted Data element" makes no sense: why would PASN Encrypted Data element be included in a PASN Encrypted Data element? | Yes | Delete "a PASN Encrypted Data element and" | Graham Smith | 11-24/0968
3174 | 330427 | RISON, Mark | Editorial | 45 | 12.13.7 | 19 | "PASN with defined key wrap" missing " AKMP" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3175 | 330428 | RISON, Mark | Editorial | 45 | 12.13.7 | 15 | "where," shouldn't have a comma | Yes | As it says in the comment | Carol Ansley | 11-24/952
3176 | 330429 | RISON, Mark | Editorial | 46 | 12.13.7 | 14 | "in PASN field" should be "in the PASN field" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3177 | 330430 | RISON, Mark | Editorial | 45 | 12.13.7 | 41 | "KEK in the PASN field" -- field name does not have "the" | Yes | Delete the "the" (and change "in" to "In") | Carol Ansley | 11-24/952
3178 | 330431 | RISON, Mark | Editorial |  |  |  | "KEK in PASN" should be "KEK In PASN" | Yes | Change throughout (3x) | Carol Ansley | 11-24/952
3179 | 330432 | RISON, Mark | Editorial | 46 | 12.13.7 | 36 | "in RSNE" should be "in the RSNE" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3180 | 330433 | RISON, Mark | Technical | 46 | 12.13.7 | 50 | "The Key ID in the PTKSA (see 12.6.1.1.6 (PTKSA)) resulting from PASN authentication shall be 0.[184]" -- isn't this incompatible with extended key IDs for individually addressed Data frames? | Yes | Clarify | Graham Smith | 11-24/0968
3181 | 330434 | RISON, Mark | Editorial | 51 | AF | 18 | "(informative) Example opaque device identifier scheme" formatting (font and lack of linebreak) seems incompatible with baseline | Yes | As it says in the comment | Carol Ansley | 11-24/952
3182 | 330435 | RISON, Mark | Editorial | 51 | AF.2 | 49 | "is 256" has two spaces | Yes | Delete one of them | Carol Ansley | 11-24/952
3183 | 330436 | RISON, Mark | Technical | 51 | AF.2 | 51 | It is not clear whether the amount of padding is itself required to be random | Yes | Clarify | [9 empty] | Discuss
3184 | 330437 | RISON, Mark | Editorial | 52 | AF.2 |  | "tweaked-padded-id" should be italicised (2x) | Yes | As it says in the comment | Carol Ansley | 11-24/952
3185 | 330438 | RISON, Mark | Editorial | 51 | AF.2 | 62 | "padded identifier" should be "padded-id" and italicised | Yes | As it says in the comment | Carol Ansley | 11-24/952
3186 | 330439 | RISON, Mark | Editorial | 52 | AF.2 | 7 | There should be more space before the para starting "The tweaked-padded-id I" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3187 | 330440 | RISON, Mark | Technical | 52 | AF.3 | 15 | "All APs in an ESS use the same tweak length for all opaque identifiers which are generated and parsed." -- how is this achieved? | Yes | Change to "All APs in an ESS need to use the same tweak length for all opaque identifiers that are generated and parsed." (uses definition of "need to" from REVme) | Graham Smith | 11-24/0968
3188 | 330441 | RISON, Mark | Technical | 52 | AF.3 | 23 | " If so, the unwrapped identity is passed up to the protocol using the scheme with an indication of success." -- and if not? | Yes | Presumably " the protocol using the opaque device identifier fails" | Graham Smith | 11-24/0968
3189 | 330442 | RISON, Mark | Editorial | 52 | AF.4 | 31 | "generate" should be "generates" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3190 | 330443 | RISON, Mark | Technical | 23 | 9.3.3.5 | 18 | "and dot11FILSActivated is true" -- why does FILS have to be activated to be able to use DID? | Yes | After the table add a "NOTE---Device ID and IRM elements are not included if dot11FILSActivated is not true because they are instead carried in the 4-way handshake." Ditto for next subclause
3191 | 330444 | RISON, Mark | Technical | 25 | 9.4.2.1 | 19 | Making the Device ID element non-extensible seems short-sighted to me. My understanding is that all elements defined after the extensibility column was added were expected to be extensible, for forward-compatibility | Yes | Change "No" in the penultimate column to "Yes" and add a Device ID Length field before the Device ID field in Figure 9-1072a--Device ID element format | Jay Yang | 11-24/0893
3192 | 330445 | RISON, Mark | Technical | 30 | 9.6.36.1 | 29 | "These frames are identified by the single octet IRM Action field, which follows immediately after the Category field." duplicates the figure and should be "An IRM Action field, in the field immediately after the Category field, differentiates the formats.". Baseline Subclause 1.4 talks of "references in this standard to a “<name> frame”, where <name> corresponds to an Action frame subtype identified by the octet immediately after the Category field (the <something> Action field identified in the subclauses of 9.6 (Action frame format details))" I accept that there are some "in the octet immediately after the Category field"s in 9.6 but I don't think we should make it any worse | Yes | As it says in the comment | Graham Smith | 11-24/0968
3193 | 330446 | RISON, Mark | Technical | 28 | 9.4.2.317 |  | There are two non-generic fields in this element. One is only used by APs, the other only by non-AP STAs. Wouldn't it be better two have two elements? | Yes | As it says in the comment | Jay Yang | 11-24/0893
3194 | 330447 | RISON, Mark | Technical | 37 | 12.2.12.1 | 44 | "(including nothing if the device ID is encrypted)" is confusing because in the example at least DIDs are always encrypted in Figure 12-0a when sent from the AP | Yes | As it says in the comment | Jay Yang | 11-24/0885 | [7 empty] | PASN ID
3195 | 330448 | RISON, Mark | Technical | 37 | 12.2.12.2 | 54 | "A non-AP STA that has dot11IRMActivated equal to true indicates the IRM mechanism is active by setting the IRM Active field to 1 in either the Extended RSN Capabilities field in (Re)Association Request frames or the first PASN frame that is sent to any AP that advertises activation of the IRM mechanism." is confusing because it suggests that if the STA wants to do it with PASN the AP has to advertise it, but if the STA wants to do it with extended caps the AP doesn't have to support it. Also the IRM Active field is always in ext caps so "either" is misplaced | Yes | Change to "A non-AP STA that has dot11IRMActivated equal to true indicates the IRM mechanism is active by setting the IRM Active field to 1 in the Extended RSN Capabilities field in either the (Re)Association Request frame or the first PASN frame that it sends to an AP that advertises activation of the IRM mechanism." and put para break before. Similarly at 34.61 | Graham Smith | 11-24/916
3196 | 330449 | RISON, Mark | Technical | 38 | 12.2.12.2 | 30 | "may then use that IRM as its TA" -- shouldn't it be more than a "may"? | Yes | Change to "shall use that IRM as its TA […] if it wants to be recognised". In the next sentence change "may also use" to "shall also use" and "that it may transmit" to "that it transmits" | Graham Smith | 11-24/916
3197 | 330450 | RISON, Mark | Technical | 36 | 12.2.12.2 | 2 | Don't all the "may"s in this para need to be shoulds or shalls? | Yes | More generally the following "may" look suspect to me: The following look suspect to me: it may proceed with the assumption [discussed elsewhere] An AP may set a Device ID Status field to 1 indicating “Not Recognized” if the AP cannot unequivocally identify the non-AP STA shared identity state. … that it may transmit … … may either continue to associate or authenticate using PASN to the AP and optionally provide a new IRM in an IRM KDE in message 4 of the 4-way handshake or, when using FILS authentication optionally provide an IRM element in the Association Request frame, or when using PASN authentication optionally provide an IRM element in the third PASN frame, else disassociate/ deauthenticate. An AP may set an IRM status field to 1 indicating Not Recognized if the AP cannot unequivocally identify the non-AP STA shared identity state. … such that the AP may identify the non-AP STA … such that APs in that ESS may identify the non-AP STA | Graham Smith | 11-24/916
3198 | 330451 | RISON, Mark | Editorial | 41 | 12.7.6.1 |  | TGme has reformulated this to put an end to the combinatorial explosion | Yes | Align with 11me | Carol Ansley | 11-24/952 | [7 empty] | REVme baseline
3199 | 330452 | RISON, Mark | Technical | 42 | AF.2 | 50 | How is n determined at both sides / negotiated? | Yes | Add a NOTE to explain that the non-AP STA does not need to know n, since it does not parse the opaque identifier, it merely passes it on to another AP | Graham Smith | 11-24/0968
3200 | 330453 | RISON, Mark | Technical |  | 12.2.12.1 | 46 | "may proceed with the assumption that the shared identity state with the AP or ESS (as per the concepts of 12.2.10) is now bound to the TA field in the Association Request frame" -- it is not clear what the implications/consequences of this assumption are | Yes | MarkH clarified that the intent was "It’s not that “something bad will happen”, but that something good (optimization) was hoped for, will not happen. The non-AP STA will not be recognized, and any state that had previously been established will need to be re-established. Or, in the case of this phrase, when things do work correctly, the AP and non-AP STA may proceed with the assumption that this state is still established, and they don’t need to take effort to re-establish it." so express that somehow | Mark Hamilton
3201 | 330454 | RISON, Mark | Editorial | 36 | 12.2.12.1 | 12 | We don't put scare quotes around identifiers/enum tags | Yes | Remove scare quotes | Carol Ansley | 11-24/952
3202 | 330455 | RISON, Mark | Editorial | 50 | C.3 |  | MIB should be ASCII-only | Yes | Change sexy double quotes to sexless ones | Carol Ansley | 11-24/952
3203 | 330456 | RISON, Mark | Editorial | 39 | 12.2.13 | 46 | "the PASN Encrypted Data " should be +"element" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3204 | 330457 | RISON, Mark | Editorial | 30 | 9.6.36.1 | 44 | An em dash is too big as a range indication | Yes | Use whatever the baseline uses (en dash?) Ditto other locations with ranges | Carol Ansley | 11-24/952
3205 | 330458 | RISON, Mark | Editorial | 37 | 12.2.12.1 | 49 | Double full stop | Yes | Delete one of them | Carol Ansley | 11-24/952
3206 | 330459 | RISON, Mark | Editorial | 37 | 12.2.12.1 | 48 | "or any procedure" doesn't make sense | Yes | Change to "or any other procedure" | Carol Ansley | 11-24/952
3207 | 330460 | RISON, Mark | Editorial | 39 | 12.2.12.2 | 32 | "can" is the correct way to say "is able to" | Yes | As it says in the comment | Carol Ansley | 11-24/952
3208 | 330461 | RISON, Mark | Editorial | 44 | 12.13.3.2 | 51 | That editorial note should not have had the "of" deleted, as it makes the sentence fragment non-grammatical | No | As it says in the comment | Carol Ansley | 11-24/952
3209 | 330462 | RISON, Mark | Technical | 51 | C.3 | 2 | "at the STA" seems superfluous (and not used for dot11DeviceIDActivated) | Yes | Delete the cited text | Graham Smith | 11-24/0968