## Summary Stats
CID RESOLUTION STATUS 2022-07-12 LB286 |  |  | 24-11/754r5
Comment Type | Ballot Total | MAY | JUN | JUL | AUG | SEP | OCT | NOV | TOTAL Motioned | PERCENTAGE
Technical | 72 | MAY: 42 | 42 | 58.3333
General | 9 | MAY: 8 | 8 | 88.8889
Editorial | 53 | MAY: 0 | 0 | 0
TOTAL | 134 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50
PLAN | JUL | AUG | SEP | OCT | NOV | DEC | JAN
Goal
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | TODO | IN_PROGRESS | EFFECTIVE TODO
Technical CIDS | 0 | 72 | 42 | 30 | 30 | 24 | 6
General CIDs | 0 | 9 | 8 | 1 | 1 | 1 | 0
Editorial CIDs | 0 | 53 | 0 | 53 | 53 | 53 | 0
Includes Withdrawn CIDs as Rejects

## CID Leaderboard
TECH CID Resolver | MAY | JUN | JUL | AUG | SEP | NOV | DEC | TOTAL Motioned | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Assaf Kasher | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Christian Berger | MAY: 22 | 22 | 25 | 3 | 0 | 0 | 0 | 3
Jonathan Segev | [7 empty] | 0 | 24 | 24 | 0 | 0 | 0 | 24
Ali Raissinia | MAY: 28 | 28 | 29 | 1 | 0 | 0 | 0 | 1
Shuling Feng | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Stephan Sand | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Dibakar Das | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Qi Wang | [7 empty] | 0 | 3 | 3 | 0 | 0 | 0 | 3
Steve Shellhammer | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 81 | 31 | 0 | 0 | 0 | 31 | 0
[8 empty] | NOT ASSIGNED | 0 |  |  |  | NET TODO= | 31
Negative likely indicates a duplicate resolution

## Motions
DB Action | DRAFT | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech IP | #Gen IP | #Ed IP | #Tech CIDs | #Gen CIDs | #Ed CIDs | CIDs/Text
MAY(M) | D2.0 | 202405-01 |  | 685r0 | Dibakar Das | Minutes | [6 empty] | TEXT KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
|  | 202405-02 |  | 899r1 | Dibakar Das | Minutes
|  | 202405-03 |  |  | Roy Want | Vice Chairs
|  | 202405-04 |  |  | Roy Want | Secretary
|  | 202405-05 |  | 787r2 | Ali Raissinia | Resolution |  |  |  | 14 | 1 |  | 2017, 2018, 2023, 2095, 2024, 2045, 2046, 2047, 2048, 2079, 2080, 2086, 2087, 2129, and 2130G (15 CIDS)
|  | 202405-06 |  | 788r2 | Ali Raissinia | Resolution |  |  |  | 7 | 6 |  | 2049G, 2067, 2069, 2073, 2074, 2085, 2090, 2100G, 2102G, 2123, 2124G, 2128G and 2131G (13 CIDs)
|  | 202405-07 |  | 785r4 | Christian Berger | Resolution |  |  |  | 10 |  |  | 2094, 2026, 2027, 2098, 2029, 2030, 2050, 2052, 2053 and 2058 (total of 10 CIDs)
|  | 202405-08 |  | 845r2 | Christian Berger | Resolution |  |  |  | 6 | 1 |  | 2057, 2062, 2063, 2108, 2109G, 2110 and 2111 (total of 7 CIDs)
|  | 202405-09 |  | 846r1 | Christian Berger | Resolution |  |  |  | 4 |  |  | 2068, 2101, 2103, and 2104 (total of 4 CIDs)
|  | 202405-10 |  | 944r1 | Christian Berger | Resolution |  |  |  | 1 |  |  | 2051 (total of 1 CID)
JUL(M) |  | 202407-0x |  | 951r1 | Jonathan Segev | Resolution | 10 | 1 |  |  |  |  | 2004, 2005, 2006, 2009, 2016, 2037, 2038, 2039G, 2043, 2044, 2055 (11 CIDs total)
|  | 202407-0x |  | 958r2 | Jonathan Segev | Resolution | 13 | [5 empty] | 2041, 2071, 2075, 2076, 2078, 2112, 2115, 2117, 2118, 2119, 2121, 2127, 2132 (13 CIDs total)
|  | 202407-0x |  | 966r4 | Ali Raissinia | Resolution | 1 | [5 empty] | 2056 (1 CID)
|  | 202407-0x |  | ? | Qi Wang | TODO | [6 empty] | 2106, 2134, 2060, 2061, 2133 (5 CIDs)
|  | 202407-0x |  | ? | Christian Berger | TODO | [6 empty] | 2003 (1 CIDs)
|  | 202407-0x |  | 1073r1 | Roy Want | Resolution |  |  | 53 |  |  |  | 53 Editorial CIDs (1073r1)
D3.0
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
TOTAL | [6 empty] | 24 | 1 | 53 | 42 | 8 | 0
TOTAL + SPs | [9 empty] | 66 | 9 | 53 | 128
TASK and TOTAL | [9 empty] | 72 | 9 | 53 | 134
TODO and TOTAL TODO | [9 empty] | 6 | 0 | 0 | 6
20
14

## ToDo Itemized
TECH/GENERAL CIDS TODO
| UNASSIGNED | Roy Want | Ali Raissinia | Qi Wang | Tianyu Wu | Assaf Kasher | Christian Berger | Jonathan Segev | Niranjan Grandhe
|  |  |  | 5 CIDS |  |  | 1 CID
TECH-TODO | 0
EDITORIAL CIDS TODO
Roy Want
ALL OTHERS
53 Editorials
TOTAL | 0 | 0 | 0