## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-24/1262r4
Venue Date: | July 2024
First Author: | Mark Hamilton (Ruckus/CommScope)
Subject: | IEEE 802.11bh LB274 comments
Full Date: | 2024-07-17
Author(s): | Name(s) | Mark Hamilton
| Company: | Ruckus/CommScope
Address
Phone:
Fax:
| email: | mark.hamilton2152@gmail.com
Abstract: | This document contains the comments received on P802.11bh Initial SA ballot, and any resolutions approved by 802.11 TGbh.

## Revision History
Revision | Date | Description
0 | 2024-07-14 | Initial revision. First recirculation SA (D5.0) Ballot comments
1 | 2024-07-14 | Added Notes for some CIDs, to be discussed on July 15 meeting
2 | 2024-07-15 | CIDs ready for motion: 4046, 4061, 4112, 4008. Updates (but not RFM) to 4003, 4002, 4009, 4113.
3 | 2024-07-16 | Updates for review/discussion on (Montreal) Tues PM1 (including revisit of CID 4008)
4 | 2024-07-17 | CIDs ready for motion from Montreal session Monday/Tuesday: 4003, 4000, 4001, 4008, 4009, 4054, 4055, 4108. CIDs 4002 and 4113 have general agreement, with off-line work needed on a Submission. All Editorial CIDs, except 4049, reviewed and Ready for motion. (11 of 51 Technical comments are RfM.)

## Comments
CID | Ballot Comment | Name | Category | Page | Subclause | Line | Comment | Must be Satisfied | Proposed Change | Assignee | Submission | Resolution Type | Resolution Text | Motion Number | Notes
4000 | 333484 | Yang, Jay | Technical | 56 | Annex AG | 22 | [On behalf of Yan Li]In the first part of figure AG-2, association response is not cipher text, because the PMKSA and PTKSA can't be generated until the EAP exchange and 4-HS complete.Therefore, the device ID and PASN ID can not be carried in the assoc response. | No | remove EAP exchange and 4-HS from the first part and optionally add clarification for the type of FILS auth(Public key with PFS) for auth frame of the first part | Okan Mutgan | 11-24/1274 | REVISED | Incorporate the changes shown in https://mentor.ieee.org/802.11/dcn/24/11-24-1274-02-00bh-sa-cr-for-some-cids.docx |  | Ready for motion
4001 | 333556 | Mutgan, Okan | Technical | 54 | Annex AG | 21 | Example text and figures for FILS do not match the current FILS procedure, therefore, need modifications. | No | Modify the text and figures for FILS (both for device ID and IRM) to match FILS procedure. | Okan Mutgan | 11-24/1274 | REVISED | Incorporate the changes shown in https://mentor.ieee.org/802.11/dcn/24/11-24-1274-02-00bh-sa-cr-for-some-cids.docx |  | Ready for motion
4002 | 333700 | Yang, Jay | Technical | 25 | 9.3.3.6 | 47 | [On behalf of Yan Li]the notes of PASN ID indicate PASN ID is only present if Device ID present,which can be interpreted as PASN ID should be mandatory if Device ID present.However, in clause 12 both of Device ID and PASN ID would be provided only in the case of initial connection and 'not recognized'case. There is no similar requirement for 'recognized'case. Please clarify it | No | as the comments | Jouni Malinen | 11-24/1301 |  |  |  | Submission Required
4003 | 333720 | Yang, Jay | Technical | 36 | 12.2.13 | 12 | Based on 11bh draft4.0, TGbe extends 11bh feature under MLO framework in 11be draft7.0. Meanwhile, there are several changes on the baseline text of 11bh, 11bh draft should synchronize all the changes made by 11be draft to avoid the inconsistence issue. | No | the commenter will make a contribution on this. | Jay Yang |  | REJECTED | The commenter is working with TGbe Editor to address the synchronization issue in 11be draft, there is no further change in 11bh draft |  | Ready for motion
4004 | 333742 | RISON, Mark | Editorial | 46 | 12.13.8 | 43 | "the Bits required" should be "the number of bits required" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4005 | 333743 | RISON, Mark | Editorial | 46 | 12.13.8 |  | I think that normally we say Hash not HASH (2x) | Yes | Change HASH to Hash throughout | Carol Ansley |  | REJECTED | The text with 'HASH' is baseline. |  | Ready for motion
4006 | 333744 | RISON, Mark | Technical | 46 | 12.13.8 | 44 | "whether a KEK and a KDK is are derived" -- as far as I can tell from later on on this page, a KDK is always derived, it's just the KEK that might not be | Yes | Change to "whether a KEK is derived" | Mark Hamilton |  |  |  |  | Discuss - "whether a KDK is derived" is in REVme baseline. Should we really remove that in 11bh?
4007 | 333745 | RISON, Mark | Editorial | 46 | 12.13.8 |  | KCK is expanded twice, KEK once, and all three of these are after their first use | Yes | Expand them once, at first use | Carol Ansley |  | REVISED | The out of order expansion is from the baseline, but the editor is directed to remove the second expansion in new TGbh text. |  | Ready for motion
4008 | 333746 | RISON, Mark | Technical | 53 | AF.2 | 8 | "The maximum amount of padding is determined by the size of the identifier being padded and the size of the tweak in octets and is equal to 231 minus the sum of the lengths of the identifier and the tweak (231 is 248, the largest Device ID possible, minus 1 for the pad length, and minus 16 for the encryption overhead)." -- it's not clear why the largest device ID possible is 248. Assuming the limit is from its inclusion in a Device ID KDE, the biggest possible Data field size in a KDE is 255-3-1 = 251 octets and then within this if there is a Device ID Status field the maximum Device ID field size is 250 octets. [The resolution to CID 3137 made no sense: "253 is largest body of an element but device ID eats up 5 more of those leaving 248 for a maximum device ID" -- the largest body of an element is 255 for a legacy element and 254 for an extended element, "device ID eats up 5 more" is huh, and "device ID eats up ... leaving 248 for a maximum device ID" is huh too.] | Yes | Change to "Any amount of padding can be added, as long as the resulting opaque identifier can fit in the Device ID element (in the Device ID field thereof)." | Mark Hamilton |  | REVISED | Incorporate the changes shown in https://mentor.ieee.org/802.11/dcn/24/11-24-1026-02-00bh-resolution-of-padding-cids.docx |  | Ready for motion
4009 | 333747 | RISON, Mark | Technical |  | 9 |  | A Device ID field appears in various structures, but its size is always given as variable. This means it is possible to end up with a device ID being passed in one structure (e.g. Device ID element) that then doesn't fit in another (e.g. Device ID KDE) | Yes | Restrict device IDs to a certain size, e.g. 240 octets | Mark Hamilton |  | REJECTED | The Device ID field can be the maximum size that will fit in the protocol constraints, which is an implied rule for all elements without an explicit statement. |  | Ready for motion
4010 | 333748 | RISON, Mark | Editorial | 38 | 12.2.13.1 | 57 | Scare quotes still present at 38.57. Also not sure what's going on at 51.36 with the red quotes | Yes | As it says in the comment | Carol Ansley |  | REVISED | Remove quotes at 38.57 and correct color at 51.36. |  | Ready for motion
4011 | 333749 | RISON, Mark | Technical | 52 | AF.1 | 35 | It is not clear what "distinct ESSs" are. CID 3149 admits that "802.11 ARC SC has spent considerable time wrestling with how to define unique ESSs, with little success." | Yes | Change to "multiple ESSs" | Mark Rison |  |  |  |  | Discuss
4012 | 333750 | RISON, Mark | General |  | 9.3.3 |  | Check order numbers with ANA | Yes | As it says in the comment | Carol Ansley |  | REJECTED | Order numbers were verified against the baseline REVmeD6.0. They are not ANA managed. |  | Ready for motion
4013 | 333751 | RISON, Mark | Technical | 28 | 9.4.2.19.7 | 13 | "The Measurement ID element has the format defined in Figure 9-1074c (Measurement ID element format). When the Measurement ID element is included in a Beacon request, it requests the responding STA include the provided Measurement ID element in the Probe Request frames the STA transmits.[3005, 3153]" still seems to confuse the element and the subelement, and the fact that it's the payload you carry in the probereq, not the subelement per se | Yes | As it says in the comment | Mark Rison |  |  |  |  | Discuss - element vs subelement
4014 | 333752 | RISON, Mark | Technical | 30 | 9.4.2.317 | 25 | "When the element is sent from an AP, the IRM Status field is defined in Table 9-417b (IRM Status field values).[3026]" -- not clear what it's set to otherwise | Yes | Add a sentence "When the IRM element is sent to an AP, the IRM Status field is not present." as for Device ID | Mark Rison |  |  |  |  | See P30.23
4015 | 333753 | RISON, Mark | Editorial | 33 | 9.4.2.320 | 1 | "Then the element" should be "When the element" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4016 | 333754 | RISON, Mark | Editorial | 31 | 9.4.2.319 | 17 | "(see (Insert the following new subclause after 12.13.10 (i.e. immediately before 12.14)))" is clearly broken. Also at 41.9 | Yes | As it says in the comment | Carol Ansley |  | REVISED | Correct the links |  | Ready for motion
4017 | 333755 | RISON, Mark | Editorial | 27 | 9.4.2.1 | 25 | "Data(see" missing space | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4018 | 333756 | RISON, Mark | Technical | 31 | 9.4.2.319 | 17 | "The Encrypted Data field contains one or more elements encrypted by the KEK" -- subelements, given the end of the para | Yes | Change "elements" to "subelements" | Mark Rison |  |  |  |  | Discuss - element vs subelement
4019 | 333757 | RISON, Mark | General |  |  |  | Change tracking is not accurate, e.g. I think the whole of the line at 46.1, and the NOTE at the bottom of the previous page, should be underlined | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4020 | 333758 | RISON, Mark | Technical | 47 | 12.13.8 | 2 | "the Encrypted Data field in the Encrypted Data element" should be "… in the PASN Encrypted Data element" | Yes | As it says in the comment | Mark Rison |  |  |  |  | Accept
4021 | 333759 | RISON, Mark | Editorial | 31 | 9.4.2.319 | 17 | "elements encrypted by the KEK" should be "… using the KEK" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4022 | 333760 | RISON, Mark | General |  |  |  | "is defined in 9.4.3." should be "is defined in 9.4.3 (Subelements)." (3x) to give it a better chance of being hyperlinkified when merged into the baseline | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4023 | 333761 | RISON, Mark | Editorial | 44 | 12.13.2 | 29 | "the AP with dot11KEKPASNActivated equal to true" -- not clear what "the AP" refers back to here | Yes | Change to "an AP…" | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4024 | 333762 | RISON, Mark | Editorial | 29 | 9.4.2.240 | 10 | "KEK In PASN" should be "KEK in PASN" here (rightmost cell) | Yes | As it says in the comment | Carol Ansley |  | REVISED | Change to: "…deriving a KEK when using PASN.." |  | Ready for motion
4025 | 333763 | RISON, Mark | Editorial | 52 | AF.2 | 56 | "ransom" should be "random" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4026 | 333764 | RISON, Mark | Editorial |  | AF |  | Sometimes, especially in AF, it's "opaque identifier", sometimes "opaque device identifier" | Yes | Pick one and use it throughout | Carol Ansley |  | REVISED | Update text to standardize on "opaque identifier". |  | Ready for motion
4027 | 333765 | RISON, Mark | Editorial | 53 | AF.3 | 39 | "opaque identity" should be "opaque identifier" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4028 | 333766 | RISON, Mark | Editorial | 53 | AF.3 | 41 | "opaque device identified" should be "opaque device identifier" | Yes | As it says in the comment | Carol Ansley |  | REVISED | Update text to standardize on "opaque identifier". |  | Ready for motion
4029 | 333767 | RISON, Mark | Technical | 30 | 9.4.2.318 | 48 | Like the Device ID element, the Measurement ID element should be extensible | Yes | As it says in the comment | Mark Rison |  |  |  |  | Discuss
4030 | 333768 | RISON, Mark | Technical |  | 9.3.3 |  | It is not clear why FILS has to be activated to be able to use DID | Yes | In 9.3.3.5/6, after the table add a "NOTE---Device ID and IRM elements are not included if dot11FILSActivated is not true because they are instead carried in the 4-way handshake." | Mark Rison |  |  |  |  | Accept
4031 | 333769 | RISON, Mark | Editorial | 39 | 12.2.13.2 | 20 | "fieldin" should be "field in" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4032 | 333770 | RISON, Mark | Technical |  | 9 |  | The IRM Active field in the RSNXE seems to have been renamed to IRM Support, but there are still references to an IRM Active field. Or are there two fields now, one to indicate support and one to indicate activation? I note the MIB attribute is still called dot11IRMActivated, not dot11IRMSupport | Yes | As it says in the comment | Robert Stacey |  |  |  |  | Support vs active
4033 | 333771 | RISON, Mark | Technical |  | AG |  | "Device ID Active field" -- no such field | Yes | As it says in the comment | Robert Stacey |  |  |  |  | Support vs active
4034 | 333772 | RISON, Mark | Technical | 39 | 12.2.13.2 | 59 | "The non-AP STA may also use that IRM as its TA for any Probe Request frames, directed or broadcast, public Action frames, Authentication frames, and (Re)Association frames that it may transmit when it intends to be identified." -- the modals seem wrong | Yes | Change to "The non-AP STA shall also use that IRM as its TA for any Probe Request frames, directed or broadcast, public Action frames, Authentication frames, and (Re)Association frames that it transmits when it intends to be identified." | Mark Rison |  |  |  |  | Discuss
4035 | 333773 | RISON, Mark | Technical |  | C.3 |  | dot11DeviceIDActivated is "the device ID mechanism is supported" but dot11IRMActivated is "the STA supports IRM operation". Either both should be active, or both should be passive | Yes | As it says in the comment | Mark Rison |  |  |  |  | Support vs active
4036 | 333774 | RISON, Mark | Editorial | 39 | 12.2.13.1 | 4 | "the procedure in Annex , or any other procedure" should be "the procedure in Annex AF, or any other procedure" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4037 | 333775 | RISON, Mark | General |  | AG |  | The figures in this annex have very poor resolution, and are not searchable | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4038 | 333776 | RISON, Mark | Editorial | 40 | 12.2.13.2 |  | "the IRM status field to 1" should be "the IRM Status field to 1" (2x). Also at 61.25 | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4039 | 333777 | RISON, Mark | Editorial | 40 | 12.2.13.2 | 34 | "If the AP recognizes the IRM used as the TA in the received frame(s) from the non-AP STA, the AP shall set the IRM Status field of the IRM KDE or IRM element to Recognized and the IRM field is not present. If the AP does not recognize the IRM, the AP shall set the IRM Status field of the IRM KDE or IRM element to Not Recognized and the IRM field is not present. " -- the IRM field absence is already specified in Clause 9 (and it reads wrong anyway) | Yes | Change to "If the AP recognizes the IRM used as the TA in the received frame(s) from the non-AP STA, the AP shall set the IRM Status field of the IRM KDE or IRM element to indicate Recognized. If the AP does not recognize the IRM, the AP shall set the IRM Status field of the IRM KDE or IRM element to indicate Not Recognized. " -- the IRM field absence is already specified in Clause 9 | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4040 | 333778 | RISON, Mark | Editorial | 40 | 12.2.13.2 | 42 | "The non-AP STA, on receipt of an IRM Status field of value 1," should be "The non-AP STA, on receipt of an IRM Status field of 1," | Yes | As it says in the comment | Carol Ansley |  | REVISED | Update text to "The non-AP STA, on receipt of an IRM Status field equal to 1,…" |  | Ready for motion
4041 | 333779 | RISON, Mark | Editorial | 53 | AF |  | 2**(n-2) does not need the parens since the superscript already indicates the precedence | Yes | Remove parens at 53.6/65 | Carol Ansley |  | REJECTED | Parentheses are added for clarity. |  | Ready for motion
4042 | 333780 | RISON, Mark | General |  |  |  | There are lots of hyphens. Hyphens are prohibited, except for some legacy ones | Yes | Replace all hyphens with spaces, except where permitted by the special legacy permission list | Carol Ansley |  | REJECTED | The commentor has not provided enough information to identify specific changes. Non-compliant hyphen use that was identified in the MDR was addressed. |  | Ready for motion
4043 | 333781 | RISON, Mark | Technical | 38 | 12.2.13.1 | 56 | Per the resolution of CID 3200, "a new shared identity" should be "a new shared identity state" | Yes | As it says in the comment | Mark Hamilton |  |  |  |  | Accept
4044 | 333782 | RISON, Mark | Technical | 39 | 12.2.13.2 | 20 | "The RSNXE with the IRM Support field equal to 1" -- this is already stated in the previous sentence | Yes | Delete "with the IRM Support field equal to 1" | Mark Rison |  |  |  |  | And combine into one sentence? But, see CID 4045 first.
4045 | 333783 | RISON, Mark | Technical | 39 | 12.2.13.2 | 20 | "The RSNXE […] is present in either (Re)Association Request frames or the first PASN frame that it sends to an AP that advertises support for the IRM mechanism." -- doesn't this duplicate Clause 9? | Yes | Delete the cited text | Mark Rison |  |  |  |  | Accept
4046 | 333784 | RISON, Mark | Technical | 17 | 3.2 | 25 | "preassociation security negotiation identifier (ID): [PASN ID] A device ID that a network can provide" should be "preassociation security negotiation identifier (ID): [PASN ID] An ID that a network can provide". Ditto change "A transient device" in previous definition to "An" | Yes | As it says in the comment | Jay Yang | 11-24/1271 | REJECTED | PASN ID and measurement ID are the variant of device ID used in PASN authentication and measurement procedure respectively. Further more, the current definition is clear and it can despicts their correlation |  | Ready for motion
4047 | 333785 | RISON, Mark | Technical | 17 | 3.2 |  | Some of the definitions are in terms of a "network", others are in terms of an "ESS" or APs therein. The same term should be used for all | Yes | As it says in the comment | Mark Hamilton |  |  |  |  | ESS
4048 | 333786 | RISON, Mark | Editorial |  |  |  | "PASN ID is only present [is/if] Device ID is present." (3x) should be "PASN ID is present if Device ID is present; otherwise not present." (note is/if typo in one location of the three) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4049 | 333787 | RISON, Mark | Editorial | 23 | 9.3.3.6 | 47 | "Specifies the PASN ID for the requesting STA. " -- yes, but how? Should say "The PASN ID element is present if…" | Yes | As it says in the comment | Jouni Malinen | 11-24/1301 |  |  |  | Reassign, address with 4002. Note correct reference is page 25.47.
4050 | 333788 | RISON, Mark | Editorial | 27 | 9.4.2.1 | 38 | Missing closing parenthesis | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4051 | 333789 | RISON, Mark | General | 28 | 9.4.2.23.3 | 38 | Suite type should be assigned by ANA. Ditto Extended RSN Capabilities field bits and KDE types | Yes | As it says in the comment | Carol Ansley |  | REVISED | Update to use KDE selectors of data type 20, 21 and 22. |  | Ready for motion
4052 | 333790 | RISON, Mark | Technical |  | 9.4.2.240 |  | It's not clear why IRM/Device ID Support are about whether something is "active", while KEK In PASN is about whether it's "support"ed. Can the latter be supported but not active? | Yes | Probably best to talk about active everywhere, since this is less ambiguous | Robert Stacey |  |  |  |  | Support vs active
4053 | 333791 | RISON, Mark | General |  |  |  | It would be better if CIDs were tagged with #, to avoid confusion with other numeric contexts, e.g. page numbers, constants | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4054 | 333792 | RISON, Mark | Technical | 31 | 9.4.2.319 | 18 | "The element format is defined in 9.4.3" well, no, 9.4.3 is about the subelement format | Yes | Refer to 9.4.2.1. instead | Carol Ansley |  | REVISED | Change element to subelement. |  | Ready for motion
4055 | 333793 | RISON, Mark | Technical | 31 | 9.4.2.319 | 18 | "subelement" has been changed to "element", but the rest of the para continues to refer to subelements | Yes | Revert the change | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4056 | 333794 | RISON, Mark | Editorial | 32 | 9.4.2.320 | 62 | "PASN ID status field" should be "PASN ID Status field" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4057 | 333795 | RISON, Mark | General |  | 11.3.3 |  | It's not just about inserting a new item anymore | Yes | As it says in the comment | Mark Rison |  | ACCEPTED |  |  | Ready for motion
4058 | 333796 | RISON, Mark | Editorial | 36 | 12.2.13 | 51 | "If both an AP and a non-AP STA have IRM and device ID activated" should be "If both an AP and a non-AP STA have both IRM and device ID activated" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4059 | 333797 | RISON, Mark | Editorial | 37 | 12.2.13.1 | 45 | "didn’t" should be "did not" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4060 | 333798 | RISON, Mark | Technical | 37 | 12.2.13.1 | 38 | "the AP shall provide both a device ID and a PASN ID using the procedure described below: 1) When using FILS authentication and the non-AP STA did not provide a device ID in the Device ID element in the Association Request frame, the AP shall provide a device ID in the Device ID ele-ment and a PASN ID in the PASN ID element in the Association Response frame. 2) When not using PASN or FILS authentication and the non-AP STA didn’t provide a device ID in the Device ID KDE in message 2 of the 4-way handshake, the AP shall provide a device ID in the Device ID KDE and a PASN ID in the PASN ID KDE in message 3 of the 4-way handshake." -- this is missing the cases of using PASN but not FILS, and the cases where the non-AP STA did provide a DID. Similarly for non-AP STA behaviour at the bottom of the page, and AP again on the next page | Yes | As it says in the comment | Mark Rison |  |  |  |  | Discuss - Check surrounding paragraphs?
4061 | 333799 | RISON, Mark | Technical | 37 | 12.2.13.1 | 56 | "If a non-AP STA has been provided a device ID and a PASN ID by an ESS" -- this is the only "by an ESS" I can find. In general things are provided by an AP | Yes | Delete "by an ESS" | Jay Yang | 11-24/1271 | REVISED | Change the cited text to “If a non-AP STA has been provided a device ID by an AP in an ESS, then it may provide that device ID when returning to that ESS” |  | Ready for motion
4062 | 333800 | RISON, Mark | Technical | 38 | 12.2.13.1 | 11 | "The value of PASN ID shall be random" -- it's just the ID that is random | Yes | Delete "value of " | Mark Rison |  |  |  |  | Accept
4063 | 333801 | RISON, Mark | Technical | 44 | 12.7.6.4 | 1 | "Additionally, may include a Device ID KDE and optionally a PASN ID KDE subject to the conditions in 12.2.13.1 (Device ID)." -- the "optionally" is already covered by the "may" | Yes | Delete "optionally" | Mark Rison |  |  |  |  | Accept (or CID 4064)?
4064 | 333802 | RISON, Mark | Technical | 44 | 12.7.6.4 | 1 | "Additionally, may include a Device ID KDE and optionally a PASN ID KDE subject to the conditions in 12.2.13.1 (Device ID)." -- the "optionally" is already covered by the "may" | Yes | Change to "Additionally, may include a Device ID KDE, subject to the conditions in 12.2.13.1 (Device ID)." and "Additionally, may include a PASN ID KDE." | Mark Rison |  |  |  |  | Accept (or CID 4063)?
4065 | 333803 | RISON, Mark | Editorial |  | 12.13 |  | "subclause" when followed by a number should be "Subclause" or omitted (4x) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4066 | 333804 | RISON, Mark | Editorial |  | 12.13.8 |  | "; see xxx" should be "(see xxx)" to minimise confusion (2x) | Yes | As it says in the comment | Carol Ansley |  | REJECTED | The text is baseline without the parenthese. The next text from TGbh does have parentheses. |  | Ready for motion
4067 | 333805 | RISON, Mark | Technical | 46 | 12.13.8 | 47 | "When dot11KEKPASNActivated is false or when dot11KEKPASNActivated is true and the KEK In PASN field in the RSNXE from the peer is 0" -- MIB attribute might be absent. Also precedence could be clearer | Yes | Change to "When dot11KEKPASNActivated is not true, or when dot11KEKPASNActivated is true and the KEK In PASN field in the RSNXE from the peer is 0" | Mark Hamilton |  |  |  |  | Accept
4068 | 333806 | RISON, Mark | Technical | 47 | 12.13.8 | 21 | "Extended Capabilities" should be "Extended RSN Capabilities field" | Yes | As it says in the comment | Mark Rison |  |  |  |  | Accept
4069 | 333807 | RISON, Mark | Technical | 47 | 12.13.11 | 39 | "To encrypt the Encrypted Data field of the PASN Encrypted Data element, the KEK, as derived from the PTK (see 12.13.8 (PTKSA derivation with PASN authentication)), shall be used with the negotiated key wrap algorithm to encrypt the Encrypted Data field of the PASN Encrypted Data element." is of the form "To do X, do Y to do X" | Yes | Change to "The KEK, as derived …" | Mark Rison |  |  |  |  | Accept
4070 | 333808 | RISON, Mark | Technical | 47 | 12.13.11 | 54 | "If the Encrypted Data field uses an AEAD cipher, the Encrypted Data field shall not be padded and the AAD for the encipherment operation shall not be used and the number of AAD components is zero. " not dlear -- the number of AAD components where, in what context? | Yes | As it says in the comment | Mark Rison |  |  |  |  | Discuss
4071 | 333809 | RISON, Mark | Editorial |  | AG |  | " in Beacons and Probe Responses" should be " in Beacon and Probe Response frames" or " in beacons and probe responses" (7x) | Yes | As it says in the comment | Carol Ansley |  | REVISED | Update phrases to "beacons and probe responses." |  | Ready for motion
4072 | 333810 | RISON, Mark | Editorial |  | AG |  | "Association Request" should be "Association Request frame" or lowercase. Ditto "Association Response" | Yes | As it says in the comment | Carol Ansley |  | REVISED | Update phrases to "association request" and "association response". |  | Ready for motion
4073 | 333811 | RISON, Mark | Technical |  | AG |  | It is not clear what a "FILS Association Request" is. Ditto "FILS Association Response" | Yes | Refer to a specific frame type | Mark Rison |  |  |  |  | Discuss
4074 | 333812 | RISON, Mark | Editorial |  | AG |  | "in Association Response" should be "in the Association Response" (2x) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4075 | 333813 | RISON, Mark | Editorial |  | AG |  | "device ID KDE" should be "Device ID KDE" (7x) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4076 | 333814 | RISON, Mark | Editorial |  | AG |  | "Non AP STA," should be "The non-AP STA," (2x) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4077 | 333815 | RISON, Mark | Editorial | 57 | AG | 20 | "its MAC" should be "its MAC address". Similarly "different MAC" should be "different MAC address" at 56.1 | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4078 | 333816 | RISON, Mark | Editorial |  | AG |  | "in first PASN frame" should be "in the first PASN frame" (2x) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4079 | 333817 | RISON, Mark | Editorial |  | AG |  | "4 way handshake" should be "4-way handshake" (2x) and also be "a" not "the" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4080 | 333818 | RISON, Mark | Editorial | 55 | AG | 58 | "includes Device ID element" should be "includes a Device ID element" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4081 | 333819 | RISON, Mark | Editorial |  | AG |  | "device ID element" should be "Device ID element" (2x) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4082 | 333820 | RISON, Mark | Editorial |  | AG |  | "the Status field" should be "the IRM Status field" (4x) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4083 | 333821 | RISON, Mark | Editorial | 60 | AG | 11 | "in IRM element" should be "in an IRM element" | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4084 | 333822 | RISON, Mark | Editorial |  | AG |  | "status field" should be "Status field" (2x) | Yes | As it says in the comment | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4085 | 333823 | RISON, Mark | Technical |  | AG |  | "AP/ESS" -- well, which is it? (5x) | Yes | I think ESS is probably better | Mark Hamilton |  |  |  |  | Discuss
4086 | 333824 | Hamilton, Mark | Technical | 22 | 6.5.7.3.2 | 37 | In MLME-ASSOCIATE.response and .confirm this is not the best wording: "Specifies the device ID (or PASN ID) for the requesting STA." It is really providing a "next time" device ID or PASN ID, not "the ID for the STA" (now), but the "ID the STA should use next time". Same thing in 9.3.3.6 for the Association Response frame carrying (FILS only) Device ID or PASN ID. | Yes | At the cited locations (MLME-ASSOCIATE.response and .confirm), change "the Device ID [or PASN ID] for the requesting STA" to "a new Device ID [or PASN ID] for the associating STA". | Mark Hamilton |  |  |  |  | Discuss
4087 | 333825 | Hamilton, Mark | Technical | 22 | 6.5.7.3.2 | 48 | We need the PASN ID to be delivered by the MLME-ASSOCIATE indication and confirm. Otherwise, how does the RXr of the info get it to match with a later PASN activity? | Yes | Add PASN ID (matching the .request and .response) to the MLME-ASSOCIATE.confirm and .indication primitives. | Mark Hamilton |  |  |  |  | Discuss
4088 | 333826 | Hamilton, Mark | Technical | 25 | 9.3.3.5 | 25 | The PASN ID provided in the MLME-ASSOCIATE.request needs to be carried in the Association Request frame. | Yes | Add PASN ID (matching the Association Response frame) to the Association Request frame. | Mark Hamilton |  |  |  |  | Discuss
4089 | 333827 | Hamilton, Mark | Technical | 45 | 12.13.3.2 | 34 | The non-AP STA can only expect/require the PASN Encrypted Data element if it knows the AP has device ID (or IRM) activiated. Otherwise, we break legacy PASN interopability. | Yes | Change cited text to, "If dot11DeviceIDActivated is true and the PASN frame is from an AP that indicated support for the device ID mechanism in its Beacon or Probe Response frame(s), it validates ...". Same thing at P45.41 (with "incidated support for the IRM mechanism"). Then, again, same things at P45.59 and P46.1. | Mark Hamilton |  |  |  |  | Discuss
4090 | 333828 | Hamilton, Mark | Technical | 46 | 12.13.8 | 47 | "When dot11KEKPASNActivated is false or when dot11KEKPASNActivated is true and the KEK In PASN field in the RSNXE from the peer is 0,": the "is false" needs to be "is not true" per the implied "or is not present" trick (see REVme 1.4). | Yes | Change "When dot11KEKPASNActivated is false" to "When dot11KEKPASNActivated is not true" | Mark Hamilton |  |  |  |  | Accept
4091 | 333829 | Hamilton, Mark | Technical | 41 | 12.2.13.2 | 6 | Its called "PASN authentication". | Yes | Change "PASN preassociation" to "PASN authentication" | Mark Hamilton |  |  |  |  | Accept
4092 | 333838 | Yang, Jay | Technical | 37 | 12.2.13.1 | 37 | [on the behalf of Yan Li]non-AP STA may not perform PASN authentication in the future,which may wast resource to store the PASN ID if AP provides PASN ID in the initial connection by default As the comment | No | as the comments. | Yan Li |  |  |  |  | Discuss
4093 | 333847 | Smith, Graham | Technical | 19 | 3.2 | 23 | PASN ID. It is transient so say so | No | Insert "transient" before "device ID" | Graham Smith |  |  |  |  | Discuss
4094 | 333848 | Smith, Graham | Editorial | 28 | 9.4.2.19.7 | 19 | "A Beacon request does not contain both an IRM Recommendation subelement and a Measurement ID." As "included' is used in previous paragtraph, suggest same here. | No | In cited sentence replace "does not contian" with "does not include" | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4095 | 333849 | Smith, Graham | Editorial | 20 | 9.4.2.316 | 29 | "The Device ID element contains a device ID." Problem is that sometimes it does not. Either replace with "The Device ID element may contain a device ID." or better still delete. | No | Delete "The Device ID element contains a device ID." | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4096 | 333850 | Smith, Graham | Editorial | 31 | 9.3.2.319 | 19 | The instruction "Insert the following new …." is not in the correct instruction format. | No | Correct instruction format at cited point. | Carol Ansley |  | REJECTED | Instructions are valid |  | Ready for motion
4097 | 333851 | Smith, Graham | Editorial | 32 | 9.4.2.319 | 35 | The Vendor Specific subelements have the same format as their corresponding elements (see 9.4.2.24) …." Should this be here? Think it should be deleted | No | delete lines 35 to 38 | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4098 | 333852 | Smith, Graham | Editorial | 33 | 9.4.2.320 | 21 | "NOTE—The PASN ID might be constructed as an opaque identified as described in 12.2.13.1" I think it should be "identifier" | No | Replace "identified" with "identifier" | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4099 | 333853 | Smith, Graham | Editorial | 37 | 12.2.13.1 | 45 | "the non-AP STA didn’t provide a device ID" do we use "didn't", replace with "did not" | No | replace "didn't" with "did not" | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4100 | 333854 | Smith, Graham | Editorial | 39 | 12.2.13.1 | 4 | extra space before first comma "…in Annex , or" | No | delete space | Carol Ansley |  | REVISED | Correct error in cross-reference to Annex. |  | Ready for motion
4101 | 333855 | Levy, Joseph | Technical | 36 | 12.2.13 | 29 | There is no such MIB variable as dot11PrivacyActivated, the variable is dot11MACPrivacyActivated. Also, the statement "MAC privacy enhancements are required in order to use the device ID mechanism or the IRM mechanism. A non-AP-STA shall set dot11PrivacyActivated equal to true to use either of these mechanisms." while "correct" is not very clear, as it is not apparent that the MAC privacy enhancements relate to the MAC privacy enhancements in clause 12.2.11. | Yes | Replace "MAC privacy enhancements are required in order to use the device ID mechanism or the IRM mechanism. A non-AP-STA shall set dot11PrivacyActivated equal to true to use either of these mechanisms." With: "The device ID mechanism and the IRM mechanism require that the Non-AP STA supports the MAC privacy enhancements in 12.2.11." And move the requirement that dot11MACPrivacyActivated is true to the 12.2.13.1 two locations (37.1, 37.12) as shown below: replace : "A non-AP STA that has dot11DeviceIDActivated equal to true ..." With: "A non-AP STA that has dot11MACPrivacyActivated and dot11DeviceIDActivated equal to true ..." And in 12.2.13.2 two locations (39.19 and 39.40) as shown below replace: "A non-AP STA that has dot11IRMActivated equal to true ..." With: "A non-AP STA that has dot11MACPrivacyActivated and dot11IRMActivated equal to true ..." | Joseph Levy |  |  |  |  | Discuss
4102 | 333856 | Levy, Joseph | Editorial | 20 | 4.5.4.10 | 19 | There are more than two IDs: device ID, PASN ID, and IRM, so the use of "both" is confusing. | No | Replace: "Such a non-AP STA, upon reconnecting to a network, can provide either a device ID or a PASN ID previously provided by the network or can use an identifiable random MAC address (IRM) the STA previously provided to the network or both." With: "Such a non-AP STA that is using device ID, upon reconnecting to a network, can provide either a device ID or a PASN ID previously provided by the network. Such a non-AP STA that is using identifiable random MAC address (IRM), upon reconnecting to a network, can provide the IRM the STA previously provided to the network. Such a non-AP STA can use both device ID and IRM." | Carol Ansley |  | REVISED | Modify reference sentence to: "Such a non-AP STA using the device ID mechanism, upon reconnecting to a network, can provide either a device ID or a PASN ID previously provided by the network. Such a non-AP STA using the identifiable random MAC address (IRM) mechanism, upon reconnecting to a network, can provide the IRM the STA previously provided to the network. Such a non-AP STA can use both device ID and IRM mechanisms concurrently." |  | Ready for motion
4103 | 333857 | Levy, Joseph | Editorial | 20 | 4.5.4.10 | 23 | The article is missing. | No | Replace: "… it can map already established shared identity …" With: "… it can map an already established shared identity …" | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4104 | 333858 | Levy, Joseph | Editorial | 20 | 4.5.4.10 | 24 | This text is very awkward and hard to read | No | Replace: "… allows the network to help with network acquisition steering and selection, or connect transactional information such as preassociation or prior association activity to a post-association device." With: "… can allow the network to provide network acquisition steering and selection, or allow the network to connect transactional information obtained preassociation or in a prior association to the device that is associating." | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4105 | 333859 | Levy, Joseph | Editorial | 40 |  | 51 | This text is very awkward and not clear. This is describing AP behavior in response to a non-AP STA that is associated for the first time or is authenticating using PASN for the first time to an AP in an ESS, but the text does not make that clear. Also it is not clear that the AP is responding to the non-AP STA in a response frame and is setting the IRM status field in the response frame to 1. | No | Replace: "When associating for the first time or authenticating using PASN for the first time to any AP in an ESS, the AP sets the IRM status field to 1 indicating Not Recognized. In this case, the non-AP STA shall ignore that setting and continue to associate or authenticate using PASN." With: "When a non-AP STA is associating for the first time or authenticating using PASN for the first time to any AP in an ESS, the AP shall set the IRM status field to 1 in the response frame to indicate Not Recognized. In this case, the non-AP STA shall ignore that the IRM status field is equal to 1 and continue to associate or authenticate using PASN." | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4106 | 333864 | Malinen, Jouni | Editorial | 32 | 9.4.2.319 | 45 | The subelements that are included in the PASN Encrypted Data element are called inconsistently either elements or subelements in this subclause. That is particularly confusing when there are actual elements with the exact same name as these subelements. | No | At P31 L45, replace "Device ID element" with "Device ID subelement". At P32 L18, replace "PASN ID element" with "PASN ID subelement". At P32 L25, replace the title of Figure 9-1074g "PASN ID element format" with "PASN ID subelement format". | Carol Ansley |  | REVISED | Make changes commentor requested and change 31.18 to align element vs subelement to be consistent. |  | Ready for motion
4107 | 333865 | Malinen, Jouni | Editorial | 33 | 9.4.2.320 | 1 | Typo in the description of PASN ID Status field: "Then" should have been "When",. | No | Replace "Then the element is sent from a non-AP STA" with "When the element is sent from a non-AP STA". | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4108 | 333866 | Malinen, Jouni | Technical | 41 | 12.7.2 | 25 | KDE selector Data Type values in Table 12-10 were changed to values that are already assigned for IEEE P802.11be and that have already been deployed in a large number of devices. It is clearly unacceptable to try to change that now even if P802.11bh were to be published before P802.11be. This would result in significant interoperability issues and in practice, would prevent deployment of P802.11bh. | Yes | Get new non-conflicting KDE selector Data Type values from IEEE 802.11 ANA for the new KDEs defined in P802.11bh. | Carol Ansley |  | REVISED | Update to use KDE selectors of data type 20, 21 and 22. |  | Ready for motion
4109 | 333867 | Malinen, Jouni | Editorial | 43 | 12.7.6.1 | 22 | Added text for Message 2 is not identified correctly: missing underlining. | Yes | Underline the added text at P43 L22: " [, Device ID KDE] [, IRM KDE]". | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4110 | 333868 | Malinen, Jouni | Editorial | 52 | AF.2 | 57 | Typo: the padding is random, not ransom.. | Yes | Replace "ransom padding" with "random padding". | Carol Ansley |  | ACCEPTED |  |  | Ready for motion
4111 | 333869 | Sun, Li-Hsiang | Technical | 41 | 12.7.2 | 48 | Similar to the device ID element, there should be text saying the Device ID status is not present when sent by non-AP STA, and must be present when sent by AP | No | as in comment | Mark Hamilton |  |  |  |  | Unclear what the issue is
4112 | 333870 | Sun, Li-Hsiang | Technical | 38 | 12.2.13.1 | 39 | On p54 L58, it was mentioned that there is an "implicit" assignment of the same device ID. Does it mean when Device Status equal to 0, and device ID is omitted from AP, the same device ID is reused? | No | If the above interpretation is correct, add a sentence to say if Device Status equal to 0, and device ID is omitted. then same device ID will be used subsequently | Jay Yang | 11-24/1271 | REJECTED | If AP intends to maintain the same device ID, the following rule will be applied “Set the Device ID Status field of the Device ID KDE or Device ID element to 0 to indicate that the AP recognizes the non-AP STA and set the Device ID field to zero length (indicating the current device ID is maintained).”, no need to add extra text for it. |  | Ready for motion
4113 | 333871 | Sun, Li-Hsiang | Technical | 38 | 12.2.13.1 | 18 | "When a non-AP STA sends a device ID or a PASN ID to an AP, it shall use the device ID or the PASN ID most recently received from any AP belonging to the same ESS." If non-AP sent the most recent received device ID, and AP returns Device ID status and no new assigned device ID, the non-AP STA should delete the device ID, so the device ID signaled by the non-AP can be reclaimed by the network | No | add requirement that non-AP deletes the device ID after AP informs Device ID status 1 and no new device ID is assigned, so the device ID signaled by the non-AP can be reclaimed by the network | Jouni Malinen | 11-24/1301 |  |  |  | Submission Required
4114 | 333872 | Sun, Li-Hsiang | Technical | 20 | 4.5.4.10 | 23 | Not clear what the definition of "shared identity state" is Baseline 12.2.12 does not seem to have the definition of "shared identity state" On p36 L13, is "cached information" the synonym of "shared identity state"? | No | Define "shared identity state" in clause 3.2 | Mark Hamilton |  |  |  |  | Submission Required