## Slide 1: REVme Closing Report – July 2024
Date: 2024-07-18
Authors:

## Slide 2: Work Completed
Completed comment resolution on SA Ballot recirculation comments received on D6.0
Initiated a 10-day recirculation ballot on D7.0
Approved a request to the 802 LMSC for conditional approval to submit REVme D7.0 to REVCOM.

## Slide 3: Plans for September
Teleconferences scheduled
  Monday August 12 at 10am ET for 2hrs
No meetings in September session
Objectives:
  Wait for TGmf to begin

## Slide 4: TGme Timeline (No changes)
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB
July 2023 – D4.0 Recirculation
Sep 2023 – D5.0 Initial SA Ballot
Feb 2024 – D6.0 Recirculation SA Ballot (roll-in of published amendment 11az, 11bd, 11bc, 11bb)
May 2024 – D7.0 Recirculation SA Ballot
Jul 2024 – D8.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval

## Slide 5: EC Conditional Approval for REVCOM
Approve document https://mentor.ieee.org/802.11/dcn/24/11-24-1141-01-000m-p802-11revme-report-to-ec-on-conditional-approval-to-forward-draft-to-revcom.pptx as the report to the IEEE 802 Executive Committee on the requirements for conditional approval to forward P802.11REVme to RevCom and
Request the IEEE 802 Executive Committee to conditionally approve forwarding P802.11REVme to RevCom.
Moved: Mark Hamilton
Second: Stephen McCann
Result: 9 – Yes; 0 – No; 0 - Abstain. Passes.
[Moved by <name> on behalf of TGme<group> vote: x-y-z ]