## Slide 1: IEEE 802.11 Jan 2025 Interim TGbp Closing Report
Chair: Bo Sun (Sanechips)
Elected Vice Chairs: Steve Shellhammer (Qualcomm)
Rakesh Taori (Infineon)
Secretary : Sebastian Max (Ericsson)
Tech Editor: Yinan Qi (OPPO)

## Slide 2: TGbp’s Progress during this week
8 TGbp meetings were planned and held during Jan interim session, with the agenda include in the latest revision of 11-24/1997r6.
TGbp approved the updated FRD and SFD documents incorporating approved motions in Nov 2024.
More than 40 tech contributions were presented and discussed, on functional requirements, PHY/MAC solutions, Wireless Power Transmission and security.
Lots of technical Motions for SFD were approved as captured in last revision of 11-24/1322r6.
  Consensus on terms, topology, operation types, transmission mode, some AMP PPDU structure in 2.4 GHz, up-link data rate in 2.4 GHz, AMP-sync in AMP DL PPDU, conception of energizer, energy harvesting and power information report, etc.
The 11bp timeline was revisited without change.
3 teleconferences were planned after Jan interim session.
Goal of future TGbp work:
  Continue developing FRD and SFD based on consensus
  Open technical discussion and prepare for PDT development

## Slide 3: TGbp Timeline Plan (Subject to change based on development progress)
  PAR approved Mar 2024
  First TG meeting May 2024
  D0.1 (ready for CC) Mar, 2025
  D1.0 Letter Ballot Feb, 2026
  D2.0 LB recirculation Nov, 2026
  Form SA Ballot Pool Mar 1 to Mar 31, 2027
  Initial SA Ballot (D4.0) Aug, 2027
  Final 802.11 WG approval Jan 2028
  802 EC approval Mar 2028
  RevCom and SASB approval May 2028

## Slide 4: TGbp Teleconference Plan
  Feb 11th (Tuesday), 9:00am, ET, 2 hours; Webex
  Feb 25th (Tuesday), 9:00am, ET, 2 hours; Webex
  Mar 4th (Tuesday), 9:00am, ET, 2 hours; Webex