## Slide 1: REVmf Closing Report – March 2025
Date: 2025-03-14
Authors:

## Slide 2: Work Completed
Considered contributions on modifications REVme D7.0
  Accepted two documents with proposed changes
Discussed a contribution on PASN with MLO
Agenda doc: https://mentor.ieee.org/802.11/dcn/25/11-25-0219-03-000m-revmf-agenda-march-2025-session.pptx
Motion doc: https://mentor.ieee.org/802.11/dcn/24/11-24-1925-04-000m-revmf-motions.pptx

## Slide 3: Plans for May
Teleconferences scheduled
  Monday April 28 at 10am ET for 2h
May session: 3 meetings
Objectives:
  Continue to discuss contributions on published REVme D7.0, P802.11bh D6.0, and P802.11be D7.0
  Approve the creation of REVmf D1.0 and the initial letter ballot.

## Slide 4: TGmf Timeline
Nov 2024 – PAR Approval
Nov 2024 – Initial meeting, contributions on REVme D7.0
Jan - Mar 2025 – Contributions on REVme D7.0/IEEE 802.11-2024
Jan - Mar 2025 – Publication of 802.11-2024 and roll-in of TGbh and TGbe
May 2025 – Initial D1.0 WG Letter ballot
May-Nov 2025 – Roll-in TGbf and TGbk
Jan 2026 – D2.0 Recirculation LB
Jul 2026 – D3.0 Recirculation
Jan 2027 – D4.0 Initial SA Ballot – Roll-in TGbi
Jul 2027 – D5.0 Recirculation SA Ballot
Nov 2027 – D6.0 Recirculation SA Ballot
Jan 2028 – D6.0 Recirculation SA Ballot (clean recirculation)
Feb 2028 – RevCom/SASB Approval