## Slide 1: IEEE 802.11 Mar 2025 Plenary TGbp Closing Report
Chair: Bo Sun (Sanechips)
Elected Vice Chairs: Steve Shellhammer (Qualcomm)
Rakesh Taori (Infineon)
Secretary : Sebastian Max (Ericsson)
Tech Editor: Yinan Qi (OPPO)

## Slide 2: TGbp’s Progress during this week
8 TGbp meetings were planned and held during Jan interim session, with the agenda include in the latest revision of 11-24/0228r7.
TGbp approved the updated SFD documents incorporating approved motions in Jan 2025.
Totally 35 tech contributions were presented and discussed, onPHY/MAC solutions, Wireless Power Transmission and security.
Lots of technical Motions for SFD were approved as captured in last revision of 11-24/0228r7.
  Consensus on waveform, coding/modulation, PPDU design, security, channel access, WPT design, etc.
The 11bp timeline was updated with the D0.1 milestone postponed to Jul 2025.
4 teleconferences were planned after Mar plenary session.
Goal of future TGbp work:
  Continue developing FRD and SFD based on consensus
  PDT development based on approved SFD
  Open technical discussion and prepare for PDT development

## Slide 3: TGbp Timeline Plan (updated)
  PAR approved Mar 2024
  First TG meeting May 2024
  D0.1 (ready for CC) Mar  Jul, 2025
  D1.0 Letter Ballot Feb, 2026
  D2.0 LB recirculation Nov, 2026
  Form SA Ballot Pool Mar 1 to Mar 31, 2027
  Initial SA Ballot (D4.0) Aug, 2027
  Final 802.11 WG approval Jan 2028
  802 EC approval Mar 2028
  RevCom and SASB approval May 2028

## Slide 4: TGbp Teleconference Plan
  Mar 25th (Tuesday), 10:00am, ET, 2 hours; Webex
  Apr 8th (Tuesday), 10:00am, ET, 2 hours; Webex
  Apr 22nd (Tuesday), 10:00am, ET, 2 hours; Webex
  May 6th (Tuesday), 10:00am, ET, 2 hours; Webex