## Slide 1: TGbq timeline proposal - follow up
Date: 2025-05-12
Authors:

## Slide 2: [Recap] Proposal: TGbq Timeline Adjustment [1]
TGbq timeline needs to be adjusted and PAR extension may be required considering the start date of TGbq (Feb. '25), sufficient technical discussions period (1-2 years), the practical letter ballot period (1-2 years), and SA ballot period (0.5 year)
  Roughly we have three options, i.e., Option 1 (maintaining PAR timeline, the expected completion time: Mar. 2027), Option 2 (+ 1 year, e.g., a timeline for compact spec. feature set, the expected completion time: Apr. 2028), and Option 3 (+ 2 years, e.g., a timeline for big spec. feature set, the expected completion time: Apr. 2029)
2024
2025
2026
2027
Break
2028
PAR/CSD
approved in WG
(Jul. '24)
IMMW SG
(Nov. '23)
34 contributions discussed
First TGbq
(Feb. '25)
Initial SA Ballot (D4.0)
(Jul. '26)
16 month
8 month
Submittal to RevCom
(Mar. '27)
10 month
D0.1 (Jan. '26)
D4.0
(Jul. '27)
Submittal to RevCom
(Mar. '28)
Option 2 (+1 year)
6 month
6 month
D1.0
(Jul. '26)
12 month
2029
Option 1 (PAR timeline)
16 month
D1.0
(Jul. '27)
Option 3 (+2 years)
D0.1
(Jul. '26)
12 month
D4.0
(Jul. '28)
Submittal to RevCom
(Mar. '29)
8 month
12 month
D0.1
D1.0
Mar. '25 (now)

## Slide 3: Proposed TGbq timeline
 | (Expected) date | Comments
TGbq PAR approved | 2024-12-11 | 
D0.1 | Jul. 2026 | For technical discussions (examples: see slides 4-10)
D1.0 (Initial WG LB) | Jul. 2027 | Adjusted based on time required for comment resolution in order to get a technically stable D1.0
Initial SA Ballots | Jul. 2028 | Adjusted based on the time required for recirculation
Final 802.11 WG Approval | Mar. 2029 | Determined in accordance with standard administrative procedures.
RevCom Approval |  | Determined in accordance with standard administrative procedures
2025
2026
2027
2028
2029
14 month
D1.0
(Jul. '27)
D0.1
(Jul. '26)
12 month
D4.0
(Jul. '28)
Final 802.11 WG Approval
(Mar. '29)
8 month
12 month
PAR approved
(Dec. '24)
2025 May Interim
(May '25)

## Slide 4: By the second half of next year...
Before getting D0.1, it is necessary to have in-depth discussions on the following topics and select from multiple design options
  Baseline PHY for IMMW and numerology
  Bandwidth range, channelization, Preamble/PPDU design
  IMMW link establishment and management
  Beam training details
  Target performance (throughput, capacity …)

## Slide 5: Decision on IMMW PHY (11ac vs. 11ax/be)
Upclocking 11ac PHY vs. upclocking 11ax/be/bn [2]
  If we do not have any performance issues that can only be addressed by using 11ax/be PHY as a baseline, it might be preferred to use 11ac as a baseline due to its stable performance [3][4]
Bandwidth
  Minimum bandwidth can be determined by upclocking factor
  Target maximum throughput is taken into account for maximum bandwidth
Channelization
IMMW Preamble design, IMMW-specific PPDU format [4]
Antenna pattern
  Omni-directional antenna [5]

## Slide 6: UHR MAC dependency?
It appears that there are few UHR MAC functions that are absolutely essential for IMMW. Therefore, EHT MAC might be sufficient.
  Following representative UHR MAC features that improve channel access efficiency and latency reduction on sub-7GHz links, however, they may not be particularly necessary for integrated mmWave link
    Seamless roaming
    Prioritized-EDCA
    Non Primary Channel Access (NPCA), Dynamic Sub-band Operation (DSO)
    Dynamic Power Save (DPS)
    Dynamic/Periodic Unavailability Operation (DUO, PUO), In-Device Coexistence (IDC)
    Multi-AP Coordination schemes (Co-TDMA, Co-RTWT …)
  UHR MAC-enabled sub-7GHz link may improve the overall performance of IMMW device
  UHR ICF/ICR format may be useful to contain IMMW-specific information via sub-7GHz

## Slide 7: Discovery and initial Link Setup for IMMW link
Beacon design for IMMW link
  Maximize offloading to sub-7GHz link beacons and use IMMW beacons only for information that must be transmitted via IMMW link [6]
IMMW link association procedure
  IMMW link establishment with the assistance of sub-7GHz link
    Sub-7GHz probe request/response frame with Multi-Link element
  Criteria for the IMMW link to establish a connection with the AP independently without the assistance of sub-7 GHz?

## Slide 8: Dedicated Service Period or Contention-based Service Period?
Whether to allow contention-based channel access or strictly adhere to scheduled-based operation depends on the specific use case and requirements
  Contention-based channel access
    Flexibility, low overhead, and low latency
    Question: Are there any unexpected (non-periodic, thus unschedulable) low-latency traffic or applications that must be transmitted via the IMMW link?"
  Scheduled-based channel access with sub-7GHz Link assistance:
    Efficiency. But limited capacity
Scheduled-based operation with sub-7GHz link assistance seems appropriate
  IMMW devices can operate predictably and efficiently, leveraging the sub-7GHz link to manage scheduling and resource allocation.
  However, if there are specific scenarios where flexibility is required, a hybrid approach which allows limited contention-based access

## Slide 9: IMMW beam management and update
Practical number of Tx/Rx sectors?
  How narrow should the TX beam be?
  How many RX sectors would be ideal?
  Considering the overhead and time required for beam training, how many TX/RX sectors would be realistic?

## Slide 10: Practical consideration
Mobility
  Should the mobility of the IMMW STA be considered? Will the IMMW device be used in scenarios where a user is walking or running, or will it move within a certain fixed location along a trajectory such as a VR/XR case?
Scalability
  How many IMMW STAs can realistically be supported simultaneously per each AP?
  Or should we consider scenarios where a large number of IMMW devices are simultaneously served in a specific area? Are we considering dense environments that cannot be resolved through channelization alone?

## Slide 11: Conclusion
While briefly mentioning the topics to be discussed in TGbq, we proposed a TGbq timeline that includes achieving D0.1 by the second half of next year and allocating about one year for D1.0.

## Slide 12: SP
Do you agree with the following proposed timeline for TGbq?
  Expected completion time: Mar. 2029
    D0.1: Jul. 2026
    D1.0: Jul. 2027
    Initial SA Ballots: Jul. 2028
    Final 802.11 WG Approval: Mar. 2029

## Slide 13: Reference
[1] 11-25/0261r2, IMMW for Consumer Device and TGbq timeline
[2] 11-25/0238r1, IMMW System Reuses
[3] 11-25/0179r0, 802.11ac waveform transmission over mmWave carrier
[4] 11-25/0360r0, High-level thoughts on IMMW PHY Design
[5] 11-25/0366r0, Simulation of Indoor Millimeter-Wave Signal Received Power Using an Omnidirectional Antenna Pattern
[6] 11-25/0632r1, Anchor Link for ML Operation with mmWave Link

## Slide 14: Appendix: Other TGs’ Timelines (as a reference)
 | PAR | PAR approved | First TG meeting | WG Letter Ballots (D1.0) | SA Ballot (D3.0/4.0/5.0) | Final 802.11 WG Approval | RevCom Approval
11ad | Very High Throughput 60GHz | 2008-12-10 |  | 2010-10-24 | 2012-01-05 | 2012-07-01 | 2012-10-23
11ay | Next Generation 60GHz | 2015-03-26 |  | 2018-01-07 | 2020-01-09 | 2020-11-01 | 2021-03-01
11bf | WLAN Sensing | 2020-09-25 | 2020-08 | 2023-03-02 | 2024-06-12 |  | 
11bh | Randomized and Changing MAC Addresses | 2021-02-10 |  | 2023-07-01 | 2024-05-09 | 2024-07-01 | 
11bi | Enhanced Data Privacy | 2021-02-10 |  | 2025-01 |  |  | 
11bk | 320 MHz Positioning | 2022-12-03 |  | 2023-12-28 | 2024-11-10 |  | 
11bp | Ambient Power Communication | 2024-03-19 | 2024-05 | 2026-02 | 2027-08 | 2028-01 | 2028-05
from first TG meeting to D1.0: 1-3 years
from D1.0 to 11 WG approval: 1-2 years