## Slide 1: 802.11bn Timeline Discussion
Date: 05-13-2025
Authors:

## Slide 2: Introduction
TGbn is working on the D0.1 review process after PAR approval and is set to generate a D1.0 for initial WG ballot.
Ahead of this first important milestone, we would like to review the previously agreed 11bn timeline [1] in this contribution and discuss our future schedule
  In February of 2025, we proceeded with Comment Collection on D0.1 (3,970 Comments are collected)
  And generating a D1.0 and the attempt at first Letter Ballot is scheduled in May

## Slide 3: 11ax/be schedule review
Before discussing the 11bn schedule, let's review the previous cases
  IEEE 802.11be
    January 2021, Comment Collection for D0.3 (2438 Comments)
    In May 2021, D1.0 ready and WG Letter Ballot attempt (1092(45%) comments from D0.3 Comment Collection were left unaddressed), *TG approval, **WG failure
    In June 2021, Comment Collection for D1.0 (4372 Comments)
    May 2022, D2.0 ready and WG Letter Ballot attempt (All comments from D1.0 Comment Collection were addressed), TG/WG approval
  IEEE 802.11ax
    March 2016, Comment Collection for D0.1 (2,919 Comments)
    In November 2016, D1.0 ready and WG Letter Ballot attempt (325(11%) comments from D0.1 Comment Collection were left unaddressed), TG/WG approval
11be processed 1346 comments for D0.3 / 4372 comments for D1.0 over 4 / 12 months, respectively (350 comments/month)
11ax processed 2594 comments for D1.0 over 8 months (324 comments/month)
** 66Y/42N/39A
* 129Y/12N/16A

## Slide 4: 11bn schedule review
We had discussed the TG schedule based on the contribution [1] in November 2023, the first meeting of TGbn. At that time, there were many opinions that the schedule was so tight. However, the current schedule was finally agreed at the time because the schedule could be revised(postponed) if necessary
  It was pointed out that the spec development schedule is shorter than the 11be and the number of features is not small
  Some said that 11bn does not need to be released quickly in the Wi-Fi market
  On the other hand, in 11bn, there was an opinion that the schedule could be reduced by utilizing what was developed in 11be and focusing only on key features that affect the market

## Slide 5: D0.1 comment collection status
Total 3,970 comments on D0.1 can be classified as follows
  Technical 2773 / Non-technical 1199
  PHY: 1073 / MAC: 2166 / Joint: 533
  Multi-AP: ~900, Power Saving: ~200, NPCA: ~350, Coex: ~400, DRU: ~200, ELR: ~100
If comments are processed with the historical speed, it may take about 10 to 12 months to address all comments
If we expect to process about 1,000 comments by May, then we have Draft v0.x and 3,000 remaining unaddressed comments at the May meeting
We must consider various points of view before discussing D1.0 schedule
  TG/WG Documents related to comment collection/resolution and operating rules
  Time to Market / Certification program
  PAR document
Note: # of comments by technology are roughly aggregated

## Slide 6: TGbn Guidelines [2] / 802.11 WG Operation Manual [3]
TGbn Guidelines
802.11 WG Operation Manual

## Slide 7: Time to Market
11ax (Wi-Fi 6) Certification was launched in September 2019
  It was 2 years and 8 months after 11ax D1.0 and LB
11be (Wi-Fi 7) Certification was launched in January 2024
  It was 2 years and 8 months after 11be D1.0 (did not pass LB)
  It was 1 year and 4 months after 11be D2.0 and LB
If based on the trend, it can be expected that 11bn (Wi-Fi 8) Certification will be launched in 2028
  If D1.0 is completed by the end of this year, there will be enough time for the certification program to launch in 2028
  But considering that a lot of work has been done on drafting it may take less than previous generations
  A stable D1.0 will facilitate faster completion of the specifications.

## Slide 8: Timeline for D1.0
Referring to TGbn Guidelines, we do not need to address all comments of CC50
However, according to 802.11 WG Operation Manual, we have to process many of the comments of CC50 so that the draft is stable
  Looking at the case of 11ax/be cases, it is apparent that before motioning the TG/WG D1.0 LB draft, we need to address at least more than 90% of the comments.
In addition, new features have been added only after D0.1 such as DSO/DBE, and there have been no comment collection at all on these features.
  It is not easy to deem these features complete at the level of D1.0 with only the SP/Motion approved so far
So, considering the current status of work, requesting in May the generation of a D1.0 seems premature

## Slide 9: Conclusion
Through this contribution, we reviewed our current situation and future schedules
Considering previous Task group cases and related documents, requesting generation of a D1.0 and First LB attempt in May appears to be an extremely ambitious schedule
A realistic schedule adjustment is required to achieve the technical completeness required for D1.0 and WG letter ballot
  The current TGbn project end-time can still remain the same.
We estimate a schedule for September or later of 2025 , when the major features are specified and comments of CC50 are sufficiently addressed, is the right time for D1.0 but this for further discussion in the group

## Slide 10: Reference
[1] 11-23-1931-01-00bn-tgbn-proposed-timeline.pptx
[2] 11-24-1682-04-00bn-tgbn-guidelines.docx
[3] 11-22-1638-04-0000-802-11-operations-manual.docx
[4] 11-23-0480-03-0uhr-uhr-proposed-par.pdf