## Slide 1: Discussion on 802.11bq Timeline
Date: 2025-05-12
Authors:
Name | Affiliations | Address | Phone | email
Mengshi Hu | Huawei |  |  | humengshi@huawei.com
Ming Gan |  |  |  | 
Yanchun Li |  |  |  | 
Xuming Wu |  |  |  | 
Bin Tian | Qualcomm |  |  | 
Abhishek Patil |  |  |  | 
George Cherian |  |  |  | 
Rolf de Vegt |  |  |  | 
Cheng Chen | Intel |  |  | 
Laurent Cariou |  |  |  | 
Carlos Cordeiro |  |  |  | 

## Slide 2: Introduction
The PAR (Project Authorization Requests) of P802.11bq has been approved in Dec. 11th, 2024 [1].
  P802.11bq, also know as the Integrated mmWave (IMMW), defines standardized modifications to both PHY and MAC that allows Wireless Local Area Network (WLAN) non-standalone operation in unlicensed bands between 42 GHz and 71 GHz using single-user (SU) Orthogonal Frequency Division Multiplexing (OFDM) based transmissions.
This presentation discusses the development timeline for the P802.11bq amendment.

## Slide 3: Key Factors Affecting 11bq Timeline
The following key factors are considered for the 11bq timeline:
  We list the timeline information of 11bp, 11bd, 11bn, 11ba and 11bf in the following slides.
    The work scope of 11bq should be smaller than those in 11bn. Thus the timelines of 11bn could be the upper bound for the estimation of 11bq.
    The work scope of 11bq is comparable to 11bp, 11bd and 11bf, which would help us derive a reasonable timeline estimation.
  Expected complexity of 11bq
    Can reuse the sub-7 GHz part.
  Time to standardize.
  Time/investment to implement.

## Slide 4: Proposed Timeline for 802.11bq
 | 11bq | 11bp | 11bd | 11bn | 11ba | 11bf
Total Months | 55 (Dec 2024 – Jul 2029) | 50 (Mar 2024 – May 2028) | 48 (Dec 2018 – Dec 2022) | 58 (Jul 2023 – May 2028) | 51 (Dec 2016 – Mar 2021) | 57 (Sep 2020 – Jun 2025)
D0.1 | +17 (May 2026) | +16* (July 2025) | +11 (Nov 2019) | +18 (Jan 2025) | +15 (Mar 2018) | +19 (Apr 2022)
Draft 1.0 | +8 (Jan 2027) | +7* (Feb 2026) | +11 (Oct 2020) | +4* (May 2025) | +6 (Sep 2018) | +9 (Jan 2023)
Draft 2.0 | +8 (Sep 2027) | +9* (Nov 2026) | +9 (July 2021) | +12* (May 2026) | +4 (Jan 2019) | +6 (Jul 2023)
Draft 3.0 | +6 (Mar 2028) | +4* (Mar 2027) | +5 (Dec 2021) | +8* (Jan 2027) | +4 (May 2019) | +9 (Apr 2024)
Draft 4.0 | +6 (Sep 2028) | +5* (Aug 2027) | +3 (Mar 2022) | +4* (May 2027) | +4 (Sep 2019) | +7 (Nov 2024)
Final | +10 (Jul 2029) | +9* (May 2028) | +9 (Dec 2024) | +12* (May 2028) | +18 (Mar 2021) | +7* (June 2025)
Stage
Standard
A duration of 55 months is suggested for 802.11bq timeline.
Note: It is expected that the task group will review and update (if needed) the timeline once a milestone is achieved

## Slide 5: Original Proposed Timeline for 802.11bq
Milestone | 11bq | 11bp [2,3] | 11bd [2,4] | 11bn [2,5] | 11ba [2,6] | 11bf [2,7]
PAR approved | Dec, 2024 | Mar, 2024 | Dec, 2018 | July, 2023 | Dec, 2016 | Sep, 2020
First TG meeting | Feb, 2025 | May, 2024 | Jan, 2019 | Nov, 2023 | Jan, 2017 | Oct, 2020
D0.1 | May, 2026 | Jul, 2025 | Nov, 2019 | Jan, 2025 | Mar, 2018 | Apr, 2022
D1.0 | Jan, 2027 | Feb, 2026 | Oct, 2020 | May, 2025* | Sep, 2018 | Jan, 2023
D2.0 | Sep, 2027 | Nov, 2026 | Jul, 2021 | May, 2026* | Jan, 2019 | July, 2023
D3.0 | Mar, 2028 | Mar, 2027 | Dec, 2021 | Jan, 2027* | May, 2019 | Apr, 2024
D4.0 | Sep, 2028 | Aug, 2027 | Mar, 2022 | May, 2027* | Sep, 2019 | Nov, 2024
Final 802.11 WG approval | May, 2029 | Jan, 2028 | Sep, 2022 | March, 2028* | Nov, 2020 | Mar, 2025*
802 EC approval | May, 2029 | Mar, 2028 | Oct, 2022 | March, 2028* | Nov, 2020 | Mar, 2025*
RevCom and SASB approval | Jul, 2029 | May, 2028 | Dec, 2024 | May, 2028* | Mar, 2021 | June, 2025*
Note: It is expected that the task group will review and update (if needed) the timeline once a milestone is achieved
The details for each milestone is given below (see blue color).
WG approval

## Slide 6: Summary
  In this proposal we shared our thoughts on the 11bq timeline.
  To compare with the other standards, the timeline of 11bp, 11bd, 11bn, 11ba and 11bf were given.
  A duration of 55 months was suggested for the 11bq standard timeline.

## Slide 7: SP 1
Do you agree with the following timeline as the initial time estimation for the development of P802.11bq amendment?
  D0.1: May 2026
  D1.0: Jan. 2027
  D2.0: Sep. 2027
  D3.0: Mar. 2028
  D4.0: Sep. 2028
  Final 802.11 WG approval: May 2029
  802 EC approval: May 2029
  RevCom and SASB approval: Jul. 2029
  Yes
  No
  Abstain

## Slide 8
[1] https://www.ieee802.org/11/PARs/P802.11bq_PAR.pdf
[2] https://grouper.ieee.org/groups/802/11/Reports/802.11_Timelines.htm
[3] 11-24-1997-06-00bp-tg-bp-meeting-agenda-for-jan-interim-2025
[4] https://www.ieee802.org/11/Reports/tgbd_update.htm
[5] https://mentor.ieee.org/802.11/dcn/24/11-24-2074-18-00bn-tgbn-jan-2025-meeting-agenda.pptx
[6] IEEE P802.11 - TASK GROUP BA
[7] https://mentor.ieee.org/802.11/dcn/24/11-24-2087-02-00bf-tgbf-meeting-agenda-2025-01-interim.pptx
References