## Slide 1: Enhanced Light Communications Study Group (ELC) May 2025 Closing Report
Date: 2025-5-15
Authors:

## Slide 2: Abstract
This presentation contains the IEEE 802.11 Enhanced Light Communications Task Group (TGbr) closing report for the May 2025 session.

## Slide 3: TGbr activities at the May 2025 meeting
  Content
  TGbr considered a number of contributions and approved:
    Specification Framework Document (doc. 11-25/0941r0)
    Work plan (doc. 11-25/0912r0)
    Officers (Vice-Chairs, Technical Editor, Secretary)
  Contributions discussed included:
    Technical Proposals for Consideration (doc. 11-25/0830r0)
    PAPR reduction considerations (doc. 11-25/0945r0)
    On the timeline for TGbr (doc. 11-25/0956r0)
    Proposal for Addition to SFD (doc. 11-25/0962r0)
  Meeting agenda is available in doc. 11-25/0616
  Motions and straw polls are available in doc. 11-25/0968
  Minutes of the meeting are available in doc. 11-25/0974

## Slide 4: TGbr moving forward
Mar-2025 PAR approved
May-2025 Create SFD and consider technical contributions
Jul-2025 Continue consider technical contributions and develop SFD
Nov-2025 agree main features (PHY) and close SFD for PHY
Jan-2026 start draft development (PHY)
Jul-2026 complete PHY (D0.1)
Sep-2026 agree main features (MAC) and close SFD for MAC
Nov-2026 start draft development (MAC)
Jan-2027 complete MAC (D0.2), start internal CC
Jul-2027 complete D0.x, start CC in 802.11 WG
Nov-2027 D1.0 for WG letter ballot
Jan-2028 D2.0
Mar-2028 D3.0
May-2028 start SA ballot
Nov-2028 submit to RevCom
2029 publish