## Slide 1: IEEE 802.11 May 2025 Interim TGbp Closing Report
Chair: Bo Sun (Sanechips)
Elected Vice Chairs: Steve Shellhammer (Qualcomm)
Rakesh Taori (Infineon)
Secretary : Sebastian Max (Ericsson)
Tech Editor: Yinan Qi (OPPO)

## Slide 2: TGbp’s Progress during this week
8 TGbp meetings were planned and held during May interim session, with the agenda include in the latest revision of 11-25/0611r7.
TGbp approved the updated SFD documents incorporating approved motions in Mar 2025.
Totally 33 tech contributions were presented and discussed, on PHY/MAC solutions, Wireless Power Transmission and security.
Lots of technical Motions for SFD were approved as captured in 11-25/0611r7.
  Consensus on duty-cycle, power-save, security, sync field design, S1G communication, channel access, WPT design, chip duration, etc.
The 11bp timeline was unchanged.
3 teleconferences were planned after Mar plenary session.
Goal of future TGbp work:
  Continue developing FRD and SFD based on consensus
  PDT development based on approved SFD
  Open technical discussion and prepare for PDT development

## Slide 3: TGbp Timeline Plan (unchanged)
  PAR approved Mar 2024
  First TG meeting May 2024
  D0.1 (ready for CC) Jul, 2025
  D1.0 Letter Ballot Feb, 2026
  D2.0 LB recirculation Nov, 2026
  Form SA Ballot Pool Mar 1 to Mar 31, 2027
  Initial SA Ballot (D4.0) Aug, 2027
  Final 802.11 WG approval Jan 2028
  802 EC approval Mar 2028
  RevCom and SASB approval May 2028

## Slide 4: TGbp Teleconference Plan
  May 27th (Tuesday), 10:00am, ET, 2 hours; Webex
  Jun 17th (Tuesday), 10:00am, ET, 2 hours; Webex
  Jul 8th (Tuesday), 10:00am, ET, 2 hours; Webex