## Slide 1
IEEE 802.11 TGbp Snapshot for IEEE 802 Jul Plenary 2025
Chair: Bo Sun (Sanechips)
Vice Chair: Steve Shellhammer (Qualcomm)
            Rakesh Taori (Infineon)
Secretary: Sebastian Max (Ericsson)
          Tech Editor: Yinan Qi (OPPO)

## Slide 2: TGbp Snapshot for Jul 2025 IEEE 802 Plenary
3 TGbp teleconfrence was held since May interim session for reviewing the updatd SFD and spec skeleton and tech contribution discussion, with agenda included in 11-25/989r4 and meeting minutes included in 11-25/0991r3
The TGbp chair called for volunteers for PDT development based on agreed spec skeleton.
8 TGbp meetings are planned during the IEEE 802 Jul plenary session, with a full meeting agenda included in the latest revision of 11-25/0990.
  Notes, all TGbp meetings will be in Comendador.
Goal for TGbp meetings in this week:
  open technical discussion and improve SFD documents based on consensus
 | Mon | Tue | Wed | Thu | Fri
AM1 (9:00~11:00) |  |  | TGbp (PHY) | TGbp (MAC) | Closing Plenary
AM2 (11:30~13:30) | 802.11 Opening Plenary | TGbp (PHY) | TGbp (MAC) |  | 
PM1 (14:30~16:30) | TGbp (Opening/GEN/PHY) | TGbp (PHY) | Mid-week Plenary | TGbp (SP/Motions/Closing) | 
PM2 (17:00~19:00) | TGbp (PHY) |  |  |  | 
EVE (19:30~21:30) |  |  |  |  | 

## Slide 3: TGbp Timeline till Jul 2025 plenary
  PAR approved Mar 2024
  First TG meeting May 2024
  D0.1 (ready for CC) Jul, 2025
  D1.0 Letter Ballot Feb, 2026
  D2.0 LB recirculation Nov, 2026
  Form SA Ballot Pool Mar 1 to Mar 31, 2027
  Initial SA Ballot (D4.0) Aug, 2027
  Final 802.11 WG approval Jan 2028
  802 EC approval Mar 2028
  RevCom and SASB approval May 2028