## Slide 1: TGbt timeline discussion

## Slide 2: Introduction
In this presentation, we offer some thoughts on 11bt timeline

## Slide 3: Recap: PQC PAR& CSD
The scope of 11bt topics is quite small and concentrated according to the PAR
The time of 802.11bt specification development is quite tense according to the following quoted text in the CSD
  Cryptographically-relevant quantum computers (CRQCs) are anticipated in the coming years. Accordingly, certain responsible government authorities have defined procurement roadmaps for adoption of quantum resistant technologies. For example, the US National Security Agency (NSA) has recently advanced its timeline to 2027 [4].

## Slide 4: Recap: TGbn timeline
PAR approved July 2023
First TG meeting Nov 2023
D0.1 Jan 2025
D1.0 Letter Ballot July 2025
D2.0 LB May 2026
D3.0 LB Jan 2027
Initial SA ballot (D4.0) May 2027
Final 802.11 WG approval Mar 2028
802 EC approval Mar 2028
RevCom and SASB approval May 2028
The latest TGbn timeline is shown as bellow:

## Slide 5: Recap: DH usage in 802.11bn draft1.0
For Per-AP MLD PTK key mode(see subclause 37.16.5.4), the non-AP MLD will generate new PTK with the target AP MLD during the roaming preparation phase.
  The DH parameters will be included in the UHR Link Reconfiguration Request and UHR Link Reconfiguration Response frame.
To protect the MAPC negotiation request/response frame, MAPC PASN is defined by 11bn as well(see subclause 12.17 Multi-AP Coordination Preassociation Security Negotiation).
  MAPC PASN is an extension based on the current PASN protocol.

## Slide 6: Recap: Amendment ordering as of September 2025
Amendment Number | Task Group | Page Count | Projected RevCom Date (submission)
802.11-2024 Amendment 3 | TGbk | 116 | May 2025
802.11-2024 Amendment 4 | TGbf | 232 | May 2025
802.11-2024 Amendment 5 | TGbi | 186 | May 2026
REVmf | TGm | 7039 | February 2028
802.11-2028 Amendment 2 | TGbn | 502 | May 2028
802.11-2028 Amendment 3 | TGbp | TBD | May 2028

## Slide 7: Capture the Market milestone discussion
2027 milestone: quote the following interpretation from 25/1634r1
CNSSP 15 states that by January 1, 2027, all new acquisitions for NSS will be required to be CNSA 2.0 compliant unless otherwise noted. [1] In terms of product readiness to ship the equipment to the government in 2027 time frame, we do not need every item defined in 11bt PAR, and as a minimum, we only need AKMs for CNSA 2.0.
2030 milestone: quote the following from CNSA2.0_FAQ
NSA expects these equipment transitions to be completed by December 31, 2030

## Slide 8: Question to the task group
If 11bt timeline is ahead of 11bn, PQC feature need to be incorporated into 11bn draft.
  We have suffered from such bad experience when we try to merge 11bh feature into 11be draft during the SA ballot.
  Alternatively, PQC feature will be incorporated into 802.11mg after 802.11bn roll-in(during the letter ballot phase. Possibly, Seamless roaming and MAPC Protection feature will be updated to PQC at 2029 or 2030, and then need additional time for certification, is it too late?)
  WIFI8 product will be mature and commercialized in 2027; and then WIFI9 is at 2031.
If 11bt timeline is behind of 11bn(or at the same time), 11bt group shall take into account the PQC feature in SMD and MAPC PASN scenario.
  Seamless roaming and MAPC Protection feature will be upgraded to PQC after 802.11bn feature stable.
  The official release will be at May 2028. Possibly the PQC certification can be done based on WIFI8 device.

## Slide 9: Proposed timeline
Develop PQC feature based on pre-11bn and 11bn device.
  PAR approved Aug 2025
  First TG meeting Sep. 2025
  Initial WG Letter Ballot (D1.0) Mar. 2026*
  Recirculation LB (D2.0) Sep. 2026 **
  Recirculation LB (D3.0) Jan. 2027
  Initial SA Ballot (D4.0) May. 2027
  Recirculation SA(D5.0) Sep. 2027
  SA clean Mar. 2028
  RevCom and SASB approval May. 2028
* Only include the feature for enterprise network to meet 2027 milestone.
** Include the feature for both enterprise and residential network

## Slide 10: Reference
[1]. 25/1376r3 draft updates to PQC PAR
[2]. 25/1377r4 draft updates to PQC CSD

## Slide 11
THANK YOU 

## Slide 12: Timeline motion
  Do you agree the following timeline for TGbt
  PAR approved Aug 2025
  First TG meeting Sep. 2025
  Initial WG Letter Ballot (D1.0) Mar. 2026
  Recirculation LB (D2.0) Sep. 2026
  Recirculation LB (D3.0) Jan. 2027
  Initial SA Ballot (D4.0) May. 2027
  Recirculation SA(D5.0) Sep. 2027
  SA clean Mar. 2028
  RevCom and SASB approval May. 2028