## Slide 1: UCM TIG Closing report for September 2025
Date: 2025-09-19
Authors:
September 2025
Notes: September 2012

## Slide 2: UCM TIG Closing report for September 2025
Agenda: 11-25/1601r4, Minutes: 11-25/1701
2 meeting slots in September
Achievements in September
Officer election: Vice Chair: Charlie Petterson, Secretary: Tuncer Baykas
Presentation and discussion of UCM TIG scope
  Introducing the Unified Channel Model (UCM) TIG, Volker Jungnickel, 11-25/1628r0
  Collected and summarized feedback from on-site WG members (11-25/1601r4, slides 20-23)
UCM TIG timeline (next slide) discussion and approval
Technical presentations
  UCM TIG Unified Channel Model Use Cases proposal, Yanchun Li 11-25/1475r0
  A Spatially Consistent Small-Scale Fading Model for Multiple Frequency Bands, Stephan Jaeckel 11-25/1627r0
September 2025

## Slide 3: UCM TIG Timeline
Sept. 2025: UCM TIG scope, Initial Q&A with WG members, Develop timeline
Nov. 2025: Table of content, initial TIG document with use cases, model description,
First overview of relevant (i.e. multi-band MIMO) measurement results
Jan. 2026 Initial model with known parameters, gap analysis w.r.t. validation in the identified use cases, links to open software
Mar. 2026 Complete TIG draft report for WG review, start comment collection
May 2026 Resolve c.c. comments, finalize TIG report

## Slide 4: UCM TIG Closing report for September 2025
Goals for November
Start to create UCM TIG report
  Agree on ToC and identify key contributors
Finish officer election
Continue technical contributions
  SoA channel models in 802.11, other SDOs and research community
  Identify use cases where existing models do not work
  Write-up formal description of the UCM
  Review existing measurement results for relevant use cases
3 Teleconferences: WEDNESDAY Oct. 8, Oct. 22 and Nov. 4, 10-11 a.m. ET
  Continue technical presentations and discussions
  Identify missing items and issue Call for Contributions at the November meeting
Any contribution in the charter of UCM TIG is welcome!
September 2025