IEEE P802.15

Wireless Personal Area Networks

| Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs) |
| --- | --- |
| Title | Schedule |
| Date Submitted | 23 February, 2011 |
| Source | Clint Chaplin Samsung Electronics 75 W. Plumeria Drive, San Jose, CA 95134 | Voice: +1-408-768-0827 Fax: E-mail: clint.chaplin@gmail.com |
| Re: |  |
| Abstract | 802.15.7 Schedule |
| Purpose | Informational |
| Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. |
| Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15. |

| ~ 802.15.7 Calendar August 2010 ~ |
| --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| 1 | 2 Ad-Hoc | 3 Ad-Hoc | 4 Ad-Hoc | 5 Ad-Hoc | 6 Sridhar and Rick finish implementation of technical comment resolutions into clause 7 | 7 Sridhar and Rick finish implementation of technical comment resolutions into clause 7 |
| 8 Sridhar and Rick finish implementation of technical comment resolutions into clause 7 | 9 Generate “rip” for attendees to review | 10 Review and fix document. Sponsor Ballot Pool Formation closes | 11 Review and fix document | 12 Review and fix document | 13 Review and fix document | 14 Review and fix document All comments must be in |
| 15 Editors finalize document | 16 Editors finalize document Conference call (Monday afternoon ET) | 17 Editors finalize document | 18 Editors finalize document | 19 Send finalized document to Rick Alfin. Send document out for MEC via Clint Chaplin | 20 Start first WG recirculation ballot. | 21 |
| 22 | 23 | 24 | 25 | 26 | 27 | 28 |
| 29 | 30 | 31 | Notes: |

| ~ 802.15.7 Calendar September 2010 ~ |
| --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  | 1 | 2 | 3 | 4 First WG recirculation ballot closes |
| 5 | 6 | 7 Post comment spreadsheet by 15:00 ET | 8 Ad-Hoc | 9 Ad-Hoc | 10 Ad-Hoc | 11 Ad-Hoc |
| 12 | 13 IEEE 802.15 meeting | 14 IEEE 802.15 meeting | 15 IEEE 802.15 meeting | 16 IEEE 802.15 meeting | 17 | 18 |
| 19 | 20 | 21 | 22 | 23 | 24 | 25 |
| 26 | 27 | 28 | 29 | 30 | Notes: |

| ~ 802.15.7 Calendar October 2010 ~ |
| --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  |  |  | 1 | 2 |
| 3 | 4 | 5 | 6 | 7 | 8 EC conditionally approves to forward to Sponsor ballot | 9 |
| 10 | 11 | 12 | 13 | 14 | 15 | 16 |
| 17 | 18 Rick complete editing of D3; send to Sridhar | 19 Sridhar review and give reviewed document back to Rick | 20 Rick send completed draft to 802.15 officers. Start second WG recirculation ballot | 21 | 22 | 23 |
| 24 | 25 | 26 | 27 | 28 | 29 | 30 |
| 31 | Notes: |

| ~ 802.15.7 Calendar November 2010 ~ |
| --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  | 1 | 2 | 3 | 4 Second WG recirculation ballot closes | 5 | 6 |
| 7 | 8 IEEE 802 Plenary | 9 IEEE 802 Plenary | 10 IEEE 802 Plenary | 11 IEEE 802 Plenary | 12 IEEE 802 Plenary | 13 |
| 14 Third WG recirculation ballot started 09:00 EST (14:00 UTC) | 15 | 16 | 17 | 18 | 19 | 20 |
| 21 | 22 | 23 | 24 | 25 | 26 | 27 |
| 28 | 29 Third WG recirculation ballot closes 09:00 EST (14:00 UTC) Teleconference 23:00 29th UTC (00:00 30th CET 17:00 29th CST 15:00 29th PST 08:00 30th Seoul) | 30 Start Initial Sponsor Ballot | Notes: |

| ~ 802.15.7 Calendar December 2010 ~ |
| --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  | 1 | 2 | 3 | 4 |
| 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 19 | 20 | 21 | 22 | 23 | 24 | 25 |
| 26 | 27 | 28 | 29 | 30 Initial Sponsor Ballot Closes | 31 | Notes: |

| ◄ December | ~ 802.15.7 Calendar January 2011 ~ | February ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  |  |  |  | 1 |
| 2 | 3 | 4 | 5 Teleconference 23:00 5th UTC (00:00 6th CET 17:00 5th CST 15:00 5th PST 08:00 6th Seoul) | 6 | 7 | 8 |
| 9 | 10 | 11 | 12 Teleconference 23:00 12th UTC (00:00 13th CET 17:00 12th CST 15:00 12th PST 08:00 13th Seoul) | 13 | 14 | 15 |
| 16 | 17 IEEE 802 Wireless Interim | 18 IEEE 802 Wireless Interim | 19 IEEE 802 Wireless Interim | 20 IEEE 802 Wireless Interim | 21 IEEE 802 Wireless Interim | 22 |
| 23 | 24 | 25 | 26 | 27 | 28 | 29 |
| 30 | 31 | Notes: |

More Calendars:  2011 Calendar, 2012 Calendar, Calendar Template

| ◄ January | ~ 802.15.7 Calendar February 2011 ~ | March ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 6 | 7 | 8 | 9 Teleconference 05:00 10th UTC (21:00 9th PST 23:00 9th CST 06:00 10th CET 14:00 10th Seoul) | 10 Start Recirculation Sponsor Ballot | 11 | 12 |
| 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| 20 Original end of Recirculation Sponsor Ballot | 21 | 22 | 23 Updated Draft 6.0 and supporting documents available | 24 | 25 | 26 |
| 27 | 28 | Notes: |

More Calendars: Mar 2011, Apr 2011, May 2011

| ◄ February | ~ 802.15.7 Calendar March 2011 ~ | April ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  | 1 | 2 | 3 | 4 | 5 Recirculation Sponsor Ballot Closes |
| 6 | 7 | 8 | 9 Teleconference 05:00 10th UTC (21:00 9th PST 23:00 9th CST 06:00 10th CET 14:00 10th Seoul) | 10 | 11 | 12 |
| 13 | 14 IEEE 802 Plenary | 15 IEEE 802 Plenary | 16 IEEE 802 Plenary | 17 IEEE 802 Plenary | 18 IEEE 802 Plenary | 19 |
| 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| 27 | 28 | 29 | 30 | 31 | Notes: |

More Calendars: April, May, June

| ◄ March | ~ 802.15.7 Calendar April 2011 ~ | May ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  |  |  | 1 | 2 |
| 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 10 | 11 | 12 | 13 | 14 | 15 | 16 |
| 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 24 | 25 | 26 | 27 | 28 | 29 | 30 |

More Calendars: May 2011, Jun 2011, Jul 2011

| ◄ April | ~ 802.15.7 Calendar May 2011 ~ | June ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| 15 | 16 | 17 | 18 | 19 | 20 | 21 |
| 22 | 23 | 24 | 25 | 26 | 27 | 28 |
| 29 | 30 | 31 | Notes: |

More Calendars: June, July, August

| ◄ May | ~ 802.15.7 Calendar June 2011 ~ | July ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  | 1 | 2 | 3 | 4 |
| 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 19 | 20 | 21 | 22 | 23 | 24 | 25 |
| 26 | 27 | 28 | 29 | 30 | Notes: |

More Calendars: Jul 2011, Aug 2011, Sep 2011

| ◄ June | ~ 802.15.7 Calendar July 2011 ~ | August ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  |  |  | 1 | 2 |
| 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 10 | 11 | 12 | 13 | 14 | 15 | 16 |
| 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 24 | 25 | 26 | 27 | 28 | 29 | 30 |
| 31 | Notes: |

More Calendars: August, September, October

| ◄ July | ~ 802.15.7 Calendar August 2011 ~ | September ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  | 1 | 2 | 3 | 4 | 5 | 6 |
| 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| 21 | 22 | 23 | 24 | 25 | 26 | 27 |
| 28 | 29 | 30 | 31 | Notes: |

More Calendars: Sep 2011, Oct 2011, Nov 2011

| ◄ August | ~ 802.15.7 Calendar September 2011 ~ | October ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  |  | 1 | 2 | 3 |
| 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| 25 | 26 | 27 | 28 | 29 | 30 | Notes: |

More Calendars: October, November, December

| ◄ September | ~ 802.15.7 Calendar October 2011 ~ | November ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  |  |  |  | 1 |
| 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| 16 | 17 | 18 | 19 | 20 | 21 | 22 |
| 23 | 24 | 25 | 26 | 27 | 28 | 29 |
| 30 | 31 | Notes: |

More Calendars: Nov 2011, Dec 2011, Jan 2012

| ◄ October | ~ 802.15.7 Calendar November 2011 ~ | December ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| 27 | 28 | 29 | 30 | Notes: |

More Calendars: December, January, February

| ◄ November | ~ 802.15.7 Calendar December 2011 ~ | January ► |
| --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  |  | 1 | 2 | 3 |
| 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| 25 | 26 | 27 | 28 | 29 | 30 | 31 |