## IEEE_Cover
March 2011 |  | P802-15-4e_Comment_Entry_Form.xls
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.4e Letter Ballot Comment Resolution Database
Date Submitted | 2010-03-14
Source | Pat Kinney | Voice: +1.847.960.3715
Kinney Consulting
| 251 Clair View Ct, Lake Zurich, IL, USA | E-mail: pat.kinney@ieee.org
Re: | d3P802-15-4e_Draft_Standard
Abstract | 802.15 TG4e Comments for Letter Ballot 69
Purpose | [This document is used to submit comments on TG4e draft amendment, Letter Ballot 69.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
Comment ID | Name | Affiliation | Email | Category | Clause | Sub-clause | Page | Line # | Comment | Proposed Change | Must Be Satisfied? (if so enter Yes) | Group | A/AiP/R/W | Adopted resolution or rationale for reject | Edits complete
1 | Rene Struik | independent | rstruik.ext@gmail.com | E | ii |  |  |  | Suggested remedy: Replace “first” by “third”. | (E) Abstract, p. ii, l. 1: This is the third draft of 802.15.4e, not the first draft. | Yes | editorial | AiP | change to fourth, as the next LB will be D4 | done
2 | Rene Struik | independent | rstruik.ext@gmail.com | T | ii |  |  |  | Abstract, p. ii, l. 1: With the original PAR, 802.15.4e was supposed to be an amendment to 802.15.4-2006 (this is also the PAR mentioned in LB 69 invite). However, the PAR has been revised months ago, resulting in – effectively – 802.15.4i becoming the baseline standard of which TG4e’s efforts are an amendment. Thus, the whole specification is relative to the wrong document. (Please note that, although 802.15.4i is not entirely finished yet, it is in sponsor ballot recirc with very limited number of comments remaining and in stable condition. | Suggested remedy: Update the draft and make this relative to the correct specification, viz. 802.15.4i. | Yes | general | AiP | This has been the plan ever since the start of the TG4i effort and was the reason to amend the PAR.
3 | Rene Struik | independent | rstruik.ext@gmail.com | E | 5 |  |  |  | (E) Participants, p. 5, l. 22-23: Please italicize the names, so as to make this consistent. | Suggested remedy: Change accordingly. | Yes | editorial | A
4 | Rene Struik | independent | rstruik.ext@gmail.com | E | ii |  |  |  | (E) p. ii – Keywords: The keywords are a mixed bag of applications and techniques. Furthermore, there is no mentioning of RFID applications and, e.g., smart grid-type applications. | Suggested remedy: Update the list of keywords, so as to reflect main applications and/or features served with the TG4e amendment. Moreover, distinguish applications (such as process control) from techniques (such as time-synchronized channel hopping. | Yes | editorial | A | Split into two bullets Amendment for - different application domains like Process automation, Factory automation Smart Grid, RFID applications, Commercial applications, etc., - using the techniques and functions like Time Slotted Channel Hopping (TSCH), Low Latency Deterministic Networks (LL), Distributed Synchronous Multi-Channel Extension (DSME), enhancements for Security, low energy, RFID Blink, Enhanced Beacon request (EBR), MAC Performance Metrics (Metrics), Fast association (FastA), Asynchronous Multi-Channel Adaptation (AMCA), etc. | done
5 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §6.2.1.1, p. 32: The PD-DATA.request should have additional parameters, including the channel page and channel numbering (since the specification allows for channel hopping, which seem both under control of the MAC). A similar change seems appropriate for the PD-DATA.confirm primitive (cf. 802.15.4-2006, §6.2.1.2, p. 33) and for the PD-DATA.indication primitive (cf. 802.15.4-2006, §6.2.1.3, p. 34). This would also include adding error status codes that indicate provide more granularity on, e.g., the parameter BUSY_TX (including which channel is busy [the latter may be of interest when performing a channel scan as well). Moreover, it seems more logical to implement channel hopping and corresponding tables as PHY PIB attributes (cf. 802.15.4-2006, §6.4.2, p. 45 ff.). It seems that the PHY-MAC interfaces should also contain references to the current time or the time at which frames are to be sent or are received at the PHY/MAC interface (this is also necessary for incoming and outgoing security processing, cf. 08/828 {technique #1}, 08/848, 08/849, 11/201). I would be happy to help with this (this never made it to pre-drafts of TG4e, as also noted in 08/848r8). | Suggested remedy: Implement accordingly. (Note RS: I already noted this on a conf call in June 2009, but would like to bring this up again. I also saw this still did not make it to Draft D03, hence bringing this up again. | Yes | general | R | Duplicate of CID 662 from LB60 comment resolution. As per the resolution to CID 662: Channel hopping behavior is not implemented in the 802.15.4 MAC. It is noted that there is no behavior added in this amendment that alters the behavior of the PD-DATA request. This proposed change is unnecessary given that the channel page and number are set via the phycurrentchannel and phycurrentpage primitives. It is further noted that PD-DATA SAP is no longer part of the base standard (4i).
6 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.6.1, p. 188, l. 16: Timing information: cryptographic processing assumes that timing information related to time of actual sending of frame is available. This information needs to be propagated ‘down the stack’. Add language to the effect that the current time macCurrentTime will be stored. Add corresponding parameters to all MAC and PHY primitives. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 663 from LB60 comment resolution. This comment was resolved in Draft3.
7 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.6.2, p. 190, l. 24: Timing information: cryptographic processing assumes that timing information related to time of actual receipt of frame is available. This information needs to be propagated ‘up the stack’. Add language to the effect that the current time macCurrentTime will be stored. Add corresponding parameters to all MAC and PHY primitives. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 664 from LB60 comment resolution. This comment was resolved in draft 3
8 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.4.2, p. 160 ff, Table 86: Timing information: cryptographic processing assumes that timing information related to time of actual sending and receipt of frame is available. This information needs to be propagated ‘up and down the stack’. Add language to the effect that the current time macCurrentTime will be stored, as a 48-bit integer, with 14-bit granularity per second (as an alternative, one may store this information in the PIB table for security-related attributes – cf. 802.15.4-2006, §7.6.1, p. 206 ff). Add corresponding parameters to all MAC and PHY primitives. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 665 from LB60 comment resolution. The PIB is an abstract interface and does not specify a physical implementation, as such the implementation is not in scope of this standard.
9 | Rene Struik | independent | rstruik.ext@gmail.com | T | 11 |  | 7.1.1.1.1 |  | (TR) §7.1.1.1.1, p. 11: 802.15.4-2006, §7.5.8.2.1, p. 202, l. 29-31: Add FrameCounterMode parameter; add macCurrentTime parameter. Adapt MAC sublayer service primitives (§7.1) accordingly. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 666 from LB60 comment resolution. This comment was resolved in draft 3
10 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.1, p. 203, Step f): Obtain macFrameCounter attribute from macCurrentTime parameter and locally maintained info (so-called frame counter conversion), such that value never decreases. This correlates frame counter to time parameter. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 668 from LB60 comment resolution. This comment was resolved in draft 3
11 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.1, p. 203, Step i), iii): Set frame counter to representation of macFrameCounter compliant with FrameCounterMode parameter. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 669 from LB60 comment resolution. This comment was resolved in draft 3
12 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.1, p. 203, Step m, l. 35: Mute frame header fields in the protected frame compliant with representation mode parameter settings. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 670 from LB60 comment resolution. This comment was resolved in draft 3
13 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.3, p. 204, l. 37-41: Add FrameCounterMode parameter; add macCurrentTime parameter. Adapt MAC sublayer service primitives (§7.1) accordingly. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 671 from LB60 comment resolution. This comment was resolved in draft 3
14 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.3, p. 205, Step i), l. 36-39: Reconstruct frame counter from representation hereof in auxiliary security header, taken into account the frame counter mode and locally maintained info as to the current time (so-called frame counter conversion). | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 672 from LB60 comment resolution This comment was resolved in draft 3
15 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.3, p. 205, Step j), l. 40-43: Correlate the frame counter and the current time macCurrentTime; reject frame if these differ by more than a set amount (presumably, because the frame was stale). This provides timeliness and facilitates significant reduction of the storage cost for frame counters on recipient’s device (since one does not need to store these for stale communications). | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 673 from LB60 comment resolution. This comment was resolved in draft 3
16 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.3, p. 205, Step k), l. 44-47: Reconstruct muted frame header fields from information in the received frame and locally maintained status information. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 674 from LB60 comment resolution This comment was resolved in draft 3
17 | Rene Struik | independent | rstruik.ext@gmail.com | T | 168 |  | 7.5.8.1.4 |  | (TR) §7.5.8.1.4, p. 168; 802.15.4-2006, §7.5.6.2, p. 203, Table 93: represent frame counter as 6-octet integers, rather than 4- or 5-octet integers. Adapt overflow checks with security processing of outgoing frames (§7.5.8.2.1) and of incoming frames (§7.5.8.2.3) accordingly (i.e., replace 0xffffffff by 0xffffffffffff). This implements time-correlated frame counters. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Repeat of CID 681 from LB60 comment resolution. This comment was resolved in draft 3
18 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.1: Proper implementation of overhead reduction techniques assumes that one can reconstruct muted fields upon receipt, thereby requiring shared conventions between sender and recipient(s) as to which representation of data elements to choose (if there is more than one option). This is currently still insufficiently specified (also with §7.5.8.2.3 and with §7.5.6.1 and §7.5.6.2). | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Duplicate of CID 682 from LB60 comment resolution. This comment was resolved in draft 3
19 | Rene Struik | independent | rstruik.ext@gmail.com | T | 164 |  | 7.5.6.2 |  | (TR) §7.5.6.2, pp. 164-166: The current text seems to be incorrect (if only because one of the first actions is to send an acknowledgement frame, irrespective of first-third level filtering). | Suggested remedy: Implement accordingly. Please also cf. 11/201 (which was originally already included in 08/848r7). Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | general | R | Comment's argument is non persuasive in that the text clearly addresses the commenter's concerns by defining the 1st, 2nd, and 3rd level filtering and the proper outcomes. Additionally, proposed action is not sufficiently descriptive.
20 | Rene Struik | independent | rstruik.ext@gmail.com | T | 7 | 7.5.6.1 | 165 | 21 | (TR) §7.5.6.2, p. 165, l. 21-24: The notion of short address causes seems ill-motivated. This aside, lots of addressing tables, e.g., those used with security (cf., e.g., 802.15.4-2006, §7.6.1, Table 93, p. 209) assume only extended addresses or 16-bit short addresses. The need for 8-bit addresses is unclear, esp. since low latency frames with short FCF do not specify any addressing information in the frame to be sent. | Suggested remedy: Remove all references to 8-bit addresses. If one really wishes to keep these in, one should do extensive modifications to all tables to cater to this (but latency does not seem a motivation, since normally not sent, and making implementations more arcane, so easiest fix would be to just remove these altogether). | Yes | LL | R | Repeat of CID 659 from LB60 comment resolution. Comment and proposed change are determined to be non persuasive by TG4e. It is noted that LL-networks use data frames with addressing in shared group time slots. An 8-bit address would reduce the number of octets of the MSDU.
21 | Rene Struik | independent | rstruik.ext@gmail.com | T |  |  |  |  | (TR) 802.15.4-2006, §7.5.8.2.1: Processing of secured acknowledgement frames is still not properly supported. As an example, the procedure with D3, §7.2.2.3.1, p. 75, completely breaks semantic security of the CCM* mode of operation. Add language on how to compress auxiliary security header and other header fields. | Suggested remedy: Implement accordingly. Please also cf. 11/201. Note RS: this was previously included in 08/828 {technique #1}, 08/848, 08/849 and supposed to have made it to Draft D03 of TG4e, but did not yet. | Yes | ESOR | R | Repeat of CID 679 from LB60 comment resolution. This comment was resolved in draft 3
22 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 2 | 11 | "periodicly" | "periodically" | Yes | editorial | A | 12 replacements | done
23 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 4 | 11 | "in7.2.2.5.2" | "in 7.2.2.5.2" | Yes | editorial | A |  | done
24 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 6 | 18 | "Since some of the retransmitted frames (in R1, R2, …, RN time slots) may fail. The bitmap in such a case is used for acknowledging the successful transmissions in R1, R2, …, RN time slots." | "Since some of the retransmitted frames (in R1, R2, …, RN time slots) may fail, the bitmap in such a case is used for acknowledging the successful transmissions in R1, R2, …, RN time slots." | Yes | editorial | A |  | done
25 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 8 | 19 | "and the IE content a payload" | "and the IE content (a payload)" | Yes | editorial | AiP | Deleted " a payload" | done
26 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 11 | 1 | "periodicly" | "periodically" | Yes | editorial | A | See CID 22 | -
27 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  | 7.1.3.4.1 | 22 | 21 | Missing indication of what to change. Also missing commas | Add indication of what to change (underline LowLatencyNetworkInfo, ChannelOffset, HoppingSequenceLength, Hopping Sequence) Add commas | Yes | editorial | A |  | done
28 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 23 | 7 | In the figure: "coodinator" | "coordinator" | Yes | editorial | A |  | done
29 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | T |  |  | 27 | 1 | "macHoppingEnabled or macTSCHenabled" | "macHoppingEnabled or macTSCHenabled are TRUE" | Yes | editorial | A |  | done
30 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 31 | 11 | Missing indication of what to change. | Add indication of what to change (underline frameControlOptions, headerIElist, payloadIElist) | Yes | editorial | A |  | done
31 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 32 | 1 | "Determines which Header Information Elements are sent frame." | "Determines which Header Information Elements are sent in the frame." | Yes | editorial | A |  | done
32 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 33 | 6 | "(see )" See what? | Fill in reference | Yes | editorial | A |  | done
33 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 33 | 31 | "The MLME then switch" | "The MLME then switches" | Yes | editorial | A |  | done
34 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 33 | 33 | "where n is the value of the ScanDuration parameter have elapsed" missing comma | "where n is the value of the ScanDuration parameter, have elapsed" | Yes | editorial | A |  | done
35 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | T |  |  | 36 | 1 | Why isn't SDIndex in the table? It's in the list of parameters | Either add SDIndex to the table or delete from the list of paramaters. | Yes | DSME | AiP | Delete the parameter.
36 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 35 | 8 | Why is SuperframeOrder underlined? It hasn't been added. | Remove underlining | Yes | DSME | A
37 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 37 | 3 | "it replies channel hopping sequence in an association response command." | "it replies with the channel hopping sequence in an association response command." | Yes | editorial | A |  | done
38 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 36 | 1 | Is it "CoorRealignment" or "CoordRealignment"? |  | Yes | editorial | A | 10 replacements including Mode, Security, etc. | done
39 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 36 | 1 | Is it "CoorRealignSecurityLevel" or "CoordRealignSecurityLevel"? |  | Yes | editorial | A | See CID 38 | -
40 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | T |  |  | 36 | 1 | Is it "CoorRealignKeyIdMode" or "CoordRealignKeyIdMode"? Both are used | Pick one and be consistent | Yes | editorial | A | See CID 38 | -
41 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 36 | 1 | Is it "CoorRealignKeySource" or "CoordRealignKeySource"? |  | Yes | editorial | A | See CID 38 | -
42 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 36 | 1 | Is it "CoorRealignKeyIndex" or "CoordRealignKeyIndex"? |  | Yes | editorial | A | See CID 38 | -
43 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | T |  |  | 47 | 11 | "DiscoveryModeStatus" is not in Table 78j | Put in Table 78j | Yes | LL | AiP | remove parameter DiscoveryModeStatus from primitive. There is already a parameter called status.
44 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 64 | 8 | "16bit" | "16-bit" | No | editorial | A | 2 replacements | done
45 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 65 | 12 | "16bit" | "16-bit" | No | editorial | A | See CID 44 | -
46 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 74 | 16 | "If the frame version in b10" | "If the frame version is b10" | Yes | ESOR | A
47 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | T |  |  | 75 | 27 | "the Auxiliary Security Header field match the corresponding field of the frame that is being acknowledged" | "the Auxiliary Security Header field shall match the corresponding field of the frame that is being acknowledged" | Yes | ESOR | A
48 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 76 | 16 | "If the frame version in b10" | "If the frame version is b10" | Yes | ESOR | A
49 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 83 | 10 | "the size" | "The size" | Yes | editorial | A |  | done
50 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 83 | 11 | "of time slots used uplink transmissions by the sensor nodes" | "of time slots used for uplink transmissions by the sensor nodes" | Yes | editorial | A |  | done
51 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 86 | 9 | "otherwise.." | "otherwise." | Yes | editorial | A |  | done
52 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 86 | 13 | "zero" | "zero." | Yes | editorial | A |  | done
53 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 94 | 20 | "7.2.2.1.27.2.2.1.2" | "7.2.2.1.2" | Yes | editorial | A |  | done
54 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | E |  |  | 96 | 12 | "in octet." | "in octets." | Yes | editorial | A |  | done
55 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | T |  |  | 96 | 14 | "This field is expressed in bitmap format which orderly represents the schedule of beacons, Corresponding bit in the bitmap shall be set to one if a beacon of neighbor devices is allocated in that SD, otherwise it is set to zero." | "This field is expressed in a bitmap format which represents the schedule of beacons. Each corresponding bit in the bitmap shall be set to one if a beacon of neighbor devices is allocated in that SD, otherwise it is set to zero." | Yes | DSME | A
56 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 3 | 3 | 2 | 10 | definition of enhanced beacon is in parts not specific enough | watertighten definition of enhanced beacon | No | EB | R | Comment and Proposed change are not sufficiently specific to justify the merit in modifying draft text
57 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 3 | 3 | 2 | 17 | The definition of LLDN device confuses uplink communication and bidirectional communication. | fix data communication directions in definition | Yes | LL | AiP | Change definition to: LLDN device: A device in a low latency deterministic network (LLDN) that is associated to a LLDN coordinator. The exchange of data frames and LL-data frames may be unidirectional (uplink only) from the LLDN device to the LLDN coordinator or it may be bidirectional.
58 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 3 | 3 | 2 | 28 | definition of downlink is missing | add definition for "downlink" similar to definition of uplink | Yes | LL | AiP | Add definition: downlink: The data communication is from the PAN coordinator to the PAN device.
59 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 5 | 5.5.1 | 4 | 8 | The superframe definition of 15.4-2006 should be at the same level as the 3 newly introduced ones. | Make 5.5.1 of 15.4-2006 to 5.5.1.1 with a brief introductory text based on lines 8-12 of 15.4e D03. | No | editorial | A |  | done
60 | Michael Bahr | Siemens AG | bahr@siemens.com | G | 7 | 7 | 11 | 16 | There are incorrect indications of changed text of 15.4-2006 throughout the draft D03. | Check whole draft standard and correctly indicate changes to 15.4-2006 | Yes | editorial | A | See also CID 4, 27, etc. | -
61 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1 | 67 | 11 | In Figure 41, upper and lower case of unchanged field names are not the same as in 15.4-2006 | Correct upper/lower case in Figure 41 (e.g. Frame Control, Sequence Number) | No | editorial | A |  | done
62 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1 | 67 | 11 | The length of 1 octet of the Auxiliary Security Header field is new. | Underscore "1/" | No | editorial | A |  | done
63 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1 | 67 | 11 | Information elements contain control information of the MAC. Therefore, they have to be in the MAC header. | Remove field "Information Elements" Rename field "Header Ies" into "Information Elements" or whatever it was in the original submission about frame types | Yes | ESOR | AiP | Incoroporate changes from 15-11-0195-00-004e which clarifies payload (type = 1) IE form.
64 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1 | 67 | 11 | Payload IEs are just the payload and only of meaning to the NHL. They are part of the Frame payload. They should be removed, because the next higher layer has to do the semantics, not the MAC. | Remove field "Payload Ies" Make the border between MHR and MAC payload between "Header IEs" which is to be renamed to "Information Elements" and "Frame Payload". | Yes | ESOR | R | MAC payload in the base standard may contain information used by the MAC (example,beacon frames where Superframe specification is MAC payload). The distinction between MAC header and MAC paylaod is important as some defined IEs (example TSCH) need to be securable. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
65 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1 | 68 | 6 | Low Latency and Multi purpose are actually frames. | Change into "The Frame Control field of Low Latency frames and Multi-purpose frames is specified in 7.2.2.5.1.2 and 7.2.2.6.2." | No | ESOR | A
66 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1 | 68 | 9 | Caption of Figure 42 does not show the changes to 15.4-2006 | indicate changes to 15.4-2006 | No | editorial | A |  | done
67 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.1 | 68 | 11 | Frame Type is a subfield | Frame Type subfield | No | editorial | R | According to the decision of 4i, a subfield of 4-2006 shall be named field in 4-2011 and this applies also to the pending Amendments. | -
68 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.1 | 68 | 13 | use consistent spelling of multi-purpose | use multi-purpose throughout the draft standard | No | editorial | R | Multipurpose is correct English, see also comment resolution to LB60. | -
69 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.2 | 68 | 17 | Security Enabled is a subfield | Security Enabled subfield | No | editorial | R | See CID 67. | -
70 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.3 | 68 | 18 | Frame Pending is a subfield | Frame Pending subfield | No | editorial | R | See CID 67. | -
71 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.1.3 | 68 | 19 | The new text will never be considered because the paragraph before it will set the Frame Pending field to zero in any case. | put new text to correct place (last before last paragraph) | No | ESOR | A
72 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.3 | 68 | 20 | "can be" has to be "may be" | as in comment | No | ESOR | A | Verify with WG Tech Editor (Gilb)
73 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.1.3 | 68 | 21 | Which device? Transmitter or receiver? | specify | No | LE | AiP | replace "device" with "transmitting device"
74 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.3 | 68 | 21 | missing s | expects | No | editorial | A |  | done
75 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.4 | 69 | 3 | Acknowledgment Request is a subfield | Acknowledgment Request subfield | No | editorial | R | See CID 67. | -
76 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.5 | 69 | 4 | PAN ID Compression is a subfield | PAN ID Compression subfield | No | editorial | R | See CID 67. | -
77 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.5a | 69 | 19 | IE List Present field and Sequence Number Suppression field are in the wrong order. | swap IE List Present field and Sequence Number Suppression field. | No | ESOR | A | Sub-clauses 7.2.1.1.5a becomes 7.2.1.1.5b and 7.2.1.1.5b becomes 7.2.1.1.5a.
78 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.5a | 69 | 19 | IE List Present is a subfield | IE List Present subfield | No | editorial | R | See CID 67. | -
79 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.5b | 69 | 22 | Sequence Number Suppression is a subfield | Sequence Number Suppression subfield | No | editorial | R | See CID 67. | -
80 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.6 | 70 | 2 | Destination Addressing Mode is a subfield | Destination Addressing Mode subfield | No | editorial | R | See CID 67. | -
81 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.6 | 70 | 16 | This paragraph is new text. | Underline | No | editorial | A |  | done
82 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.7 | 70 | 18 | Frame Version is a subfield | Frame Version subfield | No | editorial | R | See CID 67. | -
83 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.8 | 70 | 26 | Source Addressing Mode is a subfield | Source Addressing Mode subfield | No | editorial | R | See CID 67. | -
84 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.1.8 | 71 | 5 | This paragraph is new text. | Underline | No | editorial | A |  | done
85 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.7a | 72 | 1 | What is "the number of each type of information element" | be specific | Yes | ESOR | AiP | Change to: "This standard does not limit the number of Information Elements within the IE list."
86 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.7a | 72 | 2 | Application requirements are sort of "ignored" by the MAC. So the determination of whatever has to be done by the MAC. | remove "appliation requirements" and insert correct term. | Yes | ESOR | AiP | Resolved by CID #85
87 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.7a | 72 | 3 | Payload Information Elements are an ill concept and are to be removed. Therefore, there is no need to call something "Header Information Elements" | Remove "Header" lower case "element" | Yes | ESOR | R | The commenter's claim of "an ill concept" is not persuasive, the concensus of TG4e is that the concept is valid. See CID #64 for further explanation.The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
88 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.7a | 72 | 4 | considered is no standards language. Either they are part or they aren't. | remove "considered" | No | ESOR | A
89 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.7a | 72 | 4 | The list of information elements always needs termination. | remove the last two sentences of this paragraph. | Yes | ESOR | AiP | Remove last two sentences as suggested because they are redundant (already stated in prior paragraph). The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
90 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.7a | 72 | 5 | need reference to definition of information elements. | add at the end of clause new paragraph pointing to 7.2.4 where information elements are defined. | No | ESOR | R | Reference to 7.2.4 is given in prior paragraph.
91 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.7a | 72 | 6 | Payload information elements are just the payload and only of meaning to the NHL. They are part of the Frame payload. The concept of payload IEs has to be removed, because the next higher layer has to do the semantics, not the MAC. | delete paragraph on lines 6-8, delete concept of payload IEs from the whole draft standard. | Yes | ESOR | R | See explanation for CID #64. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
92 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.1.7a | 72 | 6 | There are only Information elements, and they are part of the MHR. There is no distinction between header and payload IEs. More specifically, payload IEs do not belong to the MAC and have to be removed. | Change Figure 42b so that the fields read: Information Element #1 (Octets: variable) … Information Element #n (Octets variable) List Termination IE (2) | Yes | ESOR | R | The concept as accepted by the WG has many uses. The form provides encapsulation of higher layer information; it provides for IE content longer than 511 octets (in support of proposed PHYs that need this capability); it provides for extensibility beyond a fixed length name space.
93 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.1.7a | 72 | 9 | The field is called "Information Elements" and format is written twice | Format of Information Elements field | No | ESOR | A
94 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.1 | 72 | 11 | 7.2.2.1 always had the heading "Beacon frame format" | remove underscore | No | editorial | A |  | done
95 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1 | 72 | 13 | everything defined in 7.2.2.1 is a standard beacon. | use correct and unique differentiator. | Yes | EB | AiP | change last sentence of first paragraph of 7.2.2.1 to: An enhanced beacon contains only IEs: the enhanced beacon is differentiated from the legacy beacon by the frame version being set to b10.
96 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.1 | 72 | 14 | This clause is about the Beacon, not an enhanced beacon. | Use proper wording in order to define an enhanced beacon. | No | EB | AiP | See CID 95 Enhanced beacon is a new form of the beacon frame (same frame type value) so it is appropriately described inthe beacon frame subclause. Resolution to CID 95 clarifies the differentiation. CID 98 clarifies the figure by splitting into two figures.
97 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1 | 72 | 17 | It is nowhere defined, when the GTS fields are present or not present. | Specify when the GTS fields and other fields that might not be present in a beacon frame are present or are not present. | Yes | EB | AiP | See CID 95 and 98.
98 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1 | 72 | 17 | There is confusion in distinguishing a beacon and an enhanced beacon. The enhanced beacon is still a beacon frame because it has the same frame type called beacon. It has to be clearly specified what makes a beacon an enhanced beacon, and what are the differences. | Remove confusion about beacon and enhanced beacon. Provide specification what an enhanced beacon is. Change description in new text so that this correct new specification of an enhanced beacon is followed. | Yes | EB | AiP | The figure confuses EBs and legacy beacons; change editorial instructions to "add figure…", give figure unique #, and change caption to "Enhanced Beacon"; show legacy fields from figure (Figure in doc 15-11-0196-01) Also see CID 95 for clarification
99 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1 | 72 | 22 | Payload IEs are an ill concept. There are only information elements, and these are part of the MHR. | Make fields "Header IEs" and "Payload IEs" a single field called "Information Elements" as in the general frame format. Remove field "Information Elements" from the last row of Figure 44. Make the border between MHR and MAC payload between the new field "Information Elements" and "Superframe Specification" | Yes | ESOR | R | See CID 64 for explanation of why Payload IEs are useful and nececesary; See CID 98 for clarification of figure 44.
100 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.1 | 72 | 22 | Several field lengths have new additional lengths, but they are not indicated | underline new field lengths in Figure 44 | No | ESOR | AiP | See CID 98 for corrections to figure 44.
101 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1.1 | 72 | 27 | There is some confusion between a beacon and an enhanced beacon. The distinction between the two has to be based from the specification. Especially, the enhanced beacon is also a beacon frame because it has frame type 000. | find better wording and description that has its basis in the definition of the beacon frame type. | No | EB | AiP | See CID 95 and CID 98
102 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.1.1 | 73 | 2 | 15.4e D03 is based on 15.4-2006, so the Source Addressing Mode is a subfield, not a field. Furthermore, this change is not indicated! | Throughout the 15.4e draft, correct all fields that are actually subfields according to 15.4-2006 to subfield. | No | editorial | R | See CID 67. | -
103 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1.1 | 73 | 3 | insertion "or enhanced beacon" is not necessary because enhanced beacon is still a feacon frame. | remove insertion "or enhanced beacon" | No | EB | A
104 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1.1 | 73 | 11 | The last sentence of this paragraph about macEBSN being present in a DSME-enabled PAN has nothing to do with the description of the Sequence Number field. | remove last sentence. | No | DSME | R | It is related to EBSN. DSME PAN uses enhanced beacon and DSME PAN must use beacon sequence number. This is right place to describe this.
105 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.1.1 | 73 | 17 | grammar | … contain the MAC address of … | No | editorial | A |  | done
106 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1.1 | 73 | 17 | Isn't this also the case for a non-enhanced beacon? | remove "enhanced". In general, write all allowed cases here. | No | EB | A
107 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1.1a | 73 | 24 | Information Elements are part of the MHR | Remove heading 7.2.2.1.1a | Yes | ESOR | R | There are two types: see 15-11-0196-01 which provides updates for the figures to clarify that IEs can be part of header and payload. This is important because in some cases (ie TSCH) the IE must be included in the scope of MAC payload so it may be secured.
108 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.1.1a | 73 | 25 | again, the setting of the IE list present subfield is not only valid for an enhanced beacon. | remove "enhanced" | No | ESOR | R | Refer to CID98, a legacy beacon (version < 2) can't have those FCF bits so it can't have IEs
109 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.1.1a | 73 | 25 | subfield names are upper case | "IE List Present subfield" | No | editorial | AiP | capitalization accepted; subfield rejected | done
110 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.2 | 74 | 2 | Payload IEs are an ill concept. There are only information elements, and these are part of the MHR. Payload Ies are a not recognizable part (at MAC layer) of the Data payload. | Make fields "Header IEs" and "Payload IEs" a single field called "Information Elements" as in the general frame format. Remove field "Information Elements" from the last row of Figure 52. Make the border between MHR and MAC payload between the new field "Information Elements" and "Data Payload" | Yes | ESOR | R | see CD #107. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
111 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.2 | 74 | 2 | Several field lengths have new additional lengths, but they are not indicated | underline new field lengths in Figure 52 | No | editorial | A |  | done
112 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.2 | 74 | 2 | Several field lengths have new additional lengths, but they are not indicated | underline new field lengths in Figure 54 | No | editorial | A |  | done
113 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.2.1 | 74 | 7 | line 7 is no text of 15.4-2006. | Correctly indicate changes to 15.4-2006. | No | editorial | A |  | done
114 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.3 | 74 | 26 | The frame is called "Acknowledgment" | remove "Enhanced" | Yes | ESOR | A
115 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.3 | 74 | 28 | This new paragraph is very easily leading to a sloppy specification of the ack frame, that is, there will be easily confusion about the ack and the enhanced ack. | provide a standardslike specification of ack and enhanced ack, which is still and ack frame. | Yes | ESOR | R | Commenter provided no specific proposed change. The current text appears appropriate for the standard.
116 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.3 | 75 | 1 | Payload IEs are an ill concept. There are only information elements, and these are part of the MHR. Payload Ies are a not recognizable part (at MAC layer) of the Data payload. | Make fields "Header IEs" and "Payload IEs" a single field called "Information Elements" as in the general frame format. Remove field "Information Elements" from the last row of Figure 53a. Make the border between MHR and MAC payload between the new field "Information Elements" and "Data Payload" | Yes | ESOR | R | See CID #107. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
117 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.3 | 75 | 1 | An Acknowledgment does not have Data Payload. It has an Acknowledgment Payload. | Change "Data Payload" into "Acknowledgment Payload" in Figure 53a | No | ESOR | AiP | Resolved by updated figure 53a in 15-11-0196
118 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.4 | 76 | 2 | Payload IEs are an ill concept. There are only information elements, and these are part of the MHR. Payload Ies are a not recognizable part (at MAC layer) of the Data payload. | Make fields "Header IEs" and "Payload IEs" a single field called "Information Elements" as in the general frame format. Remove field "Information Elements" from the last row of Figure 54. Make the border between MHR and MAC payload between the new field "Information Elements" and "Command Payload" | Yes | ESOR | R | See CID #107. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
119 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.6.1 | 84 | 19 | Payload IEs are an ill concept. There are only information elements, and these are part of the MHR. Payload IEs are a not recognizable part (at MAC layer) of the Data payload. | Make fields "Header IEs" and "Payload IEs" a single field called "Information Elements" as in the general frame format. Remove field "Information Elements" from the last row of Figure 54j. Make the border between MHR and MAC payload between the new field "Information Elements" and "Payload" | Yes | ESOR | R | See CID #107. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
120 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.6.1 | 84 | 19 | The field "payload" needs a qualifier and is upper case. | as in comment | No | ESOR | AiP | Make uppercase. Don't know what qualifier it needs, "Payload" is correct. See also 15-11-0196 which updates the figure and is much clearer.
121 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.6.2 | 85 | 9 | "#" is informal and not suitable as a name of a subfield | use same name as in frame control definition of general frame format | No | ESOR | A | change "#' to "Number"
122 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.6.2 | 85 | 9 | subfield names are all upper case (all words of subfield name) | make all words of subfield names in Figure 54k upper case | No | editorial | A |  | done
123 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.6.2.1 | 85 | 10 | Frame Type is a subfield as well as all other subfields of the Frame Control field | make all 7.2.2.6.2.x field into subfields | No | editorial | R | See CID 67. | -
124 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.6.2.2 | 85 | 13 | Use same name in figure 54k and text | as in comment | No | ESOR | A
125 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.6.3 | 88 | 3 | The application is out of scope of 15.4. So there cannot be any application-specific settings. | Define RFID Multi-Purpose Blink frame through its settings, not through being an application. | Yes | 4F | AiP | change "application specific MHR settings" to "special purpose MHR settings" change 7.2.2.6.3.1 to Multipurpose blink frame
126 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.63.1.1 | 88 | 6 | 15.4 only specifies the frame formats and MAC mechanisms, but no application mechanisms. Therefore, it is out of scope to say "The blink is a periodic transmission from tagged assets that is received by RFID reader infrastructure." The only way to say "RFID" is to say that the blink is used in RFID applications. | Remove the first sentence or reword according to comment. | Yes | 4F | AiP | change first two sentences to read: "The blink is a periodic transmission that has been designed to be of minimal size to make its transmission require the lowest amount of energy to yield maximum battery life."
127 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.2.63.1.1 | 88 | 12 | "#" is not suitable as a field name. Use same names in Figure 54l and in text. | as in comment | No | ESOR | A | change to "Number"
128 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.2.6.3.2.1 | 89 | 3 | How is an LE multi-purpose Wake-up frame distinguished from other Multi-Purpose frames? Or in other words, how do I know which fields are in the Multi-purpose frame? | Define the unique characteristics that make a multi-purpose frame to an LE Multi-purpose Wake-up frame | Yes | LE | AiP | edit draft as per 15-11-0262-02
129 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.4.1 | 90 | 9 | What are "unknown ID elements" | use correct term | No | ESOR | AiP | change to "elements with unknown ID values"
130 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.1 | 90 | 11 | It's not the user, it's the implementer. | change "user" into "implementer" | No | editorial | AiP | Deleted user | done
131 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.1 | 90 | 12 | Payload IEs are an ill concept. There are only information elements, and these are part of the MHR. Payload IEs are a not recognizable part (at MAC layer) of the Data payload. | Change paragraph at lines 12-16 into "Information Elements are part of the MHR." | Yes | ESOR | R | See CID #98. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
132 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.1 | 90 | 12 | Since payload IEs are an ill concept, the last sentence is not needed. | remove last sentence. | Yes | ESOR | R | Payload IEs are well conceived and very useful, however to enhance clarification remove "considered" from sentence.
133 | Michael Bahr | Siemens AG | bahr@siemens.com | E | 7 | 7.2.4.1 | 90 | 17 | Avoid using IE as a noun. | Information Element | No | editorial | R | acronym can be used as a noun
134 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.1 | 90 | 21 | Having the Element ID going across an octet border is not a good idea. | Remove the type field, because it is not needed since payload IEs should be deleted. | Yes | ESOR | R | There is no way to avoid octet boundaries for fields that are longer than 8 bits. The Type field is essential: see doc 15-11-0195 for details.
135 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.1 | 90 | 22 | Since this standard defines the Information elements, it also manages them. Therefore, there cannot be any unmanaged spaces. | remove line 22 on page 90 remove table 80i on page 91 | Yes | ESOR | R | Managed and Unmanaged are terms agreed upon by the task group and are valid, necessary concepts. To further clarify the concept, add definitions to clause 3 for "managed IE namespace" and "unmanaged IE namespace".
136 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.1 | 91 | 3 | Payload IEs are an ill concept. Group ID 0 is part of the Data Payload, Group ID 1 is a MAC Command, and Group ID 2 is also usually a MAC Command. So, there is no need for Payload IEs | remove payload IEs delete text on page 90 starting at line 3 till the end of the page. | Yes | ESOR | R | comment is not persuasive, see CID 98. Also apply changes form 15-11-0195 to correct and clarify type 1 IE form.
137 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.2 | 92 | 1 | Managed ID space is an artifical term. | Simply use Element ID | Yes | ESOR | R | Comment is not persuasive, text is not changed
138 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.2 | 92 | 2 | 20 implementation specific IEs are 19 too many. Only one is needed. | use only one element ID for implementation specific, and it should be called "vendor specific" | Yes | ESOR | R | Due consideration was given to this concept and justification was provided in prior comment resolution to similar comment.
139 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.2 | 92 | 4 | Payload IEs are an ill concept, and Group 0 is actually part of the Data payload and transparent to the MAC. Furthermore, there is no content in Table 80m anyways (that is, no element IDs defined) | Remove Table 80m | Yes | ESOR | R | Comment is non persuasive, refer to doc 15-11-0195 which clarifies and corrects payload IE definitions. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
140 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.2 | 93 | 1 | Payload IEs are an ill concept, and Group 1 is actually a MAC command. | Remove Table 80n and make these MAC command frames. | Yes | ESOR | R | Comment is non persuasive, refer to doc 15-11-0195 which clarifies and corrects payload IE definitions. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
141 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.2 | 93 | 3 | Payload IEs are an ill concept, and Group 2 is usually a MAC command. Bit it doesn't matter anyways, because there is no content in Table 80o (that is, no element IDs defined) | Remove Table 80o | Yes | ESOR | R | Comment is non persuasive, refer to doc 15-11-0195 which clarifies and corrects payload IE definitions. The issue of deteriming where the payload IE list stops is clarified via 15-11-0195-01)
142 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.3.7 | 98 | 6 | The text makes clear that the Group ACK is actually a frame, not an Information element. | Remove the Group ACK information element and define the Group ACK frame as Acknowledgment type of the Acknowlegment frame. | No | DSME | AiP | page 98 line 10: change "only a single GASCK frame" to "only a single enhanced ACK with the header IE value 0x1f"
143 | Michael Bahr | Siemens AG | bahr@siemens.com | T | 7 | 7.2.4.4 | 103 | 22 | Even with encouragement to ensure correct indentification of a specific implemente's information element, it does not work. It is still possible, that two different implementation specific IEs result in the same bitstream and cannot be distinguished. This standard actually has to define the differentiation mechanism. | Define a differentiation mechanism. 802.11 uses the OUI for this. | Yes | ESOR | R | Use of OUI was considered by TG4e (and may be used by upper layer protocols) but consensus was that it was not necessary and is burdensome. Current form is more flexible and works acceptably.
144 | Michael Bahr | Siemens AG | bahr@siemens.com | G | frontmatter | Participants | v | 11 | The lists of working group members and sponsor ballot pool member has to follow the IEEE 802 rules. | Add corresponding text and placeholders for names | No | editorial | AiP | Added the working group name. The placeholder is there saying that IEEE should provide this information. | done
145 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 5 | 5.5.3 | 8 | 19 | What is "IE content a payload"? Is this "IE content payload"? | Clarify and correct. | Yes | ESOR | AiP | see CID 25
146 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.1.1.1.1 | 12 |  | In the Type of headerIElist, "(see Figure 54m)" is an incorrect cross-reference. | Correct | Yes | ESOR | A | on Table 41 changeheaderIElist from Figure 54m to Figure 54n
147 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.1.1.1.1 | 12 |  | In the Type of payloadIElist, "(see Figure 54n)" is an incorrect cross-reference. | Correct | Yes | ESOR | A | change the Firgure 54n reference to Figure 54o
148 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.1.11.1.1 | 32 |  | In the Type of headerIElist, "(see Figure 54m)" is an incorrect cross-reference. | Correct | Yes | ESOR | A | on Table 41 changeheaderIElist from Figure 54m to Figure 54n
149 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.1.11.1.1 | 32 |  | In the Type of payloadIElist, "(see Figure 54n)" is an incorrect cross-reference. | Correct | Yes | ESOR | A | change the Firgure 54n reference to Figure 54o
150 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.1.14.1.1 | 37 |  | In the Type of headerIElist, "(see Figure 54m)" is an incorrect cross-reference. | Correct | Yes | ESOR | A | on Table 41 changeheaderIElist from Figure 54m to Figure 54n
151 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.1.14.1.1 | 37 |  | In the Type of payloadIElist, "(see Figure 54n)" is an incorrect cross-reference. | Correct | Yes | ESOR | A | change the Firgure 54n reference to Figure 54o
152 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.1.1.1.1 | 12 |  | In the Description of headerIElist it says "Determines which Header Information Elements are sent frame…." Is this typo of "Determines which Header Information Elements are sent in the frame…."? | Clarify and correct. | Yes | ESOR | A | change to Determines which Header Information Elements are sent
153 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.2.1.7a | 71 | 31 | Reference to Figure 42a is incorrect. | Change Figure 42a to Figure 42b. | Yes | editorial | A |  | done
154 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | T | 7 | 7.2.2.6 | 87-88 |  | The subclause numbering is incorrect and very confusing. For example, the numbering of "7.2.2.6.2.12-7.2.2.6.2.18" needs to be in the same hierarchy as 7.2.2.6.2 and is more appropriate to be "7.2.2.6.3-7.2.2.6.9". | Clean up the subclause numbering. | Yes | editorial | A |  | done
155 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.2.4.1 | 91 | 9 | "Layer ID" in Table 80j is "Group ID". | Make the name consistent. | Yes | ESOR | AiP | change text as per 15-11-0195-00
156 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.2.4.1 | 91 | 11 | "1-octet namespace" is inconsistent with the name used in Figure 54o. | Make the name consistent. | Yes | ESOR | AiP | change text as per 15-11-0195-00
157 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.2.4.2 | 92 | 2 | Change "Element IDs, Header IEs" to "Element IDs for Header IEs". | See comment | Yes | ESOR | A | change text as per 15-11-0195-00
158 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.2.4.2 | 92 | 4 | Change "Element IDs, Payload IEs" to "Element IDs for Payload IEs". | See comment | Yes | ESOR | A | change text as per 15-11-0195-00
159 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | T | 7 | 7.2.4.3.11 | 101 | 15 | Can not find figure 54ddb in the draft. | Clarify and correct | Yes | editorial | A |  | done
160 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | T | 7 | 7.2.4.3.15 | 103 | 15-19 | The name used in the title of the subclause, the name used in the content, and the name used in the caption of the Figure are all different. | Clarify and correct. | Yes | Metrics | AiP | delete "AllMetrics" and replace with "AllMAC Metrics", change Figure 54jj title to "Format of AllMAC Metrics IE"
161 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 7 | 7.4.2.9 | 145 | 1 | The "IDS" in the Description of macEBRattributeList should be "IDs". | See comment | Yes | editorial | A |  | done
162 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | T | 7 |  |  |  | There are many MAC additions in 4e to address several different applications. Some of the additions (for example mutipurpose frame) break baseline MAC standard to address new applications. Some of the additions are mutually exclusive (or duplicates each other), suhc as TSCH and DSME. It is important that the text in the draft makes it clear that they are options targetting at certain applications so that it won't confuse readers once it is merged into baseline standard. It will be very beneficial to the implementer if these different options can be clearly separated from each other. | See comment | Yes | general | R | Comment's argument is non persuasive and is incorrect in declaration that the additions "break baseline MAC standard" The amendment adds functionality without destroying existing function. It is not required to tie these additional MAC amendments to applications in the body of the draft but Annex M does describe the applications. Additionally, proposed action is not sufficiently descriptive.
163 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 5, 7 |  |  |  | When click on a specific cluase or subcluase in table of contents, it can not go to that particular clause or subclause. | Make it work. | No | editorial | AiP | Based on the IEEE WORD Template it is not possible. Editor will change to another template, so that it probably will work in the next rev. | done
164 | Kuor-Hsin Chang | Elster Solutions | kuor-hsin.chang@us.elster.com | E | 5, 7 |  |  |  | Only part of the draft has line numbers. | Make the line numbers cover every part of the draft. | No | editorial | R | As the document is based on WORD, the line numbers within a Figure or Table is not provided. | -
165 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | E | 5 | 5.5.3 | 8 | 19 | "and the IE content a payload" doesn't make sense. | Delete "a payload" |  | ESOR | A | see CID 25
166 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | E | 5 | 5.5.4.4 | 10 | 20 | Is AMCA intended to be used with a specific mode (e.g. DSME) or is it avaiable for all modes? | Clarify which modes may use AMCA |  | DSME | R | AMCA is another independent mode under non-beacon mode in addition to TSCH.
167 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 5 | 5.5.5.2 | 11 | 3 | What is "loose latency requirement"? Additional wording should be provided to better explain this application scenario. | See comment | Yes | LE | AiP | Change the sentence in line 3 as follows: "Low data traffic rate and loose latency requirement, where a few seconds of latency is allowable by application."
168 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.1.3.3.1 | 21 | 17 | In HoppingSequenceLength is says: "This parameter shall be set to zero when the value of macHoppingSequenceID is other than '1'." but values 2-0xF are for hopping sequences defined by the NHL so the list is used in cases other than ID = 1. This same statement is made in many other places in the document and it should be corrected in those places as well. | Change to state that it is set to zero when the macHoppingSequenceId is zero. | Yes | general | AiP | The intent of the mechanism proposed in the text is to designate the hopping sequence 0 as the default sequence, hopping sequence 1 informs a device that its sequence shall be dictated to it by the PAN coordinator.Change text to state "When macDSMEenabled is TRUE, the macSequenceLengthshall be set to 0 for all macHoppingSequenceID values other than 1."
169 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.1.14.1.1 | 37 | 3 | Why is the valid range of HoppingSequenceId listed as 0x00-0x0F? | Change to valid range of 0x00-0xFF. This change applies to several places in the document. | Yes | TSCH | A
170 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.1.14.1.1 | 37 | 3 | Why are ChannelOffsetBitmapLength and ChannelOffsetBitmap needed? The hop sequence is specified, so there is no reason that the available channels need to be listed. If this is a mechanism to specify the used channels in the default sequence, then it defeats the purpose of having a default sequence. | Delete ChannelOffsetBitmapLength and ChannelOffsetBitmap. | Yes | DSME | R | In a DSME-enabled PAN, the same channel hopping sequence can be reused among nodes using a different channel offset value. ChannelOffsetBitmap is to denote which offset value is occupied in the neighbor nodes, not to denote which specific channel is in use. Channel hopping sequence and channel offset are explained in 7.5.10.2.2.
171 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.1.14.1.1 | 37 | 3 | In MLME-START, a mechanism should be provided to allow a non-slotted hopping network to specify the time within the current channel. | In the Elements of HoppingDescriptor, add a parameter named PresentHopTimeOffset. The definition of the parameter matches the definition of Present Hop Time Offset in the Hopping Timing information element. | Yes | general | R | Since MLME-START starts the network, why is it necessary to specify the present hop time offset? To do so would attempt to describe operation if the network were to start mid-hop; the offset is be 0 when the network starts.
172 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | E | 7 | 7.2.4.3.4.4 | 96 | 24 | Re-word the following sentence: "The other value of HoppingSequenceID denotes the sequence set by NHL shall be used." | Change to: "The other values of HoppingSequenceID denote the sequence is set by the NHL" |  | DSME | A
173 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | E | 7 | 7.2.4.3.4.4 | 96 | 25 | Change the sentence: "A device shall request a channel hopping sequence to its coordinator when it associates to a PAN, if HoppingSequenceID is 1." | Change to: "If HoppingSequenceID is 1, a device shall request a channel hopping sequence from its coordinator when it associates to a PAN. |  | DSME | A
174 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.2.4.3.4.4 | 97 | 1 | Channel hopping offset is not well defined. The channel hopping specification should be a list of channels that construct the hopping sequence. If an offset into this channel list is to be used, a definition of "offset" should be provided. | Change channel offset to channel. Define offset if it remains. | Yes | DSME | R | In a DSME-enabled PAN, the same channel hopping sequence can be reused among nodes with a different channel offset value. ChannelOffsetBitmap is to denote which offset value is occupied in the neighbor nodes, not to denote which specific channel is in use. The channel hopping sequence and channel offset is explained in 7.5.10.2.2.
175 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.2.4.3.11 | 101 | 14 | The channel hopping IE is not well defined. Why are channel page and PHY configuration in this IE? How can these be 0 or some other length? What is the extended bit map? Why do we need a number of channels field when there is a hopping sequence length? | Remove everything except hopping sequence length, hopping sequence list, and current hop. | Yes | TSCH | AiP | Addressing the commenter's questions: The hopping sequence may be longer than the number of channels, thus the 2 numbers. All the 0's are for when you only send ID - they can't individually be 0. The encoding was from commenter's proposal, where the phy for pages 7 & 8 consisted of a 27 bit field indicating how the phy was being used, and an extended bitmap of channels in use. Add text to pg 101, after 1st sentence of line 18: "When the length is not equal to one the additonal fields are present"
176 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | E | 7 | 7.2.4.3.13 | 102 | 8 | The section is titled EB Filter but the paragraph says EBR filter. Which one is it? It appears this IE is only used in an EBR and is to facilitate which coordinators respond with an EB. | Clarify. Add a sentence to state that this IE is used in an EBR to filter which coordinators respond with an EB. |  | EB | AiP | page 102: line 7 change "EBFilter" to "EB Filter" and on line 8: change "The EBR filter" to "The EB filter", and change the PIB "macEBRFilteringEnabled" to "macEBFilteringEnabled"
177 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | E | 7 | 7.2.4.3.13 | 102 | 11 | In the table, "Included Link Quality filter" should be "Include Link Quality filter" | See comment |  | editorial | A |  | done
178 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | E | 7 | 7.2.4.3.15 | 103 | 15 | The section title is AllMACMetrics. The paragraph calls it AllMetrics, and the figure calls it MAC group metrics. | Use a consistent name. |  | Metrics | A | delete "AllMetrics" and replace with "AllMAC Metrics", change "Figure 54jj title to "Format of AllMAC Metrics IE"
179 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.4.2.3.5 | 137 | 1 | Why are the number of channels and the channel bit map needed? The actual channels used in the hop sequence are listed, so listing channels separately (this would presumably identify channels that are available in the PHY but not used in the hop sequence) is not needed. | Delete macChannelPage, macNumberofChannels, macPhyConfiguration, and macExtendedBitmap. | Yes | TSCH | R | In a DSME-enabled PAN, the same channel hopping sequence can be reused among nodes using a different channel offset value. ChannelOffsetBitmap is to denote which offset value is occupied in the neighbor nodes, not to denote which specific channel is in use. Channel hopping sequence and channel offset are explained in 7.5.10.2.2.
180 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.4.2.10 | 145 | 5 | Can a device choose to disable EBRFiltering? This implies that a device that receives an EBR with filtering requested can choose to ignore the filters? Is this the intent? For filtering to work, those responding to the EBR must honor the filter request in the EBR. | Clarify. | Yes | EB | AiP | pg 102, line 9: change "should" to "shall" and change ", if supported" to "if macEBFilteringEnabled is True"
181 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.5.1a | 146 | 11 | The statement "Each hopping sequence is associated with a particular PHY mode" is not necessary and should be deleted. A hopping sequence does not need to be associated with a PHY mode and a given PHY mode may use multiple hopping sequences. | Delete the sentence | Yes | general | R | The meaning of a given hopping sequence is not consistent among different PHY operations.Without identifying how the PHY is being used, the hopping sequence is an ambiguous list of channels (which means it can be invalid). Therefore there can be multiple uses of the same ID - it can be applicable across multiple PHYs, but is only valid for a specific PHY at any given time (I.e. There can be multiple ID=0 hopping sequences, one for each phy and mode).
182 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | T | 7 | 7.5.1a | 146 | 12 | Why are there "fields describing operation of the PHY"? | Delete this clause | Yes | general | AiP | change to: The Hopping Sequence PIB includes the following attributes of macHoppingSequenceID, fields describing operation of the PHY, the number of elements in the sequence macHoppingSequenceLength, an ordered list of channels macHoppingSequenceList, and the dwell time for unslotted hopping, if applicable. See Table 86f for PIB details.
183 | Bob Mason | Elster Solutions | robert.t.mason@us.elster.com | E | G |  |  |  | In general, the draft needs a good editorial "scrubbing". |  |  | editorial | A |  | done
184 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 4 | 4 | 3 | 0 | ESOR is duplicated. | Delete one of ESORs |  | editorial | A |  | done
185 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.1.3.4.1. | 22 | 21 | Underlines are missing. | Add underline to 'LowLatencyNetworkinfo', 'ChannelOffset', HoppingSequenceLength' and 'HoppingSequence'. |  | editorial | A | See CID 27. | -
186 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.1.3.6 | 23 | 8 | It seems that the Figure is wrong one. | Confirm it. |  | FastA | AIP | Replace Figure 31a here with Figure 31a in d2P802-15-4e_Draft_Standard.
187 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.2.1.7a | 71 | 31 | It seems that 'Figure 42a' should be 'Figure 42b'. | Confirm it. |  | editorial | A | See CID 153. | -
188 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.2.1.7a | 72 | 3 | The term of 'if present' is duplicated. | One of 'if present' should be deleted. |  | editorial | A |  | done
189 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.2.1.7a | 72 | 6 | The term of 'if present' is duplicated. | One of 'if present' should be deleted. |  | editorial | A |  | done
190 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.2.3 | 89 | 16 | It seems that '7.2.2.6.3' should be '7.2.3'. | Confirm it. |  | editorial | A |  | done
191 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.2.4.3.2 | 94 | 3 | It seems that '80j' should be 'Table 80p'. | Confirm it. |  | editorial | A |  | done
192 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.2.4.3.2 | 94 | 7 | it seems that '80k' should be 'Table 80q'. | Confirm it. |  | editorial | A |  | done
193 | Kiyoshi Fukui | OKI | fukui535@oki.com | E | 7 | 7.5.11.1.4 | 188 | 14 | It seems that 'go to step g' shold be 'go to step e'. | Confirm it. |  | LE | A
194 | Wun-Cheol Jeong | ETRI | wjeong@etri.re.kr | T | 7 | 7.1.3.2.1 | 20 | 1 | In Table48, the valid range of ChannelOffset is incorrect. | Change the range to 0x0000-0xffff | Yes | DSME | A
195 | Wun-Cheol Jeong | ETRI | wjeong@etri.re.kr | T | 7 | 7.1.14.1.1 | 35 | 5 | The parameter "SDIndex" is redundant, since it is included in BeaconBitmap. | Delete the parameter | Yes | DSME | A
196 | Wun-Cheol Jeong | ETRI | wjeong@etri.re.kr | T | 7 | 7.1.20.1.6 | 58 | 7 | MLME-COMM-STATUS.indication primitive needs to be added in Figure 39a. | Add it. | Yes | DSME | A
197 | Wun-Cheol Jeong | ETRI | wjeong@etri.re.kr | T | 7 | 7.1.20.3.2.2 | 64 | 8 | In Table78u, the definition of the time interval in the description of ReportPeriod is incorrect. MO should be a superscript. | Make MO to be a superscript. | Yes | DSME | A
198 | Wun-Cheol Jeong | ETRI | wjeong@etri.re.kr | T | 7 | 7.4.2.5 | 140 | 1 | In Table86h, the range of macChannelOffset is incorrect. | Change the range to 0x0000-0xffff | Yes | DSME | A
199 | Wun-Cheol Jeong | ETRI | wjeong@etri.re.kr | T | 7 | 7.4.2.5 | 141 | 2 | In Table86i, the range of ChannelOffset is incorrect. | Change the range to 0x0000-0xffff | Yes | DSME | A
200 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | T | 7 | 7.2.4 | 91 | 3 | The form for type field = 1 IEs did not get fully integrated per what was decided in LA due to incomplete information provided to the Editor. Affects table Figure 54o, Tables 80j, 80k, 80m, 80n, 80o and descriptive text associated with the figure/tables. | Incorporate as described in doc #15-11-0195-00-004e | Yes | ESOR | A
201 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E |  |  |  |  | PIB attributes for EB missing | Add atributes in 15-11-0196-00-004e |  | EB | AiP | ad two PIB attributes for EB as in doc 15-11-0196-02
202 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.2.2 | 72 | 10 | Frame figure updates that didn't make it into the draft: Figures 44, 52, 53a, 54, and 54j. | Revise figures as shwon in doc 15-11-0196-00-004e |  | EB | AiP | use document 15-11-0196-02
203 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 5 | 5.5 | 8 | 1 | Figure 8a scale is inconsistent. | Scale according to other MSCs in the standard |  | editorial | A
204 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 5 | 5.5.3 | 8 | 19 | Cut and paste failure. | Remove "a payload" at end of sentence. |  | editorial | A | See CID 25 | -
205 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.1.3.4.1 | 22 | 21 | Missing edit instructions | last four params s/b underlined to indicate they are new. |  | editorial | A | See CID 27. | -
206 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.1.3.4.1 | 22 | 27 | The formatting got messed up so it appears to say that the status parameter is only valid for LL networks, which is wrong. Note that is stats enumeration descriptions go in 7.1.17. | remove "Information for association specific to LLDNs to the next higher layer. Only available if macLLenabled is set to TRUE." from description of "stauts". Move description of UNSUPPORTED_NWK to 7.1.17 and change name to "UNSUPPORTED_FEATURE" [it's a MAC layer standard not a NWK layer standard). |  | LL | AiP | replace "Information for association specific to LLDNs to the next higher layer. Only available if macLLenabled is set to TRUE." with "The status of the association attempt." indicating unchanged text from the baseline. Add "UNSUPPORTED_FEATURE" to Table 78 with Description "The requested feature is not supported." Change "UNSUPPORTED_NWTYPE" into "UNSUPPORTED_FEATURE" in all locations (Table 50 page 22 line 28, page 19 line 3)
207 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.1.3.4.1 | 23 | 2 | The phrase "Only available if macLLenabled is set to TRUE." is poor wording. It is used several places. | change to "ovly valid when macLLenabled is ture" or simplly delete from descriptoin and and to primitive text. |  | LL | AiP | change "is set to TRUE" to "is TRUE" at the following places: page 4 line 14, page 5 line 2, page 18 table 47, page 20 table 48, page 21 table 49, page 23 table 50, page 33 line 38, page 93 line 11, page 97 line 32, page 132 line 3, page 154 line 17, page 165 line 18, page 176 line 32. change "is set to FALSE" to "is FALSE" at the following places: page 25 line 21, page 27 line 6, page 29 line 10, page 33 line 40, page 165 line 15 (Replace all is safe on D03)
208 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.1.3.5 | 23 | 7 | Figure 3 scale is out or proportion | rescale |  | editorial | AiP | See CID 186 | -
209 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.1.5.1.1 | 25 | 23 | Service primitives should not be expectant, we should be quite certain of what we want the primitive to do . | Change last sentence to "When an enhanced beacon is received, the SDU contains a list of Information Elements, and superframe specification, GTS fields, PendingAdd, and beacon Payload parameters are not present." |  | EB | A
210 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.1.11.1.3 | 33 | 6 | Cross reference to nowhere due to missing text "(see )" | should be "(see 7.3.7.1)". |  | editorial | A | See CID 32 | -
211 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.3.7.1.1 | 107 | 10 | Figure 56b CFID field should be before IEs | re-order |  | editorial | A
212 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | G |  |  |  |  | Need to align with new base standard (4i) in anticipation of it completing sponsor balloting, | reformat as needed. |  | editorial | A
213 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.1.17 | 38 | 13 | There's a lot of status enumeration values sprinkled throughout the primitives that aren't included here. | Update accordingly. |  | TSCH | A | Add "UNSUPPORTED_NWTYPE, BAD_CHANNEL" to table 78. Correct typo in Table 68: “FRAM_TOO_LONG” should be “FRAME_TOO_LONG”
214 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | T | 7 | 7.2.2.1.1a | 73 | 32 | "The EB frame should be sent on the same channel as the EBR" is this a necessary restriction? | Consider removing restriction. | Yes | EB | AiP | delete "The EB frame should be sent on the same channel as the EBR"
215 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.1.1.3.1 | 14 | 5 | In table 43, description of srcPANId seems to have extra text: “Set to the receiver’s PAN ID if the PAN ID is not carried in the received frame” ??? Did we do that on purpose? | replace with "valid only when a source PAN Id included in the received frame" |  | ESOR | AiP | replace with "valid only when a source PAN Id is included in the received frame"
216 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.2.1.7a | 72 | 9 | 42b has two much "Format" in the caption | remove "format" at the end. |  | editorial | A |  | done
217 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | T | 7 | 7.2.2.1.1 | 73 | 24 | EB Ielist should also contain IEs from macEBIElist attribute | add text. | Yes | EB | R | current text is sufficient
218 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.2.4.3 | 93 | 5 | General terminology consistence: captions, headings and text sometimes uses "field" where it should use "IE" or"information element"..someplace spelled out, some abrv. Some times just "element" etc. | clean up terminology |  | ESOR | AiP | after first use of "information element (IE) only refer to IEs, clean up as per comment
219 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.3 | 104 | 5 | "on of" should be "one of" | fix |  | editorial | A |  | done
220 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.3.7.1 | 107 | 4 | Earlier we allowed that an EBR may be generated by SCAN without addressing (implied broadcast). Need to update this text to be conistent. | fix |  | EB | AiP | page 107, line 19: insert "if present" between field and shall, line 21: insert at end of first sentence add "if macImplicitBroadcast is FALSE."
221 | Benjamin A. Rolfe | Blind Creek Associates, Silver Spring Networks | ben@blindcreek.com | E | 7 | 7.5.6.2 | 164 | 11 | Editing instruction says "change" but no changes are indicated. Think it s/b "insert"? | fix editing instructions |  | editorial | A |  | done
222 | Tim Schmidl | Texas Instruments | schmidl@ti.com | T | Introduction | Introduction | iv | 6 | This draft has been changed from Amendment 1 (in d2) to Amendment 5 (in d3). Since 15.4i is finishing sponsor ballot, this draft should be an amendment to 802.15.4-2011. This will include putting the draft in the format of 15.4i. 15.4g has already done the work of putting their draft into the 15.4i format. 15.4e will have to do the same work, whether now or in sponsor ballot. It will be cleaner to do the work now rather than creating unnecessary delays later. | Make this draft an amendment to 802.15.4-2011 including changing the format to the 15.4i format. | Yes | editorial | A | See CID 212 | -
223 | Tim Schmidl | Texas Instruments | schmidl@ti.com | E | 7 | 7.5.1.5.2 | 150 | 2 | "Pairwise" is one word, not two. | Correct spelling. The same problem also occurs on page 163, line 8. | Yes | editorial | A |  | done
224 | Tim Schmidl | Texas Instruments | schmidl@ti.com | T | 7 | 7.5.11.2.4 | 192 | 23 | The RIT sections have been clarified including the figures and the text, so now it is more understandable how RIT operates. There is a conflict between defining the broadcast address (0xffff) and then later stating that broadcast transmission shall not be supported. The sentence in 7.5.11.2.4 should be changed to allow support for broadcast with RIT. | Change the sentence in 7.5.11.2.4 to state that "Broadcast transmission may be supported in RIT mode." | Yes | LE | R | As stated in the comment, destination address of RIT data request can be broadcast address. However, it aims to receive corresponding data frame from arbitrary device(s), which may be used in mesh topology. This is different from broadcast, which means that a device sends data to arbitrary device(s). No changes required.
225 | Tim Schmidl | Texas Instruments | schmidl@ti.com | T | 7 | 7.5.11.2.4 | 193 | 1 | The figure uses new terminology "May f excha RIT o" on the right side of the figure. This terminology should be translated to English. | Translate the new terminology "May f excha RIT o" to English. | Yes | LE | AiP | Resize the figure 73r to fit into page. It will resolve CID 277 as well.
226 | Tim Schmidl | Texas Instruments | schmidl@ti.com | T | D | Annex D | 200 | 1 | MLF15.6 has it status changed from MLF14:M to MLF15:M. However in 15.4g MLF15 is defined as "MPM for all coordinators when operating at more than 1% duty cycle" | The MLF numberings between 15.4g and 15.4e need to be coordinated so that there are not duplicate definitions such as for MLF15. All the MLF numbers should be incremented by 1 to avoid the numbering conflict between 15.4g and 15.4e. | Yes | editorial | A | WG Tech Editor (J.Gilb) is in charge
227 | Chang Sub Shin | ETRI | shincs@etri.re.kr |  | 7 | 7.1.5.1.1 | 25 | 7 | There is no EB related information parameter | add EB related parameters in "PANDescriptor" parameter |  | DSME | W | commenter withdrew
228 | Chang Sub Shin | ETRI | shincs@etri.re.kr |  | 7 | 7.1.14.1.1 | 35 | 5 | "Beacon bitmap" parameter include SDIndex value | delete SDIndex | Yes | DSME | A
229 | Chang Sub Shin | ETRI | shincs@etri.re.kr |  | 7 | 7.1.20.1.5.4 | 58 | Figure 39a | MSC for DSME-GTS allocation and management need to "MLME-COMM-STATUS.indication" primitive | redraw figure 39a | Yes | DSME | A | new figure is in doc 15-11-0261-00
230 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.1 | 72 | 22 | Fig 44 - location of information elements not clear that part is payload, part is header | IE part should match figure 41 |  | ESOR | AiP | use figures from 15-11-0196-02
231 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.2 | 74 | 2 | Fig 52 - location of information elements not clear that part is payload, part is header | IE part should match figure 41 |  | ESOR | AiP | use figures from 15-11-0196-02
232 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.3 | 75 | 1 | Fig 53a - location of information elements not clear that part is payload, part is header | IE part should match figure 41 |  | ESOR | AiP | use figures from 15-11-0196-02
233 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.4 | 76 | 2 | Fig 54 - location of information elements not clear that part is payload, part is header | IE part should match figure 41 |  | ESOR | AiP | use figures from 15-11-0196-02
234 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.6.1 | 84 | 18 | Fig 54j - location of information elements not clear that part is payload, part is header | IE part should match figure 41 |  | ESOR | AiP | use figures from 15-11-0196-02
235 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.1.11.1.1 | 31 | 11 | Unclear editing instructions - New fields in service primitive not underlined | For clarity, frameControlOptions, headerIElist,and payloadIElist should be underlined. |  | editorial | R | Underlining is not needed as the editing instruction says INSERT. | -
236 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.1.11.1.2 | 33 | 2 | ScanType=0x07 for enhanced active scan not called out. | Add similar sentence for ScanType 0x07. |  | EB | A | Page 33, line 2 Add "When the ScanType is set to 0x07, this primitive is used to initiate and enhanced active scan."
237 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.1.11.1.2 | 33 | 6 | Missing refrerence - "(see )" | Add reference to 7.3.7.1 |  | EB | A | see CID 32, change to see 7.3..7.1
238 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.1.1.6 | 70 | 6 | "and" should be "and/or" | Change to " PAN ID and/or broadcast short address" |  | ESOR | AiP | page 70 line 5: change "and/or" to "or", change "may be" to "or both may be"; line 6: change "and" to "or"
239 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.2.1 | 74 | 24 | "7.2.1.7" should be underlined | underline |  | editorial | A |  | done
240 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.3.1 | 75 | 27-28 | missing "shall" | Change to "the Auxiliary Security Header field shall match the corresponding field…" |  | ESOR | A
241 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.3.1 | 75 | 32 | "Table 86a" should be underlined | underline |  | editorial | A |  | done
242 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.2.2.1 | 76 | 24 | "7.2.1.7" should be underlined | underline |  | editorial | A |  | done
243 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.2.4.3.13.4 | 102 | 5 | Filtering for particular PIBs enabled on coordinator and polling for IE's from coordinator got confused. Text in 7.3.7.1.2 is clearer. | Delete sentence "Since the requesting device may not require all the IEs returned for a particular PIB identifier (e.g. filtering on macTSCHenabled returns four IEs), the device may elect not to include PIB identifiers in the EBFilter and poll for individual IEs as described in 7.3.7.1.2." |  | EB | A
244 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.3 | 104 | 5 | Typo - "on" should be "one" | Change to "An FFD supporting one of the..." |  | editorial | A | See CID 219 | -
245 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.3 | 104 | 6 | "Table 86a" should be underlined | underline |  | editorial | A |  | done
246 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.3.7.1.1 | 107 | table 56b | Table missing column separators | fix |  | editorial | A |  | done
247 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.5.1.5.1 | 149 | 24 | "ID" should be "handle" | change |  | TSCH | A
248 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.5.6.4.3.2 | 167 | 27 | DSN isn't required | Change to "contains the same DSN as the original transmission (if present), |  | TSCH | A
249 | Jonathan Simon | Dust Networks | jsimon@dustnetworks.com | E | 7 | 7.5.6.4.3.2 | 167 | 34 | DSN no longer tied to ASN | Delete sentence "The retransmitted frame shall contain the appropriate DSN for the current ASN." |  | TSCH | A
250 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | E | 5 | 5.5.1.2 | 5 | 15 | Figure 5b. Figure labels frames as sensor and actuator time slots, text uses terms uplink and bidirectional. | Update figure to use terminology from text. | Yes | LL | AiP | Replace 5b with 5c
251 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | E | 5 | 5.5.1.2 | 6 | 1 | Figure 5c. Figure does not contain GACK frame described in text. | Update figure to include GACK. | Yes | LL | AiP | Provide 5c
252 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | E | 7 | 7.1.3.1.3 | 19 | 1 | Boolean logic of statement can be simplified. | Change "and macLLenabled is not set to TRUE" to "but macLLenabled is set to FALSE". | Yes | LL | AiP | change "and macLLenabled is not set to TRUE," to "and macLLenabled is FALSE,"
253 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | T | 7 | 7.1.3.3.1 | 21 | 18 | Definition/use of HoppingSequenceLength and Hopping Sequence are unclear. What is special about macHoppingSequenceID = 1? This is not explained in the referenced section (7.5.1a). | Clarify the definition and/or explain in 7.5.1a. | Yes | TSCH | AiP | The intent of the mechanism proposed in the text is to designate the hopping sequence 0 as the default sequence, hopping sequence 1 informs a device that its sequence shall be dictated to it by the PAN coordinator.Change text to state "When macDSMEenabled is TRUE, the macSequenceLengthshall be set to 0 for all macHoppingSequenceID values other than 1."
254 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | T | 7 | 7.1.14.1.1 | 37 | 3 | Definition/use of HoppingSequenceLength and Hopping Sequence are unclear. What is special about macHoppingSequenceID = 1? This is not explained in the referenced section (7.5.1a). | Clarify the definition and/or explain in 7.5.1a. | Yes | TSCH | AiP | The intent of the mechanism proposed in the text is to designate the hopping sequence 0 as the default sequence, hopping sequence 1 informs a device that its sequence shall be dictated to it by the PAN coordinator.Change text to state "When macDSMEenabled is TRUE, the macSequenceLengthshall be set to 0 for all macHoppingSequenceID values other than 1."
255 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | T | 7 | 7.1.5.3.1 | 26 | 13 | MLME-BEACON.request does not include IE list parameters. Although this interface is not "real", it seems clearer to include this as a parameter rather than relying only on the macEBIEList PIB, particularly for non-beacon-enabled PANs. It would also align with, e.g., MLME-START, which uses macEBIEList and header/payload IE list parameters. | Add header/payload IE list parameters. | Yes | EB | A
256 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | E | 7 | 7.1.11.1.1 | 32 | 2 | Missing words in headerIElist definition. | First sentence should end "sent IN THE frame". | Yes | editorial | A |  | done
257 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | T | 7 | 7.3.7.1.2 | 108 | 2 | Mechanism for requesting IEs needs some clarification. Text state that normal IE header is used, but with length set to 0. Is that true for any IE list, or only in an EBR? Can an EBR contain "normal" (not request) IE entries, by setting the length to the appropriate value? Sentence references section 7.2.4.1, but that section does not discuss IE requests. | Clarify what can appear in the header/payload IE lists for an EBR. Add necessary IE request text to 7.2.4.1, or remove reference here. | Yes | ESOR | AiP | page 108 line3: delete "(see 7.2.4.1.)" Addto the end of line 8 "This IE request mechanism is only available in an EBR"
258 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | T | 7 | 7.4.2.3.5 | 136 | 3 | Subsection 7.4.2.3.5, MAC PIB attributes for Hopping Sequence, is placed under Section 7.4.2.3, TSCH-specific MAC PIB attributes. However, these Hopping Sequence PIB attributes are not specific to TSCH; they also apply to unslotted hoppers. | Move the content of 7.4.2.3.5 up level (i.e., to a new section 7.4.2.X). | Yes | general | A
259 | Jeffrey King | Elster Solutions | jeff.c.king@us.elster.com | T | D | D.7.3.1 | 201 | 1 | Need PICS items for unslotted hopping and related support. | Add item for optional Unslotted Hopping Capability (with reference to Table 86a). Add item for mandatory (for Unslotted Hopping capability) Unslotted Hopping Information Elements (references to 7.2.4.3.11, 7.2.4.3.12 and 7.2.4.3.13). Updated items for Enhanced Beacon and Enhanced Beacon Request to indicate that support is mandatory for Unslotted Hopping. | Yes | general | A
260 | Emmanuel Monnerie | Landis+Gyr | emmanuel . monnerie @ landisgyr.com | E | all | all | all | all | The layout of the document is following the 802.15.4-2006 template. Since the 802.15.4i format is already in sponsor ballot it would be a good idea to reformat accordingly. The TG4g group has already reformated the draft according to 802.15.4e format. | Reformat the document according to 802.15.4i structure. | Yes | editorial | A | See CID 212 | -
261 | Emmanuel Monnerie | Landis+Gyr | emmanuel . monnerie @ landisgyr.com | T | all | all | all | all | This MAC amendment introduces multiple options that are not interoperable with each other (DSME, TSCH, Low-Latency, Unslotted Frequency Hopping). Some of these options are clearly highlighted (cf clause 7.1.20) while some others are burried into the text. This is very hard to follow for a reader and an implementer will have a hard time to select the features that are needed to fully implement one of the options. | Clearly separate each options with explicit title for each clauses. The current title of clause 7.1.20 is a good example "DSME-specific MAC sublayer service specification". We should see also similar clauses for the other options (particularly for the Unslotted-Frequency Hopping mode). If some of the modes don't require a specific text, at least, there should be clause listing all the features that must be supported to fully implement each mode. | Yes | general | R | There can be no attempt to limit certain MAC processes for specific applications, to do so would invalidate the layering concept. It should be noted that Annex M describes the cited applications
262 | Sverre Brubæk | Texas Instruments | s.brubak@ti.com | E | 7.1.13.1.1 |  | 43 | 1 | ScanType is set as integer, but is actually an enumeration type | Change to enumeration |  | TSCH | AiP | It’s cited as an integer in the base standard, but is fixed in revision 4i.
263 | Sverre Brubæk | Texas Instruments | s.brubak@ti.com | E | 7.1.13.2.1 |  | 45 | 21 | ScanType is set as integer, but is actually an enumeration type | Change to enumeration |  | TSCH | AiP | It’s cited as an integer in the base standard, but is fixed in revision 4i.
264 | Sverre Brubæk | Texas Instruments | s.brubak@ti.com | E | 7.1.5.5.1 |  | 40 | 24 | ChannelHoppingSpecificationBeaconType is coded as integer but should be enumeration | Change to enumeration |  | TSCH | AiP | Change to enumeration, change valid range to BEACON, ENHANCED BEACON, and change the description to “BEACON = 0: send a beacon. ENHANCED BEACON = 1: send an enhanced beacon.”
265 | Sverre Brubæk | Texas Instruments | s.brubak@ti.com | E | 7.1.5.5.1 |  | 41 | 1 | NameSrcAddrMode is coded as integer but should be enumeration | Change to enumeration |  | TSCH | AiP | It’s cited as an integer in the base standard, but is fixed in revision 4i.
266 | Sverre Brubæk | Texas Instruments | s.brubak@ti.com | E | 7 | 7.1.22.1.2.3 | 65 | 1 | MACDecisionManagementType, Direction, PriortizedChannelAccess are erronously typed | Change to Enumeration |  | DSME | R | The cited sub-clause and comment primitives cannot be found in the draft
267 | Sverre Brubæk | Texas Instruments | s.brubak@ti.com | E | 7.1.22.1.6.2 |  | 74 | 1 | ManagementType, Direction, PriortizedChannelAccess are erronously typed | Change to Enumeration |  | TSCH | A | change table 78o for these parameters from integer to enumeration
268 | Sverre Brubæk | Texas Instruments | s.brubak@ti.com | E | 7.1.22.1.7.2 |  | 75 | 1 | ManagementType, Direction, PriortizedChannelAccess are erronously typed | Change to Enumeration |  | TSCH | A | change table 78p for these parameters from integer to enumeration
269 | Sverre Brubæk | Texas Instruments | s.brubak@ti.com | E | 7.1.22.1.8.2 |  | 77 | 1 | ManagementType, Direction, PriortizedChannelAccess are erronously typed | Change to Enumeration |  | TSCH | AiP | Rework as in CID 264, i.e. Change to enumeration, change valid range to enum names instead of integers, change description to list of enum values and what they mean. Editor should be able to proceed based on 264 as an example.
270 | Betty Zhao | Huawei | betty.zhao@huawei.com | E | 7 | 7.5.10.10 | 186 | 32 | The specific name of MAC command is not described here. | Change 'upon receipt of a request' to 'upon receipt of a DSME-Information request command' | Yes | DSME | A
271 | Yang Yang | SIMIT,CAS / WSNIRI | youcyyang@gmail.com | T | 7 | 7.2.1.1.5 | 69 | line 15 | When PAN ID Compression bit is set to "1", and Frame Version is set to "10", here we added 3 new situations: 1.if both Source Addr and Dst Addr exist, only when they are both 16-bit, we need Dst PAN ID; 2. if only one of the Source Addr and Dst Addr exist, we don't need any PAN ID; 3. if none of the Source Addr and Dst Addr exist, we need Dst PAN ID. Why these fields should be set as this? can add some explaination? | Add some description about the setting of PAN ID Compression field maybe better. | No | ESOR | R | Current text is sufficient to describe necessary settings.
272 | Yang Yang | SIMIT,CAS / WSNIRI | youcyyang@gmail.com | T | 7 | 7.2.1.7a | 71 | line 31 | "Information Element List field is shown in Figure 42a". Can't find "Figure 42a" in this draft, please check. |  | Yes | EB | AiP | change 42a to 42b
273 | Yang Yang | SIMIT,CAS / WSNIRI | youcyyang@gmail.com | E | 7 | 7.2.2.1.1a | 73 | line 25 | "when the IE list present field of the frame control field", change to "… the IE list present subfield of …" may be better. |  | No | EB | R | it was agreed to only use "field" not subfield
274 | Yang Yang | SIMIT,CAS / WSNIRI | youcyyang@gmail.com | T | 7 | 7.2.2.6.2 | 85 | figure 54k | for 1-octet frame control, don’t need information like Frame Version, is this setting suitable? |  | No | ESOR | AiP | Add the following text after Page 85, line 9 (end of sub-clause 7.2.2.6.2): NOTE- The unique frame type value or the multipurpose frame assures that legacy devices will reject the frame. When the 'Long FCF' field is not set, filtering on the version number is not possible, so the position of the Frame Type, Long FCF, addressing and version fields should not be changed in future versions of the protocol".
275 | Yang Yang | SIMIT,CAS / WSNIRI | youcyyang@gmail.com | T | 7 | 7.2.2.6.3.1.2 | 88 | line 28~31 | length of "Blink payload" field is variable, how can the receiver knows how long should it process as payload? |  | No | 4F | AiP | the packet length as noted in the PHY determines the end of the frame
276 | Yang Yang | SIMIT,CAS / WSNIRI | youcyyang@gmail.com | T | 7 | 7.2.4.1 | 91 | table 80j | For the payload of MAC frames, in which situation, the Group ID means the IE will for PLME? From the view of lay design, each layer should only contain information for its upper layer. |  | Yes | ESOR | AiP | refer to 15-11-0195-00 for clarifying text
277 | Yang Yang | SIMIT,CAS / WSNIRI | youcyyang@gmail.com | E | 7 | 7.5.11.2.4 | 193 | figure 73r | size of this figure is not suitable. |  | Yes | editorial | A |  | done
278 | Cristina Seibert | Silver Spring Networks | cseibert @ silverspringnet.com | T | 7 | 7.2.4.1 | 91 | 3 | The format of the payload IE is different from what was agreed by the group. The format should consist of 1 bit (always set to 1), followed by 4 bits of ID and 11 bits of length. For the case of the MLME IE, nested IE may follow. Like in the case of the "outer" IEs, two formats can be defined for the "inner" (nested) IEs: a short format, consisting of 1 bit set to 0 to indicate short format, 7 bits of the (sub) ID field and 8 bits of length. The second format is a long format, consisting of 1 bit set to 1 to indicate long format, 4 bits of (sub) ID and 11 bits of length. This format combination provides flexibility but also efficiency, particularly when packaging multiple nested IEs. | Change as indicated in the comment. | Yes | ESOR | A | refer to 15-11-0195-00 for change information
279 | Chin-Sean Sum | NICT |  | T | 7 | 7.4.2.5 | 140 | 1 | In Table 86h, PIB attribute "macLowEnergySuperframeSupported" is not relevant to DSME in this revision any more. | Remove entry (row) of macLowEnergySuperframeSupported from Table 86h | Yes | LE | A
280 | Larry Taylor | DTC (UK) | larry.taylor@acm.org | E | 7.2.4 |  | 90 | 5 | The description of IEs does not match the corresponding description of IEs in D3 802.15.4g. The Editors of 4g & 4e amendments must align IE descriptions so that they are consistent across both drafts | Editors to amend either/both drafts so that IE descriptions are consistent |  | ESOR | A | refer to 15-11-0195-00 for change information
281 | David Cypher | NIST | david.cypher@nist.gov | T | 3 |  | 1 | 34 | CID 217 was not dispositioned | Insert "sampled" between "listening period", to agree with term on line 35 (i.e., listening sampled period) | Yes | LE | AiP | CID 217 is the wrong reference. However, the proposed change is correct. In the definitions change "coordinated sampled listening payload frame: A beacon, data or command frame carrying the real payload following the wakeup sequence in a coordinated listening period." to "coordinated sampled listening payload frame: A beacon, data or command frame carrying the real payload following the wakeup sequence in a coordinated sampled listening period."
282 | David Cypher | NIST | david.cypher@nist.gov | T | 7 | 7.1.1.3.1 | 14 | 5 | CID 221 Table now includes two new parmeters, which are not shown in the parameters list preceding the Table | Insert AngleOfArrival Azimuth and AngleOfArrival Elevation and show as being added (underscore) | Yes | 4F | A | Insert AngleOfArrival Azimuth and AngleOfArrival Elevation in the listed if parameters preceding the table
283 | David Cypher | NIST | david.cypher@nist.gov | T | 7 | 7.1.11.1.1 | 31 | 11 | Lines 11, 12, & 13 are not underlines to indicate the change by including them. | Underline these three parameters to indicate change | Yes | editorial | A | Insert AngleOfArrival Azimuth and AngleOfArrival Elevation in the listed if parameters preceding the table | -
284 | David Cypher | NIST | david.cypher@nist.gov | T | 7 | 7.1.14.1.1 | 36 |  | Table 72 does not include the new parameters as indicated in parameter list preceding Table. | Either delete new parameters (SD Index SuperFrameOrder) from list OR add new parameters (SDINdex and underline SuperFrame Order) to Table 72 | Yes | DSME | AiP | Delete the parameter "SD Index" and underline "SuperFrameOrder"
285 | David Cypher | NIST | david.cypher@nist.gov | T | 7 | 7.1.19. | 47 | 11 | Parameter (DiscoveryModeStatus) not in table | Either add parameter to table or delete parameter from list | Yes | LL | AiP | remove parameter DiscoveryModeStatus from primitive since there is already a primitive called status.
286 | David Cypher | NIST | david.cypher@nist.gov | T | 7 | 7.1.2.4 | 16 | 11 | Table 46c; Misisng GTS.response in 7.1.20.1.4 | Either add cross reference for this primitive or delete the text for the primitive in 7.1.20.1.4 | Yes | DSME | AiP | cross reference will be added
287 | David Cypher | NIST | david.cypher@nist.gov | E | 7 | 7.3.7.1.1 | 107 | 11 | Figure 56b; missing vertial lines separating fields (possible PDF artifact) | Add missing vertical lines separating fields | Yes | editorial | A | See CID 246 | -
288 | David Cypher | NIST | david.cypher@nist.gov | E | 7 | 7.6.2 | 196 | 6 | Figure 74; missing vertial lines separating fields (possible PDF artifact) | Add missing vertical lines separating fields | Yes | editorial | A |  | done
289 | David Cypher | NIST | david.cypher@nist.gov | E | 7 | 7.6.2.2 | 196 | 10 | Figure 75; missing vertial lines separating fields (possible PDF artifact) | Add missing vertical lines separating fields | Yes | editorial | A |  | done
290 | David Cypher | NIST | david.cypher@nist.gov | T |  |  | 200 |  | Annex D, Table D.5; Numbering of the items are not in sequence. MLF15.7 & 8 occur after MLF16.5 | Correct numbering or placement of items | Yes | editorial | A |  | done
291 | David Cypher | NIST | david.cypher@nist.gov | G |  |  | 200 |  | Annex D, Table D.5; defines MLF15, so does the lastest draft of 802.15.4g | Please coordinate the numbering between the multiple active drafts. Merging these multiple ammendments with the same numbering WILL lead to errors. | Yes | editorial | A | See CID 226 | -
292 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | T | 7 | 7.1.3.1.1 | 18 | Table 47 | At the MLME-SAP, it'll be impossible to extract the ChannelOffset and HoppingSequenceID parameters from the MLME-ASSOCIATE.request primitive, because the length of LowLatencyNetworkInfo is not given in prior. | Specify the LowLatencyNetworkInfo. |  | LL | A | See CID 22 | -
293 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 5 | 5.5.1.1 | 4 | 15 | typo: " .. by coordinators which periodicly .." | correct to "periodically" |  | editorial | A | See CID 22 | -
294 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 5 | 5.5.3 | 8 | 10 | the order of description of six frame structures would be preferred to align with the order of sub-claues of 5.5.3. | move "- Low latnecy frames, .." sentence after to "- A multipurpose frame, .." sentence |  | editorial | A |  | done
295 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 5 | 5.5.3 | 8 | 19 | typo: ", and the IE content a payload." | correct "content a payload" to "content payload" |  | editorial | AiP | See CIP 25 | -
296 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.1.2.3 | 16 | 4 | typo: "When LL is implemented the services" | correct to "When LL option is implemented, the services" |  | editorial | A |  | done
297 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.1.2.3 | 16 | Table 46c | omit the sub-clause for MLME-DSME-GTS.response | insert "7.1.20.1.4" in (Response, MLME-DSME-GTS) |  | editorial | A |  | done
298 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.1.5.1 | 25 | 19 | Sub-clause numbering is wrong, one level up. | change "7.1.5.2" to "7.1.5.1.2" After this sub-clause, change the sub-clause number: "7.1.5.3" to "7.1.5.2", so on. |  | editorial | A |  | done
299 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.5.9.4 | 170 | 5 | typo: "can sent their .. " | correct "sent" to "send" |  | editorial | A |  | done
300 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.5.9.4 | 171 | 9 | difficult to find the meaning of "bit bi-1". specify the closer related sub-clause. | change "7.2.2.5." to "7.2.2.5.2.2.6" |  | editorial | A |  | done
301 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.5.10.1 | 172 | 7 | typo: " ..shall periodicly transmit.." | correct to "periodically" |  | editorial | A | See CID 22 | -
302 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.5.12.1 | 193 | 9 | typo: ".. is specified, which are .." | correct ".. is specified, which are .." to ".. are specified: .." |  | editorial | A |  | done
303 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.5.12.2 | 194 | 10 | typo: ".. the acknowledge frame .." | correct to ".. the acknowledgement frame .." |  | editorial | A |  | done
304 | Seong-Soon Joo | ETRI | ssjoo@etri.re.kr | Editorial | 7 | 7.5.12.2 | 194 | 29 | typo: ".. the device make decision .." | correct to ".. the device makes decision .." |  | editorial | A |  | done