## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: Time Planning for the Task Group
Date Submitted: 17 March 2014
Source: Thomas Kürner Company TU Braunschweig
Address Schleinitzstr. 22, D-38092 Braunschweig, Germany
Voice:+495313912416, FAX: +495313915192, E-Mail: t.kuerner@tu-bs.de
Re: n/a
Abstract: This document puts together some first thoughts on the time planning of a potential Task Group 3d
Purpose: Information of IEEE 802.15 SG 100G
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Tim Planning for the Task Group
Thomas Kürner
TU Braunschweig

## Slide 3: Scope
This document puts together some first thoughts on the time planning of a potential Task Group 3d.
A proposal is made taking into account the Expected Date of submission of draft to the IEEE-SA for initial Sponsor Ballot and the projected completion date for submittal to RevCom as indicated in the working darft PAR (15-13-0523-05-0thz-thz-working-draft-par):
  Initial Sponsor Ballot (11/2015)
  Submittal to RevCom: (5/2016)
There is no need to decide on this while we are a study group
We need to decide on such a time plan and procedure after formation of TG3d

## Slide 4: Proposed Documents
In preparation of the standard‘s amendment document the following five documents are proposed to be created:
  Application Requirements Document (ARD)
  Technical Requirements Document (TRD)
  Channel Modelling Document (CMD)
  Evaluation Criteria Document (ECD)
  Call for Proposals

## Slide 5: Application Requirements Document (ARD)
The ARD will contain description on applications and use cases with performance and functional requirements
Some input to this document is available in the Techncial Expectation Document (TED) (https://mentor.ieee.org/802.15/dcn/11/15-11-0745-13-0thz-thz-ig-technical-expectations-document-ted.doc) developed within IG THz and SG3d 100G, respectively
Proposal to start on the ARD: May 2014
Proposal to finalize the ARD: July 2014

## Slide 6: Technical Requirements Document (TRD)
The TRD will serve as a guideline to develop technical proposals satisfying the requirements
Some input to this document is available in the Techncial Expectation Document (TED) (https://mentor.ieee.org/802.15/dcn/11/15-11-0745-13-0thz-thz-ig-technical-expectations-document-ted.doc) developed within IG THz and SG3d 100G, respectively
The TRD has to take into account also the 48/64 bit addressing issue
Proposal to start on TRD: May 2014
Proposal to finalize TRD: September 2014

## Slide 7: Channel Modeling Document (CMD)
The CMD will contain descriptions of the propagation characteristics and channel models of the operational environments relevant for the considered applications (e. g. data required to calculate link budgets)
The CMS will support the evaluation of the proposals
Some input to this document is available in the Technical Expectation Document (TED) (https://mentor.ieee.org/802.15/dcn/11/15-11-0745-13-0thz-thz-ig-technical-expectations-document-ted.doc) developed within IG THz and SG3d 100G, respectively
Proposal to start on the CMD: May 2014
Proposal to finalize CMD: September 2014

## Slide 8: Evaluation Criteria Document (ECD)
The ECD will serve as a framework for evaluating proposals with some performance criteria
It will be based on information form the ARD, TRD and CMD.
Proposal to start on TRD: July 2014
Proposal to finalize TRD: September 2014

## Slide 9: Call for Proposals (CfP)
The CfP will be the formal document to trigger submission of proposals to be included in the standard.
The ARD, TRD, CMD and ECD will serve as a reference. Ideally these documents have to be finished before the CfP is issued.
Proposal to start on the CfP: September 2014
Proposal to finalize CfP: September 2014
Suggested date for presenting proposals: November 2014

## Slide 10: Letter Ballots / Sponsor Ballots
Once the 1st draft of the standard‘s amendment has been finished, it has to be submitted for the Letter Ballot (LB) with WG 15.
The main work in the time period after the submission to LB will be comment resolution and recirculation.
To pass 75% yes votes are required
Once the draft has passed the LB it will be submitted to IEEE-SA for Sponsor Ballot (SB).
A similar procedure as with the LB will take place.
Proposal to start the LB process: January 2015
Target to start the SB process: November 2015 (as indicated in the draft PAR)

## Slide 11: Time Planning (1/2)
Task | 2014 |  |  |  | 2015 |  |  |  |  |  | 2016 |  | 
 | M | J | S | N | J | M | M | J | S | N | J | M | M
Kick Off | X |  |  |  |  |  |  |  |  |  |  |  | 
Applic. Req. Doc. |  |  |  |  |  |  |  |  |  |  |  |  | 
Technical Req. Doc. |  |  |  |  |  |  |  |  |  |  |  |  | 
Channel Mod. Doc. |  |  |  |  |  |  |  |  |  |  |  |  | 
Eval. Crit. Doc. |  |  |  |  |  |  |  |  |  |  |  |  | 
Work on CfP |  |  |  |  |  |  |  |  |  |  |  |  | 
Issuing CfP |  |  | X |  |  |  |  |  |  |  |  |  | 
Pres. of Proposals |  |  |  |  |  |  |  |  |  |  |  |  | 
Editing 1st Draft |  |  |  |  |  |  |  |  |  |  |  |  | 
Motion for 1st LB |  |  |  |  | X |  |  |  |  |  |  |  | 

## Slide 12: Time Planning (2/2)
Task | 2014 |  |  |  | 2015 |  |  |  |  |  | 2016 |  | 
 | M | J | S | N | J | M | M | J | S | N | J | M | M
LB Comment Res. and Recirculation |  |  |  |  |  |  |  |  |  |  |  |  | 
Submission for Sponsor Ballot |  |  |  |  |  |  |  |  |  | x |  |  | 
SB Comment Res. And Recirculation |  |  |  |  |  |  |  |  |  |  |  |  | 
Submission to RevCom |  |  |  |  |  |  |  |  |  |  |  |  | x