## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: Time Planning for the Task Group
Date Submitted: 28 July J2016
Source: Thomas Kürner Company TU Braunschweig
Address Schleinitzstr. 22, D-38092 Braunschweig, Germany
Voice:+495313912416, FAX: +495313915192, E-Mail: t.kuerner@tu-bs.de
Re: doc. 14/0155r10
Abstract: This document presents a revised version of the task and time planning for TG3d
Purpose: Information of IEEE 802.15 TG3d (100G)
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Time Planning for the Task Group
Thomas Kürner
TU Braunschweig

## Slide 3: Scope
This document presents a revised version of the task and time planning for TG3d
The time planning in this revision of the document is based on a projection for the single supporting documents.

## Slide 4: Proposed Documents
In preparation of the standard‘s amendment document the following five documents are proposed to be created:
  Application Requirements Document (ARD)
  Technical Requirements Document (TRD)
  Channel Modelling Document (CMD)
  Evaluation Criteria Document (ECD)
  Preliminary Call for Proposals/ Call for Proposals

## Slide 5: Application Requirements Document (ARD)
The ARD will contain description on applications and use cases with performance and functional requirements
Some input to this document is available in the Technical Expectation Document (TED) (https://mentor.ieee.org/802.15/dcn/11/15-11-0745-13-0thz-thz-ig-technical-expectations-document-ted.doc) developed within IG THz and SG3d 100G, respectively
Proposal to start on the ARD: May 2014
Proposal to finalize the ARD: May 2015
ü

## Slide 6: Technical Requirements Document (TRD)
The TRD will serve as a guideline to develop technical proposals satisfying the requirements
Some input to this document is available in the Techncial Expectation Document (TED) (https://mentor.ieee.org/802.15/dcn/11/15-11-0745-13-0thz-thz-ig-technical-expectations-document-ted.doc) developed within IG THz and SG3d 100G, respectively
The TRD has to take into account also the 48/64 bit addressing issue
Proposal to start on TRD: May 2014
Proposal to finalize TRD: March 2016
ü

## Slide 7: Channel Modeling Document (CMD)
The CMD will contain descriptions of the propagation characteristics and channel models of the operational environments relevant for the considered applications (e. g. data required to calculate link budgets)
The CMD will support the evaluation of the proposals
Some input to this document is available in the Technical Expectation Document (TED) (https://mentor.ieee.org/802.15/dcn/11/15-11-0745-13-0thz-thz-ig-technical-expectations-document-ted.doc) developed within IG THz and SG3d 100G, respectively
Proposal to start on the CMD: May 2014
Proposal to finalize CMD: March 2016
ü

## Slide 8: Evaluation Criteria Document (ECD)
The ECD will serve as a framework for evaluating proposals with some performance criteria
It will be based on information from the ARD, TRD and CMD.
Proposal to start on ECD: March 2015
Proposal to finalize ECD: March 2016
ü

## Slide 9: Call for Proposals (CfP)
The CfP will be the formal document to trigger submission of proposals to be included in the standard.
The ARD, TRD, CMD and ECD will serve as a reference. Ideally these documents have to be finished before the CfP is issued.
Proposal to start on the CfP: July 2015
Proposal to finalize the CfP : March 2016
Suggested date for presenting of first proposals: July 2016
ü

## Slide 10: Letter Ballots / Sponsor Ballots
Once the 1st draft of the standard‘s amendment has been finished, it has to be submitted for the Letter Ballot (LB) with WG 15.
The main work in the time period after the submission to LB will be comment resolution and recirculation.
To pass 75% yes votes are required
Once the draft has passed the LB it will be submitted to IEEE-SA for Sponsor Ballot (SB).
A similar procedure as with the LB will take place.
Proposal to start the LB process: January 2017
Target to start the SB process: July 2017

## Slide 11: Time Planning (1/2)
Task | 2014 |  |  |  | 2015 |  |  |  |  |  | 2016 |  | 
 | M | J | S | N | J | M | M | J | S | N | J | M | M
Kick Off | X |  |  |  |  |  |  |  |  |  |  |  | 
Applic. Req. Doc. |  |  |  |  |  |  |  |  |  |  |  |  | 
Technical Req. Doc. |  |  |  |  |  |  |  |  |  |  |  |  | 
Channel Mod. Doc. |  |  |  |  |  |  |  |  |  |  |  |  | 
Eval. Crit. Doc. |  |  |  |  |  |  |  |  |  |  |  |  | 
Work on CfP |  |  |  |  |  |  |  |  |  |  |  |  | 
Issueing CfP |  |  |  |  |  |  |  |  |  |  |  | X | 

## Slide 12: Time Planning (2/2)
Task | 2016 |  |  |  | 2017 |  |  |  |  |  | 2018 |  | 
 | M | J | S | N | J | M | M | J | S | N | J | M | M
Pres. of Proposals |  |  |  |  |  |  |  |  |  |  |  |  | 
Editing 1st Draft |  |  |  |  |  |  |  |  |  |  |  |  | 
Motion for 1st LB |  |  |  |  | x |  |  |  |  |  |  |  | 
LB Comment Res. and Recirculation |  |  |  |  |  |  |  |  |  |  |  |  | 
Submission for Sponsor Ballot |  |  |  |  |  |  |  | X |  |  |  |  | 
SB Comment Res. And Recirculation |  |  |  |  |  |  |  |  |  |  |  |  | 
Submission to RevCom |  |  |  |  |  |  |  |  |  | x |  |  |