## Sheet1
Index	Things wrong and general idiocy	How can we fix them	Status	Tech/Ed.	Severity	Assigned to:
1	Clause 5 is too big	Split Clause 5 into functional and frame formats	Written	Editorial	Moderate
2	Can we delete the Industrial applications Annex.	Move to a mentor document?	Written	Editorial	Moderate
3	Move example packet encodings to a mentor document.	Do for all of them.	Written	Editorial	Moderate
4	Should we delete ACKs from the MSCs	Yes, do it to simplify the MSCs	Resolved	Editorial	Moderate
5	Define clearly what causes an ACK to be sent.	Check to see if it stated in one location.	- When should ACK be sent? 3 Conditions of: AR=1 & unicast destination = device address & CRC is valid / - When should enhanced ACK be sent: 4 Conditions of: AR=1 & frame=multipurpose or data/command with rev>1 & unicast destination = device address & CRC is valid & ??	Technical	High	J Simon
6	What is channel page used for? Can't we get rid of it?	Lets try to remove channel page. Ben to propose.	Change severity to moderate, if too complex for schedule, drop it	Technical	High	Rolfe
7	5.1.6.4.2 – ACKs happen without security processing.	Yes, delete this.		Editorial	High
8	What the hell is the structure of the SUN channel page nonsense?	Perhaps this can be deleted? If not, then it needs to be updated to be correct.		Technical	Moderate
9	Add, candidate for deprecation, deprecated, removed and archived.	Write a short paragraph that says what these mean. Perhaps steal text from 802.11.		Technical	Moderate
10	Should plus/minus be followed with a space?	No space between it and the number.	Resolved	Editorial	Low
11	Are we really putting the length field in backwards?	We need uniform language do describe this idiocy.	change to editorial	Technical	High	All
12	Tb for the MSK PHY isn't defined anywhere.		Should be symbol times? If simple, add definition otherwise drop, change severity to moderate	Technical	High	Beecher
13	MSK PHY is simply orthogonal GFSK, why not use that?	Simplify the clause. Perhaps reference the GFSK.		Editorial	Moderate
14	LRP UWB frame format is BS, needs to be re-done	Need better definition of what is wrong.		Editorial	Moderate
15	Remove country and regulations from SUN PHY frequency table.	Yes	Resolved	Editorial	Moderate
16	Is it really ith and jth?	It is superscript, upright text.	Resolved	Editorial	Low
17	Is it i.e. or i. e.?	i.e., no space	Resolved	Editorial	Low
18	Can we deprecate mode switch?	Candidate for deprecation.		Technical	Moderate
19	RIT MSC, is it correct?	Ask Kojima-san		Technical	Moderate
20	Equations in RFID annex need to be fixed.	Clint Powell		Editorial	High
21	Figures in RFID annex need to be fixed.			Editorial	High
22	MSCs in Clause 4 need to be deleted or moved.	Pat will work on it.		Technical	High	Kinney
23	MSCs in Clause 6 need to be deleted or moved.	Pat will work on it.		Technical	High	Kinney
24	Too much detail on precise behavior in Clause 4. Needs complete re-write.	Make it only a general overview and pointers to correct locations.		Editorial	Low
25	Access methods should not be bound to PHYs in the MAC clause, but rather in the PHY clauses.	Make sure that we are tying access methods to modes, not PHYs		Technical	Moderate
26	In LECIM, it says “The format of the PHR is shown in Figure . All multi-bit fields are unsigned integers and shall be processed MSB first”, but earlier, lsbs are on the left, msbs are on the right.	Check with LECIM people, Rolfe will liaise with Christina?	Ben to look at wording vs. figures	Technical	High	Rolfe
27	In multi-purpose wakeup frame, the RZ Time IE has size 4/6, yet it is listed as a fixed 2 octets	Ben should check this.		Technical	Moderate
28	There are references to “short address less than 0xfffe” but that simply means a device that has been allocated a short address.	Say instead “shall only be sent by a device that has been assigned a short address.”		Editorial	Moderate
29	Need to combine the PCA alternatives with the general CSMA-CA flow chart.	Pat knows who will work on it.		Editorial	Moderate
30	Merge FastA capabilities field figure with existing capabilities field figure.	Finished.	Resolved	Editorial	Low
31	Is GTSR in the acronyms?			Editorial	Low
32	What where they smoking when they added Enhanced Beacon information to MLME-SET.request?	Delete from here, it is in MLME-START.request.		Editorial	High
33	sduLength is not passed in the MLME, or indeed the length of any multi-octet field.	Delete from this MLME, check to see if msduLength is used by 802.1.
34	For what possible reason is the MR-FSK symbol timing in the MAC clause?	Move to MR-FSK clause		Editorial	Low
35	Split PHYs into one PHY per clause.	Do it.	Resolved	Editorial	High
36	Is LE needed as an acronym			Editorial	Low
37	There are too many definitions, lets create a glossary			Editorial	Low
38	Number figures and tables by Clause	Use Michelle's suggestion		Editorial	Moderate
39	Rename frame control field for other frame.	Do it.		Editorial	Low
40	Rename all PIB attributes for new amendments and move to a single table?	Split PIB table into Generic, PHY specifics		Editorial	Low
41	What is a simple address and shouldn't this be defined along side the other addresses?			Technical	Moderate
42	LL Beacon references 2450 MHz PHY, yet none exists	Delete the equation and figure out what the hell this is supposed to mean.		Technical	Moderate
43	GACK is referred to as a GACK frame, yet it is an IE. Can it be sent with other information in a frame? Shall it only be sent alone?			Technical	Moderate
44	Is it going to be GACK, group ACK, G-ACK?			Editorial	Low
45	Group ACK flags is referenced in the MAC protocol, but it is not a field name in the Group ACK IE.			Technical	Moderate
46	Move LL generic to the generic frame format. Move the LL frames to the command section (perhaps?).			Editorial	Low
47	Delete MHR and MFR from command figures, i.e., only specify the Payload field?			Editorial	Low
48	Is it going to be RZ or Rendezvous?			Editorial	Low
49	Serious problems with the Group ACK IE definition		James: where is this problem and why is it a problem?	Technical	High	Rolfe
50	Why doesn't the numbering for IEs start at zero? Was there some master plan?			Technical	Moderate
51	Are all the IEs referenced in the text? If they are defined in the frame formats there needs to be some mention of how they are used.			Technical	Moderate
52	MR-FSK Generic PHY IE is defined but not used	Suggest delete.		Technical	Moderate
53	IEID in Beacon frame only includes short IEs, is that correct			Technical	Moderate
54	The Enhanced Beacon IE has a field with PIB IDs, but no such things exist	Suggest delete.	check to see if delete would cause other problems	Technical	High	Rolfe
55	The “Enhanced Beacon Request command IE per enabled attribute” table can't be in the right place and it is likely incorrectly defined coexistence specification	Suggest delete.	change to editorial, seems out of place, put into 5.1? or 5.3.7.2.2?	Technical	High	Rolfe
56	The SUN PHY IE has a length calculation that we likely don't need.	Suggest delete.		Technical	Moderate
57	Can we kill the Generic PHY?	Suggest delete.	Phil to respond diplomatically	Technical	High	Beecher
58	Should we have subclauses for all the fields in the commands?	Suggest we delete the subclause headings to be consistent with other usage		Editorial	Low
59	In RIT transmissions, it says “Also at this point, the device may set macRITPeriod parameter to zero (RIT off) at the discretion of the next higher layer. If this is the case, it shall continue to stop periodic transmission of RIT data request command and become always active until macRITPeriod parameter is set to nonzero value by the next higher layer again.	When you stop laughing at “continue to stop”, there are a lot of things that need to be fixed here.	change to editorial, reword	Technical	High	Kojima
60	RIT text needs to be cleaned up with the T, T0 and N to match the text.
61	The RIT IE is defined, but it is not used anywhere. Do we need it?	Suggest delete.		Technical	Moderate
62	The Discovery Parameters field of the LL Discover Response command is undefined	Define the field	mark as deprecate, if party wishes to keep they must fix	Technical	High	??
63	All of the LL MAC commands are incorrectly defined	Define the Command Payload fields of the commands	mark as deprecate, if party wishes to keep they must fix	Technical	High	??
64	What's with all the new MAC commands being mandatory? That makes older devices non-compliant, e.g., this is not backwards compatible	Change the mandatory nature of the new commands to match the optional feature that they are used to implement.	mark as deprecate, if party wishes to keep they must fix	Technical	High	??
65	In “The CTS command may be sent using LL MAC Command frames.” <ed note: I chnaged “can” to “may”, perhaps it should be “shall”>	What is correct here?	mark as deprecate, if party wishes to keep they must fix	Technical	High	??
66	Replace “command frame” with just “command”	Please be consistent.		Editorial	Low
67	How should we list what MAC frames are mandatory for which types of devices?	In the table (similar to RFD and FFD), separate text in MAC protocol?		Editorial	Moderate
68	Enumerations are not given values, that is why they are enumerations	See the table describing “MLME-DSME-GTS.indication parameters” for an example	need to search for all occurrences and resolve	Technical	High	All
69	Primitive parameters do no have associated length parameters. This is a logical interface.	Delete all length parameters for their associated primitive parameters		Editorial	Moderate
70	Do we need to name commands LL, DSME and AMCA?	If there isn't a reason for this, delete the extra modifiers		Editorial	Low
71	We don't really define what the broadcast address is in the base standard, it is used but not defined (as far as I can see).	Define the broadcast extended address and broadcast short address (is there a broadcast simple address?)		Technical	Low
72	Add editorial convention, figures are referred to by saying “as illustrated in”, tables are referred to by saying “as shown in”	Change our style guide and update the draft.		Editorial	Low
73	Figure “SAB sub-block in channel hopping” seems to have problems in that the SAB sub-block index is 15 bits rather than 14 bits. And the SAB sub-block unit doesn't seem right.	What is correct here?		Technical	Moderate
74	Should it be sub-block or subblock	Ask Michelle for definitive answer		Editorial	Low
75	Fragmentation relies on the ACK to begin fragmentation, but this is insufficient to guarantee that the peer MAC is ready to begin the process.	This needs discussion	address at f-f meeting in Waikoloa	Technical	High	Rolfe
76	The I-ACK Content field should be 4 bits, not 8 bits.	I fixed this, is it OK?	Ben to look	Technical	High	Rolfe
77	In the I-ACK Content field, is it acceptable to set bit 0 to zero and bits 1-3 to one?	If so, what does that mean?	Ben to look	Technical	High	Rolfe
78	In the LQI field, at the very least, this needs to be stated that the field is encoded from low to high or high to low and what this means.	Add text that describes this	LQI in I-ACK?	Technical	High	Callaway
79	I simplified the Fragments Received field, is it correct?	Please review	James to send text to Ben, Ben to look	Technical	High	Rolfe
80	How is it determined that a 2 or 4 octet FCS will be used? Where is this defined? Please don't say something stupid like it is a PIB entry.	Discuss.	Phil to resolve w/o saying something stupid	Technical	High	Beecher
81
82
83
84
85
86
87
88
89
90
91
92
93

## Sheet2
Recommended Deprecation list					For sure we keep.
PSSS PHY					O-QPSK
MPSK PHY					BPSK
LLDN					MR-FSK
ASK					MR-OFDM
MR-OQPSK (DSSS)					UWB
AMCA					GFSK (MSK becomes GFSK with option)
					TVWS
					RCC
					LEICIM DSSS
					LEICIM FSK
					TSCH
					DSME
					CSS
					Access methods (all, inc. PCA)
					Fragmentation
					Multi-purpose frame (for TSCH)
					Header IEs
					Payload IEs
					64 bit addressing