## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: TG4r May 2014 Closing Report
Date Submitted: May 2014
Source: SS Dietmar Eggert, Atmel
Koenigsbruecker Str. 61, Dresden, Germany
Abstract: Opening and support of session
Purpose: Overview of activities during the meeting
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Closing Report for TG 4r Sessions
Waikoloa, US
May 2014

## Slide 3: Outlook
Year |  | 2014 |  |  |  |  | 2015 |  |  |  |  | 
Month |  | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11
Approval of PAR and CSD |  |  |  |  |  |  |  |  |  |  |  | 
Technical Guidance Document |  |  |  |  |  |  |  |  |  |  |  | 
Call for Proposal | Call for Interest |  |  |  |  |  |  |  |  |  |  | 
 | Call for Preliminary Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Presentation of Preliminary Propos. |  |  |  |  |  |  |  |  |  |  | 
 | Call for Final Proposals |  |  |  |  |  |  |  |  |  |  | 
Drafting | Presentation of Final Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Alignment of Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Build the first Draft for WG Ballot |  |  |  |  |  |  |  |  |  |  | 
WG Letter Ballot |  |  |  |  |  |  |  |  |  |  |  | 
Sponsor Ballot |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4: Status
May 2014 Meeting:
Agreed upon procedure for Call for Proposal (15-14-0296-01-004r-draft of call-for-proposals.docx)
Started Draft for TGD (15-14-0297-01-004r-tg4r draft for TGD for TG4r.docx)
Initiated a call for intent to submit a preliminary proposal(s) (During the meeting Thu PM1 and to be distributed over TG4r reflector by 05/16 by the TG Chair)

## Slide 5: Next Steps
May to July 2014 Conf. Calls:
Consolidate into formal TGD over 3 conference calls towards the July Meeting
June 05th - June 19th - July 3rd 06:00am PDT / 03.00pm CET / 10.00pm JPN (06/05, 07/03) 10:00pm PDT / 07.00am CET / 02.00pm JPN (06/19)
July 2014 Meeting:
Finalize TGD along with the received intent to submit preliminary proposal(s)
Issue Call for Preliminary Proposal(s)
.