## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: TG4r July 2014 Closing Report
Date Submitted: July 2014
Source: SS Dietmar Eggert, Atmel
Koenigsbruecker Str. 61, Dresden, Germany
Abstract: Closing of the Meetings
Purpose: Overview of activities during the meeting
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Closing Report for TG 4r Sessions
San Diego, US
July 2014

## Slide 3: Status
Conducted 4 meetings this week (Wed and Thu)
Work focused on Technical Guidelines Document (15-14-0297-01-004r-tg4r draft for TGD for TG4r.docx)
Updated Call for Proposal Time Lines (15-14-0296-02-004r-draft of call-for-proposals.docx)
Extend time line for call for intend to Sept’14
New Time Line for Call for Preliminary Proposal – Sept’14 Meeting (Submission deadline: Nov’14)
New Time Line for Call for Proposal – Nov’14 Meeting (Submission deadline: Jan’15)

## Slide 4: Next Steps
July’14 to Sept’14
Consolidate TGD over 3 conference calls towards the September Meeting
Aug 07th - Aug’21st – Sep 4th 06:00am PDT / 03.00pm CET / 10.00pm JPN (08/07, 09/04) 10:00pm PDT / 07.00am CET / 02.00pm JPN (08/21)
September 2014 Meeting:
Finalize TGD along with the received intent to submit preliminary proposal(s)
Issue Call for Preliminary Proposal(s)
.

## Slide 5: Outlook
Year |  | 2014 |  |  |  |  | 2015 |  |  |  |  | 
Month |  | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11
Approval of PAR and CSD |  |  |  |  |  |  |  |  |  |  |  | 
Technical Guidance Document |  |  |  |  |  |  |  |  |  |  |  | 
Call for Proposal | Call for Interest |  |  |  |  |  |  |  |  |  |  | 
 | Call for Preliminary Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Presentation of Preliminary Propos. |  |  |  |  |  |  |  |  |  |  | 
 | Call for Final Proposals |  |  |  |  |  |  |  |  |  |  | 
Drafting | Presentation of Final Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Alignment of Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Build the first Draft for WG Ballot |  |  |  |  |  |  |  |  |  |  | 
WG Letter Ballot |  |  |  |  |  |  |  |  |  |  |  | 
Sponsor Ballot |  |  |  |  |  |  |  |  |  |  |  |